## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Ausgram-II | Burdwan Division | BAKSIBAD POGRAM PIPED WATER SUPPLY SCHEME | SM/18408 | New | Material Requisition To Resource Division |  |  | RTOR000418/2023-2024 | 3864/BWD | 01/09/2023 | 01/09/2023 | Resource Division | 128.72 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Ausgram-II | Burdwan Division | BAKSIBAD POGRAM PIPED WATER SUPPLY SCHEME | SM/18408 | New | Material Requisition To Resource Division |  |  | RTOR000223/2023-2024 | 2155/BWD | 10/05/2023 | 10/05/2023 | Resource Division | 20.29 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Ausgram-II | Burdwan Division | BAKSIBAD POGRAM PIPED WATER SUPPLY SCHEME | SM/18408 | New | Material Requisition To Resource Division |  |  | RTOR000644/2023-2024 | 5110/BWD | 23/11/2023 | 23/11/2023 | Resource Division | 22.15 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Ausgram-II | Central Mechanical | BAKSIBAD POGRAM PIPED WATER SUPPLY SCHEME | SM/18408 | New | Quotation for new service connection at Baksibad PWSS TW-2. |  |  | BILL/01191/2024-2025 | BP-2024-25-412 | 11/12/2024 | 11/12/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.75 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Ausgram-II | Central Mechanical | BAKSIBAD POGRAM PIPED WATER SUPPLY SCHEME | SM/18408 | New | NEW SERVICE CONNECTION FOR BAKSIBAD PWSS PH-1. |  |  | BILL/03140/2023-2024 | BP-2023-24-652 | 20/03/2024 | 20/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 12.55 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Ausgram-II | Burdwan Division | BAKSIBAD POGRAM PIPED WATER SUPPLY SCHEME | SM/18408 | New | BAKSIBAD POGRAM Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 600 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Ausgram-II Block, District:- Purba-Bardhaman [NEW SCHEME]_2ND CALL |  |  | ORD/000484/2023-2024 | 3504/BWD | 10/08/2023 | 31/10/2025 | M/S PIONEER CONSTRUCTION | 691.24 | 162.06 | 23.45 | 40
7 | PURBA BARDHAMAN | Ausgram-II | Central Mechanical | BAKSIBAD POGRAM PIPED WATER SUPPLY SCHEME | SM/18408 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Chora, Kalaijhuti & others water supply scheme under Ausgram-2 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Driller In-Charge | JUNIOR ENGINEER | ORD/000143/2024-2025 | 2405/CMD | 02/08/2024 | 31/10/2024 | NABAUDYOG ELECTRICAL ENGINEERING CO-OPERATIVE SOCIETY LTD | 95.26 | 0 | 0 | 80
8 | PURBA BARDHAMAN | Ausgram-II | Durgapur W/S Division | BAKSIBAD POGRAM PIPED WATER SUPPLY SCHEME | SM/18408 | New | FORMAL WORK ORDER FOR Balance work for construction of boundary wall, dismantling concrete road including mending work, construction of approach road by fillup stone dust, bolders on low load at OHR site and etc allied works under Bakshibad PWSS, Ausgram-II Block under DURGAPUR W/S DIVISION,PHE DTE. | Assistant Engineer-II | JUNIOR ENGINEER-1 | ORD/000264/2024-2025 | 256/DWSD | 11/02/2025 | 01/01/2026 | M/S. UNIT CONSTRUCTION | 122.59 | 29.85 | 24.35 | 95
9 | PURBA BARDHAMAN | Ausgram-II | Central Mechanical | BAKSIBAD POGRAM PIPED WATER SUPPLY SCHEME | SM/18408 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Baksibad Pogram Water Supply Scheme [ Block- Ausgram-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | JUNIOR ENGINEER | ORD/000742/2023-2024 | 4052/CMD | 29/08/2023 | 04/03/2025 | JAGANNATH ENTERPRISE | 29.61 | 12.33 | 41.65 | 80
Total | [13 empty] | 1126.16 | 204.24 | 18.14