## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Ausgram-II | Burdwan Division | PANDUK PIPED WATER SUPPLY SCHEME | SM/18445 | New | Material Requisition To Resource Division |  |  | RTOR000363/2023-2024 | 2197/BWD | 12/05/2023 | 12/05/2023 | Resource Division | 7.25 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Ausgram-II | Burdwan Division | PANDUK PIPED WATER SUPPLY SCHEME | SM/18445 | New | Material Requisition To Resource Division |  |  | RTOR000415/2023-2024 | 3840/BWD | 01/09/2023 | 01/09/2023 | Resource Division | 55.98 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Ausgram-II | Burdwan Division | PANDUK PIPED WATER SUPPLY SCHEME | SM/18445 | New | Material Requisition To Resource Division |  |  | RTOR000565/2023-2024 | 4919/BWD | 10/11/2023 | 10/11/2023 | Resource Division | 53.67 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Ausgram-II | Durgapur W/S Division | PANDUK PIPED WATER SUPPLY SCHEME | SM/18445 | New | Acceptance cum Formal Work Order for Sinking of 300X200 mm dia TW,Pump House,Boundary wall concrete road & bituminous road restoration ,Jack pushing with laying of MS Pipe FHTC and land development of H/W Site drain & Internal pathway laying of MS pipe under Bhedia PWSS (JJM),Block-Aushgram-II,Dist-Purba Bardhaman under Durgapur W/S Division,PHE Dte. | Assistant Engineer-II | JUNIOR ENGINEER-2 | ORD/000170/2024-2025 | 1611/DWSD | 26/11/2024 | 24/02/2025 | SUPRIYA RAY | 87.54 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Ausgram-II | Burdwan Division | PANDUK PIPED WATER SUPPLY SCHEME | SM/18445 | New | Material Requisition To Resource Division |  |  | RTOR000768/2023-2024 | 204/BWD | 10/01/2024 | 10/01/2024 | Resource Division | 12.89 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Ausgram-II | Central Mechanical | PANDUK PIPED WATER SUPPLY SCHEME | SM/18445 | New | Quotation for new service connection for Panduk PWSS PH 1. |  |  | BILL/00221/2024-2025 | BP-2024-25-112 | 28/05/2024 | 28/05/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.47 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Ausgram-II | Central Mechanical | PANDUK PIPED WATER SUPPLY SCHEME | SM/18445 | New | Quotation for new service connection for Panduk PWSS PH 2. |  |  | BILL/00222/2024-2025 | BP-2024-25-113 | 28/05/2024 | 28/05/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 9.92 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Ausgram-II | Central Mechanical | PANDUK PIPED WATER SUPPLY SCHEME | SM/18445 | New | Quotation for new service connection for Panduk PWSS PH 3. |  |  | BILL/00223/2024-2025 | BP-2024-25-114 | 28/05/2024 | 28/05/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.39 | 0 | 0 | 0
9 | PURBA BARDHAMAN | Ausgram-II | Burdwan Division | PANDUK PIPED WATER SUPPLY SCHEME | SM/18445 | New | PANDUK Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 500 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Ausgram-II Block, District:- Purba-Bardhaman [NEW SCHEME]_2ND CALL |  |  | ORD/000483/2023-2024 | 3505/BWD | 10/08/2023 | 01/01/2026 | M/S PIONEER CONSTRUCTION | 722.29 | 397.52 | 55.04 | 80
10 | PURBA BARDHAMAN | Ausgram-II | Central Mechanical | PANDUK PIPED WATER SUPPLY SCHEME | SM/18445 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1, 2 & 3 at PANDUK Water Supply Scheme [ Block- AUSGRAM-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | JUNIOR ENGINEER | ORD/000794/2023-2024 | 4082/CMD | 29/08/2023 | 01/05/2025 | PADMA ENGINEERING CO. | 41.68 | 0 | 0 | 67
11 | PURBA BARDHAMAN | Ausgram-II | Durgapur W/S Division | PANDUK PIPED WATER SUPPLY SCHEME | SM/18445 | New | FORMAL WORK ORDER FOR Balance work for Construction of Boundary wall, dismantling concrete road including mending work, construction of approach road by fill-up stone dust, bolders on lowland at OHR site and etc. allied work under PANDUK PWSS, Block-Ausgram-II under DURGAPUR W/S DIVISION, PHE DTE. | Assistant Engineer-II | JUNIOR ENGINEER-1 | ORD/000265/2024-2025 | 257/DWSD | 11/02/2025 | 12/05/2025 | M/S PIONEER CONSTRUCTION | 124.43 | 32.46 | 26.09 | 100
Total | [13 empty] | 1124.5 | 429.98 | 38.24