## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Galsi-I | Burdwan Division | PURANGAN PIPED WATER SUPPLY SCHEME | SM/18446 | New | Sub Surface Based Piped Water Supply Scheme with LDS, FHTC, Construction of different capacity RCC OHRs with 20.0 mtr. with Staging height including soil investigation, Construction of CWR, Chlorine Room, Guard Room, Sub Station Building, High Lift Pump House Boundary walls with gates, land development, drain and internal pathway of PURANGAN Piped Water Supply Scheme under Galsi-II Block, District:- Purba-Bardhaman [NEW SCHEME]_ 2ND CALL |  |  | ORD/000459/2023-2024 | 3441/BWD | 08/08/2023 | 07/08/2025 | MANASH GHOSH | 1312.95 | 401.09 | 30.55 | 65
2 | PURBA BARDHAMAN | Galsi-I | Burdwan Division | PURANGAN PIPED WATER SUPPLY SCHEME | SM/18446 | New | Hydro-geological study of Sub Surface Water Flow/Storage Characteristics for Creation of Sustainable Source and Estimation of Sustainable Yield (5 Nos of Schemes) in Purba Bardhaman District, West Bengal towards implementation of water supply project. |  |  | ORD/000872/2023-2024 | 5324/BWD | 01/12/2023 | 30/03/2024 | THE REGISTRAR JADAVPUR UNIVERSITY | 113.34 | 21.53 | 19 | 100
3 | PURBA BARDHAMAN | Galsi-I | Burdwan Division | PURANGAN PIPED WATER SUPPLY SCHEME | SM/18446 | New | Material Requisition To Resource Division |  |  | RTOR000373/2023-2024 | 2197/BWD | 12/05/2023 | 12/05/2023 | Resource Division | 10.26 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Galsi-I | Burdwan Division | PURANGAN PIPED WATER SUPPLY SCHEME | SM/18446 | New | Material Requisition To Resource Division |  |  | RTOR000436/2023-2024 | 3835/BWD | 01/09/2023 | 01/09/2023 | Resource Division | 24.5 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Galsi-I | Durgapur W/S Division | PURANGAN PIPED WATER SUPPLY SCHEME | SM/18446 | New | Acceptance cum Formal Work Order for Additional work of Construction of CWR cum Pump House with MS Structural work, Substation, Chlorine Room etc, Laying of MS pipe and necessary allied works of Surface Based Purangan and 11 Nos Mouzas Sub Surface based Pipe W/S Scheme (JJM) under Galsi-I Block, Dist- Purba Bardhaman under Durgapur W/S Division, PHE Dte. | Assistant Engineer-II | JUNIOR ENGINEER-2 | ORD/000124/2024-2025 | 1112/DWSD | 02/08/2024 | 30/11/2024 | MANASH GHOSH | 98.87 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Galsi-I | Central Mechanical | PURANGAN PIPED WATER SUPPLY SCHEME | SM/18446 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for OHR SITE of Zone-1, 2, & 3 at PURANGAN Water Supply Scheme [ BLOCK- Galsi-I ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | JUNIOR ENGINEER | ORD/000562/2024-2025 | 3099/CMD | 11/12/2024 | 19/12/2025 | CHOUDHURY ENTERPRISE | 38.16 | 0 | 0 | 32
7 | PURBA BARDHAMAN | Galsi-I | Durgapur W/S Division | PURANGAN PIPED WATER SUPPLY SCHEME | SM/18446 | New | Formal Work Order for Additional work of Soil investigation & construction of CWR/Pump House etc, Land development of H/W Site,drain & internal Path Way, Concrete Road Restoration,FHTC with Platform with necessary allied Works of Sub Surface Based PURANGAN Pipe W/S Scheme (JJM) under Galsi - I Block, Dist - Purba- Bardhaman ,under Durgapur Water Supply Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | JUNIOR ENGINEER-2,Junior Engineer_3 | ORD/000163/2024-2025 | 1521/DWSD | 11/11/2024 | 06/11/2025 | MANASH GHOSH | 789.87 | 0 | 0 | 75
8 | PURBA BARDHAMAN | Galsi-I | Durgapur W/S Division | PURANGAN PIPED WATER SUPPLY SCHEME | SM/18446 | New | Acceptance cum Formal Work Order for the work of Sinking of 3 Nos 300 x 200 mm dia T/W 150 mtr and 5 nos 200 x 200 mm dia River Bank T/W 51 mtr with Construction of 3 nos P/H cum switch room under chlorine room under PURANGAN PWSS (JJM), Block:- Galsi-I , Dist- Purba Bardhaman. | Assistant Engineer-I,Assistant Engineer-II | JUNIOR ENGINEER-2 | ORD/000309/2023-2024 | 372/DWSD | 15/03/2024 | 13/06/2024 | MANASH GHOSH | 90.55 | 65.91 | 72.79 | 53
9 | PURBA BARDHAMAN | Galsi-I | Durgapur W/S Division | PURANGAN PIPED WATER SUPPLY SCHEME | SM/18446 | New | Formal Work Order for Road Restoration work of PWD Road for laying of Rising Main of 11 Nos Mouzas and Purangan PWSS under Sub Surface Based 11 Nos Mouzas Pipe W/S Scheme (JJM), Galsi-I Block, Dist- Purba Bardhaman under Durgapur W/S Division, PHE Dte. | Assistant Engineer-II | JUNIOR ENGINEER-2,Junior Engineer_3 | ORD/000140/2024-2025 | 1290/DWSD | 06/09/2024 | 08/06/2025 | MANASH GHOSH | 216.51 | 0 | 0 | 80
10 | PURBA BARDHAMAN | Galsi-I | Durgapur W/S Division | PURANGAN PIPED WATER SUPPLY SCHEME | SM/18446 | New | Acceptance cum Formal Work Order for Preparation and Submission of Structural Design Calculation (Civil) & Structural drawing of Proposed CWR with M.S Structural Pump House over cwr, WBSEDCL Mettering Room and - PDB Room -2 Nos, Transformer yeard -2 nos, Chlorin Room -1 No with General Arrangement Drawing of Internal Road - Drain & necessary Soil investigation at Intake Site of "PURANGAN (Zone-I, II, III) and 11 Nos. Mouzas PWSS under Durgapur W/s Division, PHE Dte. | Assistant Engineer-II | JUNIOR ENGINEER-2 | ORD/000190/2024-2025 | 1607/DWSD | 26/11/2024 | 10/01/2025 | MANASH GHOSH | 9.46 | 9.46 | 100 | 100
11 | PURBA BARDHAMAN | Galsi-I | Burdwan Division | PURANGAN PIPED WATER SUPPLY SCHEME | SM/18446 | New | Material Requisition To Resource Division |  |  | RTOR000766/2023-2024 | 192/BWD | 10/01/2024 | 10/01/2024 | Resource Division | 24.5 | 0 | 0 | 0
12 | PURBA BARDHAMAN | Galsi-I | Central Mechanical | PURANGAN PIPED WATER SUPPLY SCHEME | SM/18446 | New | Quotation for new service connection at Purangan. |  |  | BILL/01083/2024-2025 | BP-2024-25-403 | 22/11/2024 | 22/11/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.32 | 0 | 0 | 0
13 | PURBA BARDHAMAN | Galsi-I | Central Mechanical | PURANGAN PIPED WATER SUPPLY SCHEME | SM/18446 | New | Supply, installation, commissioning of Electro-Mechanical and instrumentation components at newly constructed Boosting Station under Purangan & 11 nos. Mouza water supply scheme under Central Mechanical Division PHE Dte. | ASSISTANT ENGINEER | Junior Engineer | ORD/000774/2024-2025 | 479/CMD | 06/02/2025 | 22/04/2025 | S.P. CONSTRUCTION | 135.24 | 0 | 0 | 0
14 | PURBA BARDHAMAN | Galsi-I | Central Mechanical | PURANGAN PIPED WATER SUPPLY SCHEME | SM/18446 | New | Providing Mechanical/Electrical equipment with all ancillaries and auxiliaries including intake (Low lift) pumping machineries, High Lift pumping machineries, 0-1 kg/hour gaseous chlorination system and illumination arrangement of Purangan & 11 nos. mouza Sub-Surface Based Piped Water Supply Scheme under Purba Bardhaman District PHE Dte. | ASSISTANT ENGINEER | Junior Engineer | ORD/000003/2025-2026 | 905/CMD | 04/04/2025 | 18/06/2025 | WEST BENGAL ENGINEERING CO. | 317.99 | 0 | 0 | 40
15 | PURBA BARDHAMAN | Galsi-I | Durgapur W/S Division | PURANGAN PIPED WATER SUPPLY SCHEME | SM/18446 | New | Quotation for new electricity connection for Purbangram PWSS under DWSD PHE Dte |  |  | BILL/00239/2024-2025 | BP-2024-25-111 | 09/01/2025 | 09/01/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 11.71 | 0 | 0 | 0
16 | PURBA BARDHAMAN | Galsi-I | Durgapur W/S Division | PURANGAN PIPED WATER SUPPLY SCHEME | SM/18446 | New | Quotation money for new service connection at PURANGAN PWSS Head work site under DWSD PHE Dte |  |  | BILL/00279/2024-2025 | BP-2024-25-120 | 04/02/2025 | 04/02/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 51.44 | 0 | 0 | 0
Total | [13 empty] | 3249.66 | 497.99 | 15.32