## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Galsi-II | Burdwan Division | TAHERPUR PIPED WATER SUPPLY SCHEME | SM/18478 | New | Material Requisition To Resource Division |  |  | RTOR000329/2023-2024 | 2197/BWD | 12/05/2023 | 12/05/2023 | Resource Division | 55.9 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Galsi-II | Burdwan Division | TAHERPUR PIPED WATER SUPPLY SCHEME | SM/18478 | New | Material Requisition To Resource Division |  |  | RTOR000400/2023-2024 | 3831/BWD | 01/09/2023 | 01/09/2023 | Resource Division | 269.94 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Galsi-II | Durgapur W/S Division | TAHERPUR PIPED WATER SUPPLY SCHEME | SM/18478 | New | Formal Work Order for the work of " Sinking of 3 nos. 300 x 200 mm dia T/W- 150 mtr and 7 nos 200 x 200 mm dia River Bank T/W- 51 mtr with Construction of P/H cum switch room under Taherpur PWSS (JJM) Block- Galsi-II, Dist- Purba Bardhaman under Durgapur W/S Division, PHE Dte. | Assistant Engineer-II | JUNIOR ENGINEER-1 | ORD/000317/2023-2024 | 377/DWSD | 15/03/2024 | 13/06/2024 | S & P ENTERPRISE | 0 | 0 | NAN | 0
4 | PURBA BARDHAMAN | Galsi-II | Durgapur W/S Division | TAHERPUR PIPED WATER SUPPLY SCHEME | SM/18478 | New | Acceptance cum Formal Work Order for the work of " Construction of Additional Store Room at Nababhat Office Building under Galsi-II Pipe Water Supply Scheme (JJM) under Durgapur W/S Division, PHE Dte | Assistant Engineer-II | JUNIOR ENGINEER-2,Junior Engineer_3 | ORD/000046/2024-2025 | 764/DWSD | 06/06/2024 | 04/09/2024 | KIRON ENTERPRISE | 17.08 | 0 | 0 | 30
5 | PURBA BARDHAMAN | Galsi-II | Burdwan Division | TAHERPUR PIPED WATER SUPPLY SCHEME | SM/18478 | New | Hydro-geological study of Sub Surface Water Flow/Storage Characteristics for Creation of Sustainable Source and Estimation of Sustainable Yield (5 Nos of Schemes) in Purba Bardhaman District, West Bengal towards implementation of water supply project. |  |  | ORD/000872/2023-2024 | 5324/BWD | 01/12/2023 | 30/03/2024 | THE REGISTRAR JADAVPUR UNIVERSITY | 113.34 | 32.86 | 29 | 100
6 | PURBA BARDHAMAN | Galsi-II | Durgapur W/S Division | TAHERPUR PIPED WATER SUPPLY SCHEME | SM/18478 | New | Acceptance cum Formal Work Order for the work of Trial bore with necessary allied work and supply and delivery of office furnitures for the new office setup of the EE/DWSD/PHE Dte. at Nababhat,Purba bardhaman.in connection with Taherpur W/S Scheme under Durgapur Water Supply Division, PHE Dte. | Assistant Engineer-II | JUNIOR ENGINEER-2 | ORD/000038/2024-2025 | 750/DWSD | 05/06/2024 | 03/09/2024 | K.M. ENTERPRISE | 3.83 | 3.82 | 99.76 | 100
7 | PURBA BARDHAMAN | Galsi-II | Central Mechanical | TAHERPUR PIPED WATER SUPPLY SCHEME | SM/18478 | New | Quotation for new service connection for Taherpur PWSS TW - 2 (Z-I) |  |  | BILL/00296/2024-2025 | BP-2024-25-146 | 19/06/2024 | 19/06/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.26 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Galsi-II | Central Mechanical | TAHERPUR PIPED WATER SUPPLY SCHEME | SM/18478 | New | Quotation for new service connection at Taherpur PWSS TW-3 |  |  | BILL/01092/2024-2025 | BP-2024-25-404 | 22/11/2024 | 22/11/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 9.08 | 0 | 0 | 0
9 | PURBA BARDHAMAN | Galsi-II | Durgapur W/S Division | TAHERPUR PIPED WATER SUPPLY SCHEME | SM/18478 | New | Formal Work Order for the work of Sinking of 3 nos 300 x 200mm dia Tube Well-150 mtr and 7 Nos 200 x 200 mm dia River Bank Tube Well- 51 mtr with Construction of Pump House Cum Switch Room Chlorine Room under TAHERPUR PWSS (JJM) Block- Galsi-II, Distric- Purba Bardhaman under Durgapur W/S Division, PHE Dte | Assistant Engineer-II | JUNIOR ENGINEER-2,Junior Engineer_3 | ORD/000093/2024-2025 | 1000/DWSD | 11/07/2024 | 13/12/2025 | S & P ENTERPRISE | 102.54 | 0 | 0 | 60
10 | PURBA BARDHAMAN | Galsi-II | Durgapur W/S Division | TAHERPUR PIPED WATER SUPPLY SCHEME | SM/18478 | New | Formal Work Order for Laying of Rising Main including Jack Pushing and construction of Pipe Carring Bridge with Pipe supporting structure under TAHERPUR and KHANO Piped Water Supply Scheme under Durgapur W/S Division, PHE Dte. | Assistant Engineer-II | JUNIOR ENGINEER-2,Junior Engineer_3 | ORD/000158/2024-2025 | 1506/DWSD | 05/11/2024 | 29/06/2025 | MANASH GHOSH | 1114.23 | 0 | 0 | 60
11 | PURBA BARDHAMAN | Galsi-II | Central Mechanical | TAHERPUR PIPED WATER SUPPLY SCHEME | SM/18478 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for OHR SITE of Zone-1, 2, & 3 at TAHERPUR Water Supply Scheme [ BLOCK- Galsi-II ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | JUNIOR ENGINEER | ORD/000560/2024-2025 | 3102/CMD | 11/12/2024 | 09/02/2025 | M/S, S.S. ENTERPRISE. | 38.16 | 0 | 0 | 28
12 | PURBA BARDHAMAN | Galsi-II | Central Mechanical | TAHERPUR PIPED WATER SUPPLY SCHEME | SM/18478 | New | Supply, installation, commissioning of Electro-Mechanical and instrumentation components at newly constructed Boosting Station under Taherpur-khano sub surface water supply scheme under Central Mechanical Division PHE Dte. | ASSISTANT ENGINEER | Junior Engineer | ORD/000784/2024-2025 | 480/CMD | 06/02/2025 | 22/04/2025 | GLACIER ENGINEERING CO | 105.71 | 0 | 0 | 0
13 | PURBA BARDHAMAN | Galsi-II | Durgapur W/S Division | TAHERPUR PIPED WATER SUPPLY SCHEME | SM/18478 | New | Acceptance cum Formal Work Order for Preparation and Submission of Structural Design Calculation (Civil) & Structural drawing of Proposed CWR with M.S Structural Pump House over cwr, WBSEDCL Mettering Room and - PDB Room -2 Nos, Transformer yeard -2 nos, Chlorin Room -1 No with General Arrangement Drawing of Internal Road - Drain & necessary Soil investigation at Intake Site of "THERPUR (Zone-I, II, III) and KHANO (Zone I & II) PWSS (6 Copy) under Durgapur W/s Division, PHE Dte. | Assistant Engineer-II | JUNIOR ENGINEER-2 | ORD/000192/2024-2025 | 1608/DWSD | 26/11/2024 | 10/01/2025 | DAFFODIL | 9.48 | 9.48 | 100 | 90
Total | [13 empty] | 1843.54 | 46.16 | 2.5