## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Galsi-I | Burdwan Division | Sub-Surface Water based Piped Water Supply Scheme for 11 nos. Mouzas under Galsi-I Block | SM/18679 | New | Piped Water Supply Scheme for different Mouzas works related (LDSs, Rising Mains, FHTCs, Constn. CWR, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) under Galsi-I Block, District:- Purba-Bardhaman [NEW SCHEME] (For Pursha, Uchhagram & Rampur Jurisdiction) |  |  | ORD/000475/2023-2024 | 3761/BWD | 29/08/2023 | 28/08/2026 | S & P ENTERPRISE | 1827.37 | 396.15 | 21.68 | 45
2 | PURBA BARDHAMAN | Galsi-I | Burdwan Division | Sub-Surface Water based Piped Water Supply Scheme for 11 nos. Mouzas under Galsi-I Block | SM/18679 | New | Hydro-geological study of Sub Surface Water Flow/Storage Characteristics for Creation of Sustainable Source and Estimation of Sustainable Yield (5 Nos of Schemes) in Purba Bardhaman District, West Bengal towards implementation of water supply project. |  |  | ORD/000872/2023-2024 | 5324/BWD | 01/12/2023 | 30/03/2024 | THE REGISTRAR JADAVPUR UNIVERSITY | 113.34 | 15.87 | 14 | 100
3 | PURBA BARDHAMAN | Galsi-I | Durgapur W/S Division | Sub-Surface Water based Piped Water Supply Scheme for 11 nos. Mouzas under Galsi-I Block | SM/18679 | New | Formal Work Order for Laying of Rising Main including Jack Pushing and construction of Pipe carring Bridge with Pipe supporting structure under PURANGRAM and 11 nos Mouzas Piped Water Supply Scheme under Durgapur W/S Division, PHE Dte. | Assistant Engineer-II | JUNIOR ENGINEER-2,Junior Engineer_3 | ORD/000157/2024-2025 | 1503/DWSD | 05/11/2024 | 05/03/2025 | MANASH GHOSH | 1075.24 | 58.36 | 5.43 | 50
4 | PURBA BARDHAMAN | Galsi-I | Central Mechanical | Sub-Surface Water based Piped Water Supply Scheme for 11 nos. Mouzas under Galsi-I Block | SM/18679 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Zone- Pursa, Uchchagram &, Rampur at 11 nos. Mouja Water Supply Scheme [ BLOCK- Galsi-I ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | JUNIOR ENGINEER | ORD/000605/2024-2025 | 3100/CMD | 11/12/2024 | 09/02/2025 | PROGRESSIVE ENGINEERS CO-OPERATIVE SOCIETY LIMITED | 37.78 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Galsi-I | Durgapur W/S Division | Sub-Surface Water based Piped Water Supply Scheme for 11 nos. Mouzas under Galsi-I Block | SM/18679 | New | Continuation order for Hiring of LUXURY Diesel Ambassador Car (Inspection Vehicle) for using of the Assistant Engineer-I under office of the Executive Engineer, Durgapur Water Supply Division, Public Health Engineering Dte at Fagupur, Nababhat, Purba Bardhaman for the period of 01.09.2024 to 28.02.2025 (6 Months)(Sl-03) | Assistant Engineer-II | JUNIOR ENGINEER-1 | ORD/000137/2024-2025 | 1250/DWSD | 30/08/2024 | 28/02/2025 | BIPLAB BANERJEE | 0.82 | 2.39 | 290.47 | 0
6 | PURBA BARDHAMAN | Galsi-I | Durgapur W/S Division | Sub-Surface Water based Piped Water Supply Scheme for 11 nos. Mouzas under Galsi-I Block | SM/18679 | New | Formal Work Order for Additional work of Soil investigation & construction of CWR/Pump House etc, Land development of H/W Site,drain & internal Path Way, Concrete Road Restoration,FHTC with Platform with necessary allied Works of Sub Surface Based PURANGAN Pipe W/S Scheme (JJM) under Galsi - I Block, Dist - Purba- Bardhaman ,under Durgapur Water Supply Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | JUNIOR ENGINEER-2,Junior Engineer_3 | ORD/000163/2024-2025 | 1521/DWSD | 11/11/2024 | 06/11/2025 | MANASH GHOSH | 789.87 | 0 | 0 | 75
7 | PURBA BARDHAMAN | Galsi-I | Durgapur W/S Division | Sub-Surface Water based Piped Water Supply Scheme for 11 nos. Mouzas under Galsi-I Block | SM/18679 | New | Hiring of LUXURY Diesel Ambassador Car (Inspection Vehicle) for using of the Assistant Engineer-I under office of the Executive Engineer, Durgapur Water Supply Division, Public Health Engineering Dte at Fagupur, Nababhat, Purba Bardhaman for the period of 01.03.2024 to 31.08.2024 (6 Months)(Sl-03) | Assistant Engineer-I,Assistant Engineer-II | JUNIOR ENGINEER-1,JUNIOR ENGINEER-2 | ORD/000296/2023-2024 | 269/DWSD | 29/02/2024 | 31/08/2024 | BIPLAB BANERJEE | 0.82 | 2.4 | 291.06 | 0
8 | PURBA BARDHAMAN | Galsi-I | Durgapur W/S Division | Sub-Surface Water based Piped Water Supply Scheme for 11 nos. Mouzas under Galsi-I Block | SM/18679 | New | Acceptance cum Formal Work Order for the work of Sinking of 3 nos 300 x 200 mm dia T/W 150 mtr and 20Nos 200 x 200 mm dia Riverbank T/W 51 mtr with Construction of P/H cum switch room chlorine room at Uchagram under 11 nos mouzas PWSS (JJM), Block:- Galsi-I, Dist- Purba Bardhaman. | Assistant Engineer-I,Assistant Engineer-II | JUNIOR ENGINEER-1,JUNIOR ENGINEER-2,Junior Engineer_3 | ORD/000310/2023-2024 | 373/DWSD | 15/03/2024 | 09/05/2026 | S & P ENTERPRISE | 72.51 | 34.25 | 47.23 | 50
9 | PURBA BARDHAMAN | Galsi-I | Durgapur W/S Division | Sub-Surface Water based Piped Water Supply Scheme for 11 nos. Mouzas under Galsi-I Block | SM/18679 | New | Continuation order for the work of Computer routine maintenance and software's installation including supply of computer peripherals and Stationeries etc. for use office under DWSD, PHE Dte (w.e.f 01.06.2024 to 30.05.2025) | Assistant Engineer-II | Contractual Junior Engineer_1,Contractual Junior Engineer_5,JUNIOR ENGINEER-1 | ORD/000025/2024-2025 | 575/DWSD | 22/04/2024 | 22/04/2025 | JOY GURU ENTERPRISE | 3.79 | 0 | 0 | 100
10 | PURBA BARDHAMAN | Galsi-I | Durgapur W/S Division | Sub-Surface Water based Piped Water Supply Scheme for 11 nos. Mouzas under Galsi-I Block | SM/18679 | New | Acceptance cum Formal Work Order for Design Engineering Services of Survey, General arrangement drawing, Pile foundation design and drawings, Pipe Pedestal and BOM, Structural design design and drawing, Fabrication drawings for 26 Numbers different dia meter pipe crossing Pipe Bridge at "PURANGAN (Zone-I, II, III), 11 Nos. Mouzas under PURSHA and UCHCHGRAM, SHILLA (Zone-I, II, III, IV), TAHER PUR (Zone-I, II, III) and KHANO (Zone-I and II) sites under Durgapur W/S Division,PHE Dte. | Assistant Engineer-II | JUNIOR ENGINEER-2 | ORD/000105/2024-2025 | 1058/DWSD | 25/07/2024 | 21/04/2025 | ASTER CONSULTANCY | 47.43 | 0 | 0 | 70
11 | PURBA BARDHAMAN | Galsi-I | Central Mechanical | Sub-Surface Water based Piped Water Supply Scheme for 11 nos. Mouzas under Galsi-I Block | SM/18679 | New | Supply, installation, commissioning of Electro-Mechanical and instrumentation components at newly constructed Boosting Station under Purangan & 11 nos. Mouza water supply scheme under Central Mechanical Division PHE Dte. | ASSISTANT ENGINEER | Junior Engineer | ORD/000774/2024-2025 | 479/CMD | 06/02/2025 | 22/04/2025 | S.P. CONSTRUCTION | 135.24 | 0 | 0 | 0
12 | PURBA BARDHAMAN | Galsi-I | Central Mechanical | Sub-Surface Water based Piped Water Supply Scheme for 11 nos. Mouzas under Galsi-I Block | SM/18679 | New | Providing Mechanical/Electrical equipment with all ancillaries and auxiliaries including intake (Low lift) pumping machineries, High Lift pumping machineries, 0-1 kg/hour gaseous chlorination system and illumination arrangement of Taherpur & Khano Sub-Surface Based Piped Water Supply Scheme under Purba Bardhaman District PHE Dte. | ASSISTANT ENGINEER | Junior Engineer | ORD/000002/2025-2026 | 904/CMD | 04/04/2025 | 18/06/2025 | SINHA ELECTRICALS | 329.09 | 0 | 0 | 40
13 | PURBA BARDHAMAN | Galsi-I | Central Mechanical | Sub-Surface Water based Piped Water Supply Scheme for 11 nos. Mouzas under Galsi-I Block | SM/18679 | New | Providing Mechanical/Electrical equipment with all ancillaries and auxiliaries including intake (Low lift) pumping machineries, High Lift pumping machineries, 0-1 kg/hour gaseous chlorination system and illumination arrangement of Purangan & 11 nos. mouza Sub-Surface Based Piped Water Supply Scheme under Purba Bardhaman District PHE Dte. | ASSISTANT ENGINEER | Junior Engineer | ORD/000003/2025-2026 | 905/CMD | 04/04/2025 | 18/06/2025 | WEST BENGAL ENGINEERING CO. | 317.99 | 0 | 0 | 40
14 | PURBA BARDHAMAN | Galsi-I | Durgapur W/S Division | Sub-Surface Water based Piped Water Supply Scheme for 11 nos. Mouzas under Galsi-I Block | SM/18679 | New | Continuation order for Hiring of LUXURY Diesel Ambassador Car (Inspection Vehicle) for using of the Assistant Engineer-I under office of the Executive Engineer, Durgapur Water Supply Division, Public Health Engineering Dte at Fagupur, Nababhat, Purba Bardhaman for the period of 01.06.2025 to 31.08.2025. | Assistangt Engineer,Assistant Engineer-I,Assistant Engineer-II,Assistant Engineer-II (Newly Charge takenover) | JUNIOR ENGINEER-1 | ORD/000041/2025-2026 | 852/DWSD | 29/05/2025 | 27/08/2025 | BIPLAB BANERJEE | 0.41 | 0.4 | 96.75 | 35
15 | PURBA BARDHAMAN | Galsi-I | Central Mechanical | Sub-Surface Water based Piped Water Supply Scheme for 11 nos. Mouzas under Galsi-I Block | SM/18679 | New | Providing Mechanical/Electrical equipment with all ancillaries and auxiliaries including intake (Low lift) pumping machineries, illumination arrangement of Shilla Sub-Surface Based Piped Water Supply Scheme under Purba Bardhaman District PHE Dte. | ASSISTANT ENGINEER,Driller In-Charge | Junior Engineer | ORD/000004/2025-2026 | 906/CMD | 04/04/2025 | 18/06/2025 | JAL PRAVAHIKA PVT LTD | 131.56 | 0 | 0 | 45
16 | PURBA BARDHAMAN | Galsi-I | Central Mechanical | Sub-Surface Water based Piped Water Supply Scheme for 11 nos. Mouzas under Galsi-I Block | SM/18679 | New | Providing Mechanical/Electrical equipment with all ancillaries and auxiliaries including High Lift pumping machineries, 0-1 kg/hour gaseous chlorination system of Shilla Sub-Surface Based Piped Water Supply Scheme under Purba Bardhaman District PHE Dte. | ASSISTANT ENGINEER,Driller In-Charge | JUNIOR ENGINEER | ORD/000001/2025-2026 | 903/CMD | 04/04/2025 | 18/06/2025 | DEY ENTERPRISE | 211 | 0 | 0 | 40
17 | PURBA BARDHAMAN | Galsi-I | Durgapur W/S Division | Sub-Surface Water based Piped Water Supply Scheme for 11 nos. Mouzas under Galsi-I Block | SM/18679 | New | Continuation order for Hiring of LUXURY Diesel Ambassador Car (Inspection Vehicle) for using of the Assistant Engineer-I under office of the Executive Engineer, Durgapur Water Supply Division, Public Health Engineering Dte at Fagupur, Nababhat, Purba Bardhaman for the period of 01.03.2025 to 31.05.2025. | Assistant Engineer-I,Assistant Engineer-II,Assistant Engineer-II (Newly Charge takenover) | JUNIOR ENGINEER-1 | ORD/000273/2024-2025 | 334/DWSD | 27/02/2025 | 27/05/2025 | BIPLAB BANERJEE | 0.41 | 1.2 | 290.92 | 35
18 | PURBA BARDHAMAN | Galsi-I | Durgapur W/S Division | Sub-Surface Water based Piped Water Supply Scheme for 11 nos. Mouzas under Galsi-I Block | SM/18679 | New | Hiring of Diesel Ambassador car BS_IV /Luxury taxi catalytic converter attachment (Euro-4)/Bolero/Scorpio having contract carriage permit from Regional Transport Authority for the use of the JJM under the office of the Executive Engineer,Durgapur water supply division PHE. Dte. at Fagupur , Nababhat,Purba Bardhhaman on daily basis (as and when required including Govt. holidays) period of 01.09.2025 to 28.02.2026 (181 days) (Sl-02) | Assistant Engineer-I,Assistant Engineer-II | JUNIOR ENGINEER-1,JUNIOR ENGINEER-2 | ORD/000127/2025-2026 | 1380/DWSD | 26/08/2025 | 23/02/2026 | PRAMIT CHATTERJEE | 0.86 | 0 | 0 | 0
19 | PURBA BARDHAMAN | Galsi-I | Durgapur W/S Division | Sub-Surface Water based Piped Water Supply Scheme for 11 nos. Mouzas under Galsi-I Block | SM/18679 | New | Laying HDPE pipe with Auger boring Construction of Valve Chamber and Remaining Road Restoration of CHHORA PWSS, Ausgram-II Block of under Durgapur Water Supply Division, PHE Dte. (Sl-03) | Assistant Engineer-I,Assistant Engineer-II | Contractual Junior Engineer_1,JUNIOR ENGINEER-2 | ORD/000131/2025-2026 | 1385/DWSD | 26/08/2025 | 05/09/2025 | SIDDHARTH ENTERPRISE | 0.97 | 0 | 0 | 100
20 | PURBA BARDHAMAN | Galsi-I | Durgapur W/S Division | Sub-Surface Water based Piped Water Supply Scheme for 11 nos. Mouzas under Galsi-I Block | SM/18679 | New | ADDITIONAL QUOTATION FOR NEW SERVICE CONNECTION AT UCHCHAGRAM (UNDER 11 NO MOUJA) UNDER CMD, PHE, Dte. |  |  | BILL/00252/2025-2026 |  | 29/08/2025 | 29/08/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.84 | 0 | 0 | 0
21 | PURBA BARDHAMAN | Galsi-I | Durgapur W/S Division | Sub-Surface Water based Piped Water Supply Scheme for 11 nos. Mouzas under Galsi-I Block | SM/18679 | New | Quotation for new electricity connection for 11 Nos sub-surface PWSS under DWSD PHE Dte |  |  | BILL/00240/2024-2025 | BP-2024-25-112 | 09/01/2025 | 09/01/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.99 | 0 | 0 | 0
22 | PURBA BARDHAMAN | Galsi-I | Durgapur W/S Division | Sub-Surface Water based Piped Water Supply Scheme for 11 nos. Mouzas under Galsi-I Block | SM/18679 | New | Acceptance cum formal order for the work of Preparation & Submission of Augmentation DPR for Sub Surface based Taher pur Pipe Water Supply Scheme under DWSD , PHE Dte.(Sl-01) | Assistant Engineer-I | JUNIOR ENGINEER-2 | ORD/000148/2025-2026 | 40/DWSD | 08/01/2026 | 15/01/2026 | MARS PLANNING AND ENGINEERING SERVICES PVT.LTD. | 0.78 | 0 | 0 | 0
23 | PURBA BARDHAMAN | Galsi-I | Durgapur W/S Division | Sub-Surface Water based Piped Water Supply Scheme for 11 nos. Mouzas under Galsi-I Block | SM/18679 | New | Acceptance cum Formal order for the work of Preparation & Submission of Augmentation DPR for Sub Surface based Khano Pipe Water Supply Scheme under DWSD, PHE Dte.(Sl-02) | Assistant Engineer-I | JUNIOR ENGINEER-2 | ORD/000149/2025-2026 | 47/DWSD | 08/01/2026 | 15/01/2026 | MARS PLANNING AND ENGINEERING SERVICES PVT.LTD. | 0.78 | 0 | 0 | 0
24 | PURBA BARDHAMAN | Galsi-I | Durgapur W/S Division | Sub-Surface Water based Piped Water Supply Scheme for 11 nos. Mouzas under Galsi-I Block | SM/18679 | New | C/O for the work of Preparation & Submission of Augmentation DPR for Sub Surface based Purangan Pipe Water Supply Scheme under DWSD , PHE Dte.(Sl-03) | Assistant Engineer-I | JUNIOR ENGINEER-2 | ORD/000159/2025-2026 | 73/DWSD | 15/01/2026 | 22/01/2026 | MARS PLANNING AND ENGINEERING SERVICES PVT.LTD. | 0.78 | 0 | 0 | 0
25 | PURBA BARDHAMAN | Galsi-I | Durgapur W/S Division | Sub-Surface Water based Piped Water Supply Scheme for 11 nos. Mouzas under Galsi-I Block | SM/18679 | New | Acceptance cum formal order for the work of Preparation & Submission of Augmentation DPR for Sub Surface based Purangan Pipe Water Supply Scheme under DWSD , PHE Dte.(Sl-03) | Assistant Engineer-I | JUNIOR ENGINEER-2 | ORD/000150/2025-2026 | 42/DWSD | 08/01/2026 | 15/01/2026 | MARS PLANNING AND ENGINEERING SERVICES PVT.LTD. | 0.78 | 0 | 0 | 0
26 | PURBA BARDHAMAN | Galsi-I | Durgapur W/S Division | Sub-Surface Water based Piped Water Supply Scheme for 11 nos. Mouzas under Galsi-I Block | SM/18679 | New | Annual O and Mtc of distribution system, rising main, sluice valves including operation of sluice valves at KRISHNARAMPUR PWSS under Durgapur W/S Division, PHE Dte (w.e.f. 01.07.2026 to 30.06.2027) | Assistant Engineer-I | JUNIOR ENGINEER-1 | ORD/000242/2026-2027 | 835/DWSD | 24/06/2026 | 24/06/2027 | JOY GURU ENTERPRISE | 5.09 | 0 | 0 | 0
Total | [13 empty] | 5114.52 | 511.01 | 9.99