## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Teandul PWSS | SM/06746 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of TEANDUL Piped Water Supply Scheme at Raina-I Block under Burdwan Division, PHE Dte.(Agreement No. 61/2020-2021 OF SE/CC/PHE. DTE.) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000112/2020-2021 | 4881/BWD | 07/12/2020 | 07/03/2021 | ASHOK KUMAR GHOSH | 70.51 | 26.97 | 38.25 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Teandul PWSS | SM/06746 | Retrofitting | Extension Pipeline with Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Madhuban, Sultanbad, Dhamas & Teyandul of TEANDUL Piped Water Supply Scheme within Raina I Block of Burdwan Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000754/2022-2023 | 1228/BWD | 17/03/2023 | 16/05/2023 | M/S UNIQUE | 31.31 | 0 | 0 | 0
3 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Teandul PWSS | SM/06746 | Retrofitting | Construction of Retaining wall for protection of soil erosion at Headwork site (Western Side) at TEANDUL Piped Water Supply Scheme under Burdwan Division, PHE Dte. [Group : B] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000035/2022-2023 | 241/AE/HQ | 20/04/2022 | 20/05/2022 | ROY CONSTRUCTION | 4.82 | 0 | 0 | 1
4 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Teandul PWSS | SM/06746 | Retrofitting | Construction of Retaining wall for protection of soil erosion at Headwork site (southern side) at Teandul PWSS under Burdwan Division, PHE Dte. [Group: ¿H¿] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000224/2021-2022 | 1902/AE/HQ | 16/11/2021 | 16/12/2021 | ASHOK KUMAR GHOSH | 4.5 | 0 | 0 | 1
Total | [13 empty] | 111.14 | 26.97 | 24.26