## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Mugura PWSS | SM/06747 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Mugura village of Mugura piped water supply scheme within Headquarters under Burdwan Division, PHE Dte. [Phase-I](Tr No.-163/BWD/2020-21) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000088/2020-2021 | 2690/BWD | 07/08/2020 | 06/09/2020 | LAKSHMIKANTA DAS | 4.92 | 9.84 | 200 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Mugura PWSS | SM/06747 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Jagarpur & Mugura village of Mugura piped water supply scheme within Headquarters under Burdwan Division, PHE Dte. [Phase-I](Tr No.-238/BWD/2020-21) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000095/2020-2021 | 2689/BWD | 07/08/2020 | 06/09/2020 | HAFIJUR RAHAMAN MIDYA | 4.92 | 9.84 | 200 | 1
3 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Mugura PWSS | SM/06747 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Mugura village of Mugura Piped Water Supply Scheme within Headquarters under Burdwan Division, PHE. Dte. [Phase - I] [GROUP : ¿3A¿] (Agreement no. 163/BWD,2020-2021) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000135/2020-2021 | 3535/BWD | 25/09/2020 | 25/10/2020 | LAKSHMIKANTA DAS | 2.69 | 0 | 0 | 1
4 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Mugura PWSS | SM/06747 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Jagarpur & Mugura village of Mugura Piped Water Supply Scheme within Headquarters under Burdwan Division, PHE. Dte. [Phase - I] [GROUP : ¿3B¿] (Agreement no.238/BWD of 2020-21) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000136/2020-2021 | 4118/BWD | 16/10/2020 | 15/11/2020 | HAFIJUR RAHAMAN MIDYA | 4.92 | 0 | 0 | 1
5 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Mugura PWSS | SM/06747 | Retrofitting | Laying Parallel Pipeline to improve drinking water supply, Construction of Boundary wall, Path Way, Drain at Head Work Site & 2nd TW Site and providing leftout FHTC, Road Restoration with allied work for MUGRA Piped Water Supply Scheme, Block- Raina-I, within Burdwan Sub Division under Burdwan Division PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000279/2024-2025 | 2711/BWD | 11/07/2024 | 22/12/2031 | M/S PURBASHA | 40.24 | 0 | 0 | 90
6 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Mugura PWSS | SM/06747 | Retrofitting | Providing 7 Nos.FHTC at Mugura Dakshinpara village under MUGURA Piped Water Supply Scheme,Block:Raina-I within Burdwan Sub Division under Burdwan Division PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/001013/2024-2025 | 08/BSD | 02/01/2025 | 17/01/2025 | RUPALI ENTERPRISE | 0.76 | 0.74 | 97.98 | 100
Total | [13 empty] | 58.45 | 20.42 | 34.94