## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Sultanpur PWSS | SM/06748 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Sultanpur village of Sultanpur piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-373/BWD/2020-21) |  |  | ORD/000084/2020-2021 | 2602/BWD | 04/08/2020 | 03/09/2020 | INVENT ENGINEERS CO. OPERATIVE SOCIETY LTD. | 4.91 | 4.91 | 100 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Sultanpur PWSS | SM/06748 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Gopalpur village of Sultanpur piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-338/BWD/2020-21) |  |  | ORD/000087/2020-2021 | 2609/BWD | 04/08/2020 | 03/09/2020 | BISWAS ENTERPRISE | 4.91 | 4.91 | 100 | 1
3 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Sultanpur PWSS | SM/06748 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Gopalpur village of Sultanpur piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-339/BWD/2020-21) | AE(HQs) | J.E. 2 BURDWAN | ORD/000356/2020-2021 | 3700/BWD | 05/10/2020 | 04/11/2020 | BISWAS ENTERPRISE | 4.91 | 4.91 | 100 | 1
4 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Sultanpur PWSS | SM/06748 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Sultanpur village of Sultanpur piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-374/BWD/2020-21) | Assistant Engineer | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000116/2020-2021 | 3701/BWD | 05/10/2020 | 04/11/2020 | INVENT ENGINEERS CO. OPERATIVE SOCIETY LTD. | 4.19 | 4.19 | 100 | 1
5 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Sultanpur PWSS | SM/06748 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Sultanpur Piped Water Supply Scheme at Halbele, Hridaypur, Isabpur, Nowapara & Uplati Village (Mouza), Kalna ¿ I Block under Burdwan Division, PHE Dte.(Agreement No. 56/2020-2021 OF SE/CC/PHE. DTE.) | Assistant Engineer |  | ORD/000124/2020-2021 | 4901/BWD | 07/12/2020 | 07/03/2021 | MAJILA ENTERPRISE | 94.67 | 70.51 | 74.48 | 1
6 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Sultanpur PWSS | SM/06748 | Retrofitting | Supply of 10 mm NB Gun-metal Ferrule conforming to IS: 2692-1989 for Water tap connection in each house hold from existing distribution system within Scheme jurisdiction in different Piped Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE. Dte. and delivered at Borsul Divl. Store. [Part-5]. | AE(HQs) | J.E. 2 BURDWAN | ORD/000090/2021-2022 | 3590/BWD | 13/07/2021 | 12/08/2021 | PREMANANDA ROY BISWAS | 127.5 | 0.24 | 0.19 | 1
7 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Sultanpur PWSS | SM/06748 | Retrofitting | Protection work of distribution system (200 mm dia) of 35 Mtr length near the head work site (Right Side) of Sultanpur & its adjoining mouzas water supply scheme by UC Bullah including Drum Sheet within Kalna Sub-Division under Burdwan Division, PHE Dte.[Gr.-E] | Assistant Engineer |  | ORD/000845/2020-2021 | 20/KSD | 07/01/2021 | 06/02/2021 | DEBASHISH ENTERPRISE | 0.75 | 0 | 0 | 1
8 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Sultanpur PWSS | SM/06748 | Retrofitting | Providing FHTC in each household from dist. System within Scheme jurisdiction in Hridaypur, Upalati, Belerhat, Gopalpur, Sultanpur, Isabpur & Naopara Village of SULTANPUR W/S. Scheme under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/000584/2021-2022 | 1357/BWD | 09/03/2022 | 08/04/2022 | TAPAS KUMAR ROY | 16.69 | 0 | 0 | 1
Total | [13 empty] | 258.53 | 89.67 | 34.69