## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Deriapur PWSS | SM/06749 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Deriapur village of Deriapur piped water supply scheme within Headquarters under Burdwan Division, PHE Dte. [Phase-I](Tr No.-158/BWD/2020-21) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000086/2020-2021 | 2691/BWD | 07/08/2020 | 06/09/2020 | ASHOK KUMAR GHOSH | 4.92 | 9.84 | 200 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Deriapur PWSS | SM/06749 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Deriapur village of Deriapur piped water supply scheme within Headquarters under Burdwan Division, PHE Dte. [Phase-I](Tr No.-351/BWD/2020-21) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000108/2020-2021 | 3898/BWD | 12/10/2020 | 11/11/2020 | ASHOK KUMAR GHOSH | 3.59 | 7.18 | 200 | 1
3 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Deriapur PWSS | SM/06749 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of DERIAPUR Piped Water Supply Scheme at Astikur, Balagar & Bora Village (Mouza), Raina-I Block under Burdwan Division, PHE Dte.(Agreement No. 474/BWD OF 2020-2021) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000129/2020-2021 | 4916/BWD | 08/12/2020 | 08/03/2021 | ASHOK KUMAR GHOSH | 39.84 | 61.89 | 155.36 | 1
4 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Deriapur PWSS | SM/06749 | Retrofitting | Providing leftout water tap connection in different villages for 100% coverage to make it Sajal Gram from existing distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Raina ¿ I Block under Burdwan Division, PHE. Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000344/2021-2022 | 39/BWD | 05/01/2022 | 04/02/2022 | HAFIJUR RAHAMAN MIDYA | 15.62 | 9.1 | 58.29 | 1
5 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Deriapur PWSS | SM/06749 | Retrofitting | Sinking of Tube Well, Construction of Pump House, Boundary Wall at 3rd TW Site with Extension of Pipeline & Laying Parallel line and Providing FHTC (Leftout] with allied works for DERIAPUR Piped Water Supply Scheme under Raina-I Block within Burdwan Sub Division under Burdwan Division P.H.E Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000177/2024-2025 | 2270/BWD | 18/06/2024 | 11/07/2025 | ROY CONSTRUCTION | 68.15 | 0 | 0 | 100
Total | [13 empty] | 132.12 | 88.02 | 66.62