## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Manikhar PWS | SM/06751 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of MANIKHAR Piped Water Supply Scheme at Kalna-I Block under Burdwan Division, PHE Dte. (Agreement No. 47/2020-2021 OF SE/CC/PHE. DTE.) | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000113/2020-2021 | 4787/BWD | 02/12/2020 | 02/03/2021 | H SAMANTA | 96.04 | 0 | 0 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Manikhar PWS | SM/06751 | Retrofitting | Hire & fuel charges of vehicle (Car No.-WB-04G-7127) for the office of the Assistant Engineer, Kalna Sub-Division, PHE Dte. for the month of March to September'2022. |  |  | BILL/00145/2022-2023 | 866/VEH | 09/12/2022 | 09/12/2022 | PARTHA PRATIM ACHARYA | 2.79 | 0 | 0 | 0
3 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Manikhar PWS | SM/06751 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of PANUHAT Piped Water Supply Scheme at different villages, Katwa-I Block under Burdwan Division, PHE Dte. (Part-A).[Agreement No. 727/BWD OF 2020-2021.] | Assistant Engineer | JUNIOR ENGINEER KATWA SUB-DIVISION PHE DTE | ORD/000326/2020-2021 | 1688/BWD | 24/02/2021 | 10/04/2021 | HAMID SK | 35.66 | 32.68 | 91.64 | 0
4 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Manikhar PWS | SM/06751 | Retrofitting | Supply of 10 mm NB Gun-metal Ferrule conforming to IS: 2692-1989 for Water tap connection in each house hold from existing distribution system within Scheme jurisdiction in different Piped Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE. Dte. and delivered at Borsul Divl. Store. [Part-5]. | AE(HQs) | J.E. 2 BURDWAN | ORD/000090/2021-2022 | 3590/BWD | 13/07/2021 | 12/08/2021 | PREMANANDA ROY BISWAS | 127.5 | 82.29 | 64.54 | 1
5 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Manikhar PWS | SM/06751 | Retrofitting | Supply of 10 mm NB Gun-metal Ferrule conforming to IS: 2692-1989 for Water tap connection in each house hold from existing distribution system within Scheme jurisdiction in different Piped Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE. Dte. and delivered at Borsul Divl. Store. [Part-4]. |  |  | ORD/000004/2021-2022 | 3117/BWD | 02/06/2021 | 02/07/2021 | PREMANANDA ROY BISWAS | 76.65 | 27.07 | 35.31 | 0
6 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Manikhar PWS | SM/06751 | Retrofitting | Supply of 10 mm NB Gun-Metal Ferrule conforming to IS:2692-1989 for water tap connection in each house hold from existing distribution system within scheme jurisdiction in different piped water supply scheme within Katwa Sub-Division under Burdwan Division, PHE Dte. and delivered at Barsul Divisional Store.[Part-4] |  |  | ORD/000108/2021-2022 | 3186/BWD | 08/06/2021 | 08/07/2021 | R.K. INDUSTRIES | 76.05 | 50.06 | 65.82 | 0
Total | [13 empty] | 414.7 | 192.09 | 46.32