## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Anguna PWSS | SM/06752 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Anguna village of Anguna Piped Water Supply Scheme within Headquarters under Burdwan Division, PHE. Dte. [Phase - I] [GROUP : ¿1A¿] |  |  | ORD/000133/2020-2021 | 2694/BWD | 10/07/2020 | 09/08/2020 | ANWESHA CONSTRUCTION | 4.91 | 0 | 0 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Anguna PWSS | SM/06752 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Anguna village of Anguna Piped Water Supply Scheme within Headquarters under Burdwan Division, PHE. Dte. [Phase - I] [GROUP : ¿1A¿] (Agreement no. 171/BWD of 2020-21) |  |  | ORD/000134/2020-2021 | 2698/BWD | 07/08/2020 | 06/09/2020 | ANWESHA CONSTRUCTION | 4.91 | 0 | 0 | 1
3 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Anguna PWSS | SM/06752 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Anguna village of Anguna piped water supply scheme within Headquarters under Burdwan Division, PHE Dte. [Phase-I](Tr No.-171/BWD/2020-21) |  |  | ORD/000097/2020-2021 | 2684/BWD | 07/08/2020 | 06/09/2020 | ANWESHA CONSTRUCTION | 4.91 | 9.82 | 200 | 1
4 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Anguna PWSS | SM/06752 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Gunar village of Anguna piped water supply scheme within Headquarters under Burdwan Division, PHE Dte. [Phase-I](Tr No.-203/BWD/2020-21) |  |  | ORD/000096/2020-2021 | 2693/BWD | 07/08/2020 | 06/09/2020 | M/S ANAND CONSTRUCTION | 4.92 | 9.84 | 200 | 1
5 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Anguna PWSS | SM/06752 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Anguna village of Anguna piped water supply scheme within Headquarters under Burdwan Division, PHE Dte. [Phase-I](Tr No.-302/BWD/2020-21) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000090/2020-2021 | 3355/BWD | 21/09/2020 | 21/10/2020 | ANWESHA CONSTRUCTION | 4.59 | 9.18 | 200 | 1
6 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Anguna PWSS | SM/06752 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Gunar village of Anguna piped water supply scheme within Headquarters under Burdwan Division, PHE Dte. [Phase-I](Tr No.-369/BWD/2020-21) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000101/2020-2021 | 3515/BWD | 25/09/2020 | 25/10/2020 | M/S ANAND CONSTRUCTION | 2.17 | 4.34 | 200 | 1
7 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Anguna PWSS | SM/06752 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Anguna Piped Water Supply Scheme at Anguna (Part), Gunar (Part) & Sakita Village (Mouza), Raina-I Block under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000291/2020-2021 | 517/BWD | 21/01/2021 | 07/03/2021 | SK ALIM | 33.4 | 46.82 | 140.21 | 1
8 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Anguna PWSS | SM/06752 | Retrofitting | Extension of pipe line of existing distribution system within the command area of Anguna Piped Water Supply Scheme, Anguna village within Raina-1 Block of Burdwan Sub Division under Burdwan Division,PHE Dte".Gr.A. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000439/2022-2023 | 1465/BSD | 25/08/2022 | 09/10/2022 | ANWESHA CONSTRUCTION | 4.97 | 4.93 | 99.26 | 1
9 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Anguna PWSS | SM/06752 | Retrofitting | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. |  |  | VCH/001237/2021-2022 | 1132/DW | 26/02/2022 | 26/02/2022 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 221 | 0 | 0 | 0
10 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Anguna PWSS | SM/06752 | Retrofitting | Providing leftout water tap connection in different villages for 100% coverage to make it Sajal Gram from existing distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Raina ¿ I Block under Burdwan Division, PHE. Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000344/2021-2022 | 39/BWD | 05/01/2022 | 04/02/2022 | HAFIJUR RAHAMAN MIDYA | 15.62 | 0 | 0 | 1
11 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Anguna PWSS | SM/06752 | Retrofitting | Extension of pipeline of Anguna water supply scheme at Anguna, Sanktia and Gunar village within Raina-I Block under Burdwan division, PHE Dte.[Gr.-A] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000711/2021-2022 | 1480/BSD | 09/11/2021 | 09/12/2021 | SK ABDUL HALIM | 4.44 | 4.35 | 98.1 | 1
12 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Anguna PWSS | SM/06752 | Retrofitting | Extension of pipeline for Anguna water supply scheme at Anguna, Sanktia and Gunar village within Raina-I Block under Burdwan Division, PHE Dte.[Gr.-B] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000715/2021-2022 | 1429/BSD | 28/10/2021 | 27/11/2021 | SK ABDUL HALIM | 4.38 | 3.11 | 70.92 | 1
13 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Anguna PWSS | SM/06752 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000123/2021-2022 | 1108/BWD | 26/02/2022 | 26/02/2022 | Resource Division | 25.78 | 0 | 0 | 0
14 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Anguna PWSS | SM/06752 | Retrofitting | Hire & fuel charges of vehicle (Car No.-WB-41H-9788) for the office of the Assistant Engineer, Head Quarters, Burdwan Division, PHE Dte. for the month of March'23. |  |  | BILL/00296/2023-2024 | 201/JJM | 01/06/2023 | 01/06/2023 | SK. ASRAFUDDIN | 0.39 | 0 | 0 | 0
15 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Anguna PWSS | SM/06752 | Retrofitting | Vehicle bill for the office of the Assistant Engineer, Head Quarters Burdwan Division, PHE Dte. for the month of June'23. |  |  | BILL/00616/2023-2024 | 482/JJM | 09/08/2023 | 09/08/2023 | SK. ASRAFUDDIN | 0.4 | 0 | 0 | 0
16 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Anguna PWSS | SM/06752 | Retrofitting | Extension Pipeline with Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Anguna, Sanktia, Gunar village of ANGUNA Piped Water Supply Scheme within Raina I Block of Burdwan Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000811/2022-2023 | 1575/BWD | 31/03/2023 | 30/05/2023 | JAGADANANDAPUR CO. OP. LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 33.16 | 0 | 0 | 100
17 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Anguna PWSS | SM/06752 | Retrofitting | Vehicle bill for the month of november'2023. |  |  | BILL/01673/2023-2024 | 1140/JJM | 29/12/2023 | 29/12/2023 | SK. ASRAFUDDIN | 0.4 | 0 | 0 | 0
18 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Anguna PWSS | SM/06752 | Retrofitting | MAINTENANCE OF ROAD (WHISH IS DAMAGED FOR LAYING PIPELINE BY PHE DEPTT) NAMELY NARUGRAM H.C TO BADSHI ROAD VIDE- PACKAGE NO- WB 22 12 UNDER PMGSY-III UNDER NARUGRAM GP. & RAINA-I BLOCK, IN PURBA BARDHAMAN DISTRICT |  |  | BILL/00740/2024-2025 | 894/JJM | 25/09/2024 | 25/09/2024 | EXECUTIVE ENGINEER (WBSRDA) PURBA BARDHAMAN DIVISION | 3.86 | 0 | 0 | 0
19 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Anguna PWSS | SM/06752 | Retrofitting | Vehicle bill for the month of October & November'2023. |  |  | BILL/01671/2023-2024 | 1145/JJM | 29/12/2023 | 29/12/2023 | SOURAV JANA | 0.79 | 0 | 0 | 0
20 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Anguna PWSS | SM/06752 | Retrofitting | Vehicle bill for the month of november'2023. |  |  | BILL/01672/2023-2024 | 1141/JJM | 29/12/2023 | 29/12/2023 | SK.ASFIA | 0.4 | 0 | 0 | 0
Total | [13 empty] | 375.39 | 92.4 | 24.61