## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Bundebaj PWSS | SM/06753 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Bundebaj (Pt-B) village of Bundebaj Piped Water Supply Scheme within Kalna Sub-Divn. under Burdwan Division, PHE. Dte. [Phase - I] [Sl.No : 8B] (T.R. no. 377/BWD/2020-21) | Assistant Engineer |  | ORD/000138/2020-2021 | 2591/BWD | 04/08/2020 | 03/09/2020 | MAA LAXMI ENTERPRISE | 4.92 | 9.84 | 200 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Bundebaj PWSS | SM/06753 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Bundebaj (Pt-A) village of Bundebaj Piped Water Supply Scheme within Kalna Sub-Divn. under Burdwan Division, PHE. Dte. [Phase - I] [Sl.No : 8A] (T.R. No. 320/BWD/2020-21) | Assistant Engineer |  | ORD/000137/2020-2021 | 2586/BWD | 04/08/2020 | 03/09/2020 | MOMINUL ISLAM MONDAL | 4.92 | 9.84 | 200 | 1
3 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Bundebaj PWSS | SM/06753 | Retrofitting | Continuation work order for supply of 10 mm NB Gun-Metal /Brass Ferrul conforming to IS:2692-1989 for water tap connection in each household from existing distribution system within scheme jurisdiction in different piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. and delivered at Barsul Divisional Store.[Part-6] | Assistant Engineer |  | ORD/000867/2020-2021 | 4318/BWD | 04/11/2020 | 14/11/2020 | MD HASIN | 4.93 | 0.32 | 6.59 | 1
4 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Bundebaj PWSS | SM/06753 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Bohar village and Minapur & Khortikpara habitation of SATGACHIA piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte.[Phase-I][Gr.-4A] |  |  | ORD/000739/2020-2021 | 3326/BWD | 18/09/2020 | 18/10/2020 | SUBRATA GUPTA | 4.87 | 9.67 | 198.8 | 0
Total | [13 empty] | 19.63 | 29.68 | 151.18