## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Sudpur PWSS | SM/06769 | Retrofitting | Urgent repairing work at Sudpur piped water supply scheme to ensuring FHTC work under Katwa-I Block under Katwa Sub-Division, under Burdwan Division, PHE Dte.[Tr No.-875/BWD/20-21] | Assistant Engineer | JUNIOR ENGINEER KATWA SUB-DIVISION PHE DTE | ORD/000614/2020-2021 | 91/KTS | 12/02/2021 | 15/02/2021 | HAMID SK | 0.92 | 1.84 | 199.98 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Sudpur PWSS | SM/06769 | Retrofitting | Extension of pipe line from the existing Distribution System within scheme jurisdiction at Rayerpara, Purba and Paschim Bijoynagar village under SUDPUR PWSS under Katwa Sub-Division under Burdwan Division PHE Dte [Sl - 5 ] | Assistant Engineer | JUNIOR ENGINEER KATWA SUB-DIVISION PHE DTE | ORD/000125/2021-2022 | 565/KTS | 31/08/2021 | 15/09/2021 | HAMID SK | 3.6 | 0 | 0 | 1
3 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Sudpur PWSS | SM/06769 | Retrofitting | Extension of pipe line from the existing Distribution System within scheme jurisdiction at Sudpur, Lokpur & Narayanpur village under SUDPUR PWSS under Katwa Sub-Division under Burdwan Division PHE Dte [Sl - 4 ] | Assistant Engineer | JUNIOR ENGINEER KATWA SUB-DIVISION PHE DTE | ORD/000120/2021-2022 | 564/KTS | 31/08/2021 | 15/09/2021 | BABUL SK | 2.42 | 0 | 0 | 1
4 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Sudpur PWSS | SM/06769 | Retrofitting | Balance work of OHR at Head Work site, construction of HUME Pipe culvert , Road restoration work and boundary wall at 2nd TW site with Gate, land development at Head work site and 2nd TW site under KAITHAN, SUDPUR & PANUHAT Piped Water Supply Scheme under KATWA -I Block, under Katwa Sub-Division within Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER KATWA SUB-DIVISION PHE DTE | ORD/000486/2024-2025 | 3141/BWD | 20/08/2024 | 18/12/2024 | VISHAL CONSTRUCTION CO. | 126.29 | 0 | 0 | 50
5 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Sudpur PWSS | SM/06769 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of SUDPUR Piped Water Supply Scheme (PART-A) at Katwa-I Block under Burdwan Division, PHE Dte. [Agreement No. 44/2020-2021 OF SE/CC/PHE. DTE.] | Assistant Engineer |  | ORD/000058/2020-2021 | 4290/BWD | 03/11/2020 | 01/02/2021 | MD HASIN | 86.85 | 137.68 | 158.52 | 1
Total | [13 empty] | 220.09 | 139.52 | 63.39