## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Palasan PWSS | SM/06772 | Retrofitting | Providing Functional Household tap connection (FHTC) from existing distribution system within the command area of PALASON piped water supply scheme at Raina-I Block under Burdwan Division, PHE Dte._2nd call. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000678/2020-2021 | 1409/BWD | 18/02/2021 | 19/04/2021 | S.S. ENTERPRISE | 72.41 | 71.05 | 98.13 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Palasan PWSS | SM/06772 | Retrofitting | Interconnection between Raising Main to OHR & OHR to distribution System with bypass arrangement for Palason Water Supply Scheme within Raina-I Block under Burdwan Division, PHE Dte._2ND CALL Gr.E. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000467/2021-2022 | 278/BSD | 15/02/2022 | 17/03/2022 | S.S. ENTERPRISE | 3.23 | 0 | 0 | 1
3 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Palasan PWSS | SM/06772 | Retrofitting | Construction of concrete road and rest portion of Boundary Wall at Head Works Site of PALASON Water Supply Scheme under Raina-I Block of Burdwan Division,PHE Dte(Length-48.00 Mtr,Col-16 Nos)[Front Side]Gr.F. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000490/2021-2022 | 279/BSD | 15/02/2022 | 01/04/2022 | NEW MANGES INDUSTRIAL CORPORATION | 4.12 | 4.17 | 101.38 | 1
Total | [13 empty] | 79.76 | 75.23 | 94.32