## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Srikhanda PWSS | SM/06773 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of SRIKHANDA Piped Water Supply Scheme at Katwa - I Block under Burdwan Division, PHE Dte.(Agreement No. 53/2020-2021 OF SE/CC/PHE. DTE.) | Assistant Engineer |  | ORD/000121/2020-2021 | 4880/BWD | 07/12/2020 | 07/03/2021 | ASHOK KUMAR GHOSH | 96.84 | 37.54 | 38.77 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Srikhanda PWSS | SM/06773 | Retrofitting | Continuation work order for supply of 10 mm NB Gun-Metal /Brass Ferrul conforming to IS:2692-1989 for water tap connection in each household from existing distribution system within scheme jurisdiction in different piped water supply scheme within Durgapur (Bardhaman North) Sub-Division under Burdwan Division, PHE Dte. and delivered at Barsul Divisional Store.[Part-7] | Assistant Engineer |  | ORD/000348/2021-2022 | 2942/BWD | 04/05/2021 | 14/05/2021 | KISHORE GHOSH | 3.94 | 0 | 0 | 1
3 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Srikhanda PWSS | SM/06773 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Bohar village and Bohar habitation of Satgachia piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-435/BWD/2020-21) |  |  | ORD/000507/2020-2021 | 3327/BWD | 18/09/2020 | 18/10/2020 | TARAMA AGENCY | 4.86 | 4.83 | 99.37 | 0
4 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Srikhanda PWSS | SM/06773 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Jakra village and Jakra Paschimpara habitation of Satgachhia piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-383/BWD/2020-21) |  |  | ORD/000511/2020-2021 | 3328/BWD | 18/09/2020 | 18/10/2020 | A R TRADERS | 4.86 | 4.86 | 100 | 0
5 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Srikhanda PWSS | SM/06773 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Jakra (Part) village (Innathgore Habitation) & Bohat (Part) village (Hamunpur Habitation) of Satgachia piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte.[Sl No.-21] |  |  | ORD/000793/2020-2021 | 71/BWD | 05/01/2021 | 20/01/2021 | A R TRADERS | 4.86 | 4.86 | 100 | 0
6 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Srikhanda PWSS | SM/06773 | Retrofitting | Continuation work order for water tap connection in each house hold from existing distribution system within scheme jurisdiction in Bohar village and Bohar habitation of Satgachia piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte.[Phase-I][Gr.-4B] |  |  | ORD/000794/2020-2021 | 4990/BWD | 10/12/2020 | 09/01/2021 | TARAMA AGENCY | 4.86 | 4.69 | 96.45 | 0
Total | [13 empty] | 120.21 | 56.78 | 47.23