## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Bamunpara Piped Water Supply Scheme | SM/06962 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Bamunpara Piped Water Supply Scheme at Bamunpara (7 Nos Habitation Part), Sahajadpur (5 Nos Habitation Part), Gulita Daspara & Purba Khanpur (4 Nos Habitation) Village (Mouza), Monteswar Block under Burdwan Division, PHE Dte.(Agreement No. 69/2020-2021 OF SE/CC/PHE. DTE.) | Assistant Engineer |  | ORD/000130/2020-2021 | 5002/BWD | 07/12/2020 | 07/03/2021 | M/S S. CHOUDHURY | 50.71 | 84.67 | 166.95 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Bamunpara Piped Water Supply Scheme | SM/06962 | Retrofitting | Supply of SS316 grade flow control valve for FHTC at different water supply schemes within Kalna Sub-Division under Burdwan Division, PHE Dte. and delivered at Barsul Divisional store.[Part-2] | Assistant Engineer |  | ORD/001307/2020-2021 | 1792 /BWD | 26/02/2021 | 08/03/2021 | INDIA PIPE FITTING CO | 9.7 | 5.47 | 56.34 | 1
3 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Bamunpara Piped Water Supply Scheme | SM/06962 | Retrofitting | Providing FHTC - Sahajadpur (5 nos habitations)-170 nos & Bamunpara (7 nos habitation)-170 nos & Extension of pipeline to provide house connection at Tentulia village & Sahajadpur village for Drain out water of wash out & over flow line from existing OHR at Head Works Site of BAMUNPARA W/S Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/000588/2021-2022 | 1417/BWD | 10/03/2022 | 09/04/2022 | M/S UNIQUE | 16.5 | 16.33 | 98.92 | 1
4 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Bamunpara Piped Water Supply Scheme | SM/06962 | Retrofitting | Laying of UPVC pipeline & providing FHTC work at Bamunpara, Sahajadpur, Tentulia & Gulita village of BAMUNPARA Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. |  | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000150/2023-2024 | 2423/BWD | 30/05/2023 | 29/06/2023 | GOUTAM KUMAR MITRA | 9.65 | 9.4 | 97.45 | 100
Total | [13 empty] | 86.57 | 115.86 | 133.84