## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Putsuri Piped Water Supply Scheme | SM/06963 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Putsuri village of Putsuri piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-546/BWD/2020-21) | AE(HQs) | J.E. 2 BURDWAN | ORD/000268/2020-2021 | 3532/BWD | 25/09/2020 | 25/10/2020 | PRONAB KUMAR DEY | 4.92 | 9.84 | 200 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Putsuri Piped Water Supply Scheme | SM/06963 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Putsuri Piped Water Supply Scheme at Denur (6 Nos Habitation Part) & Putsuri (11 Nos Habitation Part) Village (Mouza), Monteswar Block under Burdwan Division, PHE Dte.(Agreement No. 55/2020-2021 OF SE/CC/PHE. DTE.) | AE(HQs) | J.E. 2 BURDWAN | ORD/000125/2020-2021 | 4887/BWD | 07/12/2020 | 07/03/2021 | M/S S. CHOUDHURY | 77.12 | 100.09 | 129.79 | 1
3 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Putsuri Piped Water Supply Scheme | SM/06963 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Denur village of Putsuri piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-562/BWD/2020-21) | AE(HQs) | J.E. 2 BURDWAN | ORD/000355/2020-2021 | 3804/BWD | 08/10/2020 | 07/11/2020 | IJABUL SEKH | 4.92 | 9.84 | 200 | 1
4 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Putsuri Piped Water Supply Scheme | SM/06963 | Retrofitting | Load Enhancement charges bill for Putsuri water supply scheme under Burdwan Division, PHE Dte.[Application No.-5003378053, Consumer Id-500684865] |  |  | VCH/000392/2022-2023 | 300/DW/22-23 | 05/07/2022 | 05/07/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.56 | 0 | 0 | 0
5 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Putsuri Piped Water Supply Scheme | SM/06963 | Retrofitting | Work Order for "Providing Functional house hold tap connections for Sajal Gram villages within Monteswar Block under Kalna Sub-Division under Burdwan Division, PHE Dte. (Putsuri water supply Scheme) (Sl No-9) |  | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000029/2023-2024 | 344/KSD | 17/04/2023 | 17/05/2023 | HASAN CONSTRUCTION | 0.88 | 0 | 0 | 0
6 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Putsuri Piped Water Supply Scheme | SM/06963 | Retrofitting | Work Order for "Providing Functional house hold tap connections for Sajal Gram Village within Monteswar Block under Kalna Sub-Division under Burdwan Division, PHE Dte. (Putsuri water supply scheme)" | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000028/2023-2024 | 344/KSD | 17/04/2023 | 17/05/2023 | HASAN CONSTRUCTION | 0.88 | 0 | 0 | 0
7 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Putsuri Piped Water Supply Scheme | SM/06963 | Retrofitting | Supply of 10 mm NB Gun-metal Ferrule conforming to IS: 2692-1989 for Water tap connection in each house hold from existing distribution system within Scheme jurisdiction in different Piped Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE. Dte. and delivered at Borsul Divl. Store. [Part-5]. | AE(HQs) | J.E. 2 BURDWAN | ORD/000090/2021-2022 | 3590/BWD | 13/07/2021 | 12/08/2021 | PREMANANDA ROY BISWAS | 127.5 | 14.26 | 11.18 | 1
8 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Putsuri Piped Water Supply Scheme | SM/06963 | Retrofitting | Extension of 75 mm dia UPVC pipeline at different places of Denur village under Putsuri & its adjoining mouzas water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte.[SL NO.-C] | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000839/2020-2021 | 169/KSD | 19/02/2021 | 21/03/2021 | M/S S. CHOUDHURY | 2.37 | 0 | 0 | 1
9 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Putsuri Piped Water Supply Scheme | SM/06963 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of PUTSURI Piped Water Supply Scheme at Kasa (6 Nos. Habs.), Purba Balarampur, Bhurkunda (7 Nos. Habs.), Patun (5 Nos. Habs.) & Bigha (3 Nos. Habs.) Village (Mouza), Monteswar Block under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/000302/2021-2022 | 7020/BWD | 17/12/2021 | 15/02/2022 | INVENT ENGINEERS CO. OPERATIVE SOCIETY LTD. | 53.94 | 8.54 | 15.83 | 1
10 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Putsuri Piped Water Supply Scheme | SM/06963 | Retrofitting | Laying of different dia.UPVC pipeline at the damaged portion from Denur to Mousa Daukadanga under Putsuri & its adjoining mouzas water supply scheme within Kalna Sub-Division, under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/000778/2021-2022 | 6013/BWD | 05/10/2021 | 04/11/2021 | D.M. ENTERPRISE | 23.17 | 0 | 0 | 1
11 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Putsuri Piped Water Supply Scheme | SM/06963 | Retrofitting | Hire & fuel charges of vehicle (Car No.-WB-04G-7127) for the office of the Assistant Engineer, Kalna Sub-Division, PHE Dte. for the month of March & April'23. |  |  | BILL/00457/2023-2024 | 367/JJM | 18/07/2023 | 18/07/2023 | PARTHA PRATIM ACHARYA | 0.77 | 0 | 0 | 0
12 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Putsuri Piped Water Supply Scheme | SM/06963 | Retrofitting | Hire & fuel charges of vehicle Car No.-WB-41H-3668 for the month of May & June'2023. |  |  | BILL/01039/2023-2024 | 744/JJM | 11/10/2023 | 11/10/2023 | MD HASIN | 0.53 | 0 | 0 | 0
13 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Putsuri Piped Water Supply Scheme | SM/06963 | Retrofitting | Providing FHTC with laying of 75 mm dia HDPE Pipe of Putsuri PWSS of near Health Centre under Manteswar Block under Durgapur Sub Division of Burdwan Division ,P.H.E.Dte | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer1, Durgapur Sub-Division, PHE Dte. | ORD/001183/2023-2024 | 272/DSD | 15/03/2024 | 14/04/2024 | SAYAK DEY | 0.97 | 0 | 0 | 0
14 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Putsuri Piped Water Supply Scheme | SM/06963 | Retrofitting | Relaying of different dia UPVC Pipeline at the different damage portion towards Mojaharnagar, Gulita, Denur & Putsuri of Putsuri PWSS within Kalna Sub-Division under Burdwan Division, PHE Dte. (Sl No-B) | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000322/2021-2022 | 985/KSD Dt- 24.09.2021 | 24/09/2021 | 24/10/2021 | M/S S. CHOUDHURY | 3.66 | 3.65 | 99.77 | 100
15 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Putsuri Piped Water Supply Scheme | SM/06963 | Retrofitting | Work order for "Interconnection of rising main from 4th Tube Well site to Over Head Reservoir for FHTC related water supply under Putsuri W/S Scheme within Kalna Sub-Division under Burdwan Division , PHE Dte." | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer1, Durgapur Sub-Division, PHE Dte. | ORD/000554/2023-2024 | 1309/KSD | 23/08/2023 | 07/09/2023 | PRONAB KUMAR DEY | 2.1 | 1.78 | 84.66 | 100
16 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Putsuri Piped Water Supply Scheme | SM/06963 | Retrofitting | Providing FHTC with laying of 75 mm dia HDPE Pipe of Putsuri PWSS of Ghosh para village under Manteswar Block under Durgapur Sub Division of Burdwan Division ,P.H.E.Dte | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer1, Durgapur Sub-Division, PHE Dte. | ORD/001182/2023-2024 | 271/DSD | 15/03/2024 | 14/04/2024 | SAYAK DEY | 0.97 | 0.96 | 99.46 | 100
Total | [13 empty] | 306.28 | 148.98 | 48.64