## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Berwa Piped Water Supply Scheme | SM/06965 | Retrofitting | Formal Work Order for Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Barwa Piped Water Supply Scheme at Berwa (2 Nos Habitation Part), Mutra (2 Nos Habitation Part), Baneswarpur & Senpur (4 Nos Habitation) Village (Mouza), Memari-II Block under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000647/2020-2021 | 916/BWD | 02/02/2021 | 03/05/2021 | KALYAN CHOWDHURY | 45.14 | 0 | 0 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Berwa Piped Water Supply Scheme | SM/06965 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Barwa village of Barwa piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-573/BWD/2020-21) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000471/2020-2021 | 4627/BWD | 25/11/2020 | 25/12/2020 | M/S SAYAN CHAKRABORTY | 4.92 | 9.84 | 200 | 1
3 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Berwa Piped Water Supply Scheme | SM/06965 | Retrofitting | Formal Work Order for Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Barwa Piped Water Supply Scheme at Berwa (2 Nos Habitation Part), Mutra (2 Nos Habitation Part), Baneswarpur & Senpur (4 Nos Habitation) Village (Mouza), Memari-II Block under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000038/2021-2022 | 3442/BWD | 28/06/2021 | 26/09/2021 | KALYAN CHOWDHURY | 45.14 | 41.9 | 92.83 | 100
4 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Berwa Piped Water Supply Scheme | SM/06965 | Retrofitting | Extension of 75 mm dia pipeline at Miya Para, Modhya Bohar & Bhagar Para Purba Bohar regarding FHTC under Satgachia (Zone-I) water supply scheme under Burdwan Division, PHE Dte.[Gr.-A] | Assistant Engineer ,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000350/2021-2022 | 703/BSD | 11/06/2021 | 16/06/2021 | M/S SAYAN CHAKRABORTY | 0.88 | 0 | 0 | 1
5 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Berwa Piped Water Supply Scheme | SM/06965 | Retrofitting | Emergency repaired cleaning of chokage AC Pipeline for BARWA Piped Water Supply Scheme (Retrrofittings)at Mutra, senpur, Mohanpur & Barwa village distribution line smooth drinking (FHTC) water supply within Memari-II Block under Burdwan Division, PHE Dte. Gr.C | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000563/2022-2023 | 1919/BSD | 11/11/2022 | 26/11/2022 | A R TRADERS | 0.79 | 0.79 | 100 | 1
6 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Berwa Piped Water Supply Scheme | SM/06965 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Bohar (Part) village (Bohar (Part) habitation) of Satgachia Piped Water Supply Scheme within Burdwan Sub-Divn. under Burdwan Division, PHE. Dte. [Sl. No. : ¿20¿] |  |  | ORD/000667/2020-2021 | 70/BWD | 05/01/2021 | 20/01/2021 | M/S SAYAN CHAKRABORTY | 4.86 | 4.79 | 98.58 | 0
7 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Berwa Piped Water Supply Scheme | SM/06965 | Retrofitting | Restoration of Pump House at Head Work site of BARWA Piped water supply scheme at Memari-II Block under Burdwan Division, Dist.-Purba Bardhaman | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER RWS BURDWAN SUB-DIVISION PHE DTE | ORD/000133/2024-2025 | 1007/BSD | 06/06/2024 | 06/07/2024 | I.S. ENTERPRISE | 0.97 | 0.96 | 99.79 | 100
8 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Berwa Piped Water Supply Scheme | SM/06965 | Retrofitting | Different Types of work involved in connection with different Augmentation & Retrofitting Schemes (06 Nos.) Piped Water Supply Scheme under Memari II Block within Burdwan Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/001269/2024-2025 | 848/BWD | 05/03/2025 | 03/07/2025 | PROJECT INDIA | 394.29 | 0 | 0 | 0
Total | [13 empty] | 496.98 | 58.29 | 11.73