## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Palla Piped Water Supply Scheme | SM/06967 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Palla(Pt-B) village of Palla piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-246/BWD/2020-21) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000082/2020-2021 | 2738/BWD | 10/08/2020 | 09/09/2020 | S.C. ENTERPRISE | 4.92 | 9.84 | 200 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Palla Piped Water Supply Scheme | SM/06967 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Palla(Pt-A) village of Palla piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-487/BWD/2020-21) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000117/2020-2021 | 3972/BWD | 14/10/2020 | 13/11/2020 | JAYANTA CHAKRABORTY | 4.92 | 9.84 | 200 | 1
3 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Palla Piped Water Supply Scheme | SM/06967 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Palla (Pt-B) village of Palla Piped Water Supply Scheme within Burdwan Sub-Divn. under Burdwan Division, PHE. Dte. [Phase - I] [GROUP : ¿11B¿] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000674/2020-2021 | 4912/BWD | 08/12/2020 | 07/01/2021 | S.C. ENTERPRISE | 4.92 | 9.76 | 198.34 | 1
4 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Palla Piped Water Supply Scheme | SM/06967 | Retrofitting | Additional work providing Functional Household Tap connection (FHTC) from existing distribution system within the command area of Palla piped water supply scheme at Palla village (Mouza) Memari-I Block under Burdwan Division, PHE Dte. [Gr.-F] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000153/2021-2022 | 685/BSD | 09/06/2021 | 09/07/2021 | S.C. ENTERPRISE | 0.77 | 1.52 | 197.1 | 1
5 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Palla Piped Water Supply Scheme | SM/06967 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of PALLA Piped Water Supply Scheme at Palla(Paschim Palla Habitation Part)village(Mouza)Memari-I Block under Burdwan Division, PHE Dte.Gr.C | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000441/2021-2022 | 199/BSD | 01/02/2022 | 03/03/2022 | MUKHERJEE ENTERPRISE | 4.58 | 4.51 | 98.53 | 1
6 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Palla Piped Water Supply Scheme | SM/06967 | Retrofitting | Providing Functional Household Tap Connection(FHTC)from existing distribution system within the command area of PALLA Water supply scheme at Palla(Paschim palla Habitation part) village (Mouza) opposite side of navigation cannel, in Memari-I Block including leftout household water tap connection(FHTC) under Burdwan Division, PHE Dte. Group : B | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000103/2022-2023 | 984/BSD | 16/06/2022 | 16/07/2022 | DUBE ENTERPRISE | 4.22 | 4.21 | 99.8 | 1
7 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Palla Piped Water Supply Scheme | SM/06967 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Palla Piped Water Supply Scheme at Palla (Part) (7 Nos Habitation Part) Village (Mouza), Memari-I Block under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000023/2021-2022 | 3345/BWD | 21/06/2021 | 21/07/2021 | M/S ASHA CONSTRUCTION | 27.79 | 26.27 | 94.53 | 0
8 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Palla Piped Water Supply Scheme | SM/06967 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Palla(Pt-A) village of Palla piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-245/BWD/2020-21) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000094/2020-2021 | 2746/BWD | 10/08/2020 | 09/09/2020 | JAYANTA CHAKRABORTY | 4.92 | 9.84 | 200 | 1
Total | [13 empty] | 57.04 | 75.8 | 132.88