## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Chhotobainan Piped Water Supply Scheme | SM/06968 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Momrejpur village of Chhotobainan piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-174/BWD/2020-21) |  |  | ORD/000119/2020-2021 | 2741/BWD | 10/08/2020 | 09/09/2020 | TIRUPATI ENTERPRISES | 4.92 | 4.92 | 100 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Chhotobainan Piped Water Supply Scheme | SM/06968 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Chhotobainan Piped Water Supply Scheme at Chhotobainan (3 Nos Part Habitation), Akhina, Dakhin Mohanour, Pahalanpur & Rupsara Village (Mouza), Raina-II Block under Burdwan Division, PHE Dte.(Agreement No. 62/2020-2021 OF SE/CC/PHE. DTE.) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000127/2020-2021 | 4852/BWD | 04/12/2020 | 04/03/2021 | TIRUPATI ENTERPRISES | 100.4 | 82.44 | 82.11 | 1
3 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Chhotobainan Piped Water Supply Scheme | SM/06968 | Retrofitting | Extension of pipeline for CHHOTOBAINAN water supply scheme at Pahalanpur and Rupsara and Dakshin Mohonpur village within Raina-II Block under Burdwan Division, PHE Dte. [Gr.-E] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000212/2021-2022 | 988/BSD | 30/07/2021 | 29/08/2021 | TIRUPATI ENTERPRISES | 4.82 | 3.35 | 69.6 | 1
4 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Chhotobainan Piped Water Supply Scheme | SM/06968 | Retrofitting | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. |  |  | VCH/001246/2021-2022 | 900/DW | 03/02/2022 | 03/02/2022 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 34.54 | 0 | 0 | 0
5 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Chhotobainan Piped Water Supply Scheme | SM/06968 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Chhotobainan village of Chhotobainan piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-173/BWD/2020-21) |  |  | ORD/000118/2020-2021 | 2740/BWD | 10/08/2020 | 09/09/2020 | BOSE ENTERPRISE | 4.9 | 4.9 | 100 | 1
6 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Chhotobainan Piped Water Supply Scheme | SM/06968 | Retrofitting | Extension of pipeline for CHHOTOBAINAN water supply scheme at Chhotobainan village within Raina-II Block under Burdwan Division, PHE Dte. (Gr.-D) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000208/2021-2022 | 956/BSD | 23/07/2021 | 22/08/2021 | BOSE ENTERPRISE | 4.92 | 4.28 | 86.93 | 0
Total | [13 empty] | 154.5 | 99.88 | 64.65