## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Amra Piped Water Supply Scheme | SM/06969 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Dogachia village of Amra piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-232/BWD/2020-21) |  |  | ORD/000093/2020-2021 | 2737/BWD | 10/08/2020 | 09/09/2020 | KALYAN CHOWDHURY | 4.92 | 4.92 | 100 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Amra Piped Water Supply Scheme | SM/06969 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Amra village of Amra piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-404/BWD/2020-21) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000092/2020-2021 | 3531/BWD | 25/09/2020 | 25/10/2020 | DEBASHISH ENTERPRISE | 4.92 | 4.92 | 100 | 1
3 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Amra Piped Water Supply Scheme | SM/06969 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Teli Nuri village of Amra piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-427/BWD/2020-21) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000085/2020-2021 | 3530/BWD | 25/09/2020 | 25/10/2020 | KALYAN CHOWDHURY | 4.92 | 4.92 | 100 | 1
4 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Amra Piped Water Supply Scheme | SM/06969 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Amra village of Amra piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-208/BWD/2020-21) |  |  | ORD/000083/2020-2021 | 2734/BWD | 10/08/2020 | 09/09/2020 | DEBASHISH ENTERPRISE | 4.92 | 4.92 | 100 | 1
5 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Amra Piped Water Supply Scheme | SM/06969 | Retrofitting | Supply of SS316 grade flow control valve for FHTC at different water supply schemes within Kalna Sub-Division under Burdwan Division, PHE Dte. and delivered at Barsul Divisional store.[Part-2] | Assistant Engineer |  | ORD/001307/2020-2021 | 1792 /BWD | 26/02/2021 | 08/03/2021 | INDIA PIPE FITTING CO | 9.7 | 0 | 0 | 1
6 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Amra Piped Water Supply Scheme | SM/06969 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Amra Piped Water Supply Scheme at Amra (2 Nos Habitation Part) & Dogachia Village (Mouza), Jamalpur Block under Burdwan Division, PHE Dte._3rd CALL. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000008/2021-2022 | 3138/BWD | 03/06/2021 | 18/07/2021 | D.M. ENTERPRISE | 57.42 | 20.77 | 36.17 | 1
7 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Amra Piped Water Supply Scheme | SM/06969 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of AMRA Piped Water Supply Scheme (Vill-Dogechia, Habitation- Dogechia ) at Jamalpur Block of Burdwan Sub-Division under Burdwan Division, PHE Dte.Gr.A. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000386/2021-2022 | 57/BSD | 13/01/2022 | 12/02/2022 | DEY NIRMAN | 4.81 | 0 | 0 | 1
8 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Amra Piped Water Supply Scheme | SM/06969 | Retrofitting | Extension of pipeline at AMRA water supply scheme at different villages (Tengaberia, Badpur & Kolupukur) FHTC of Jamalpur Block under Burdwan Division, PHE Dte.[Gr.-F] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000561/2021-2022 | 1374/BSD | 05/10/2021 | 04/11/2021 | D.M. ENTERPRISE | 4.74 | 0 | 0 | 1
9 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Amra Piped Water Supply Scheme | SM/06969 | Retrofitting | Construction of Boundary wall at 3rd Tube well site of Dogachia Mouza of Amra water supply scheme under Jamalpur block under Burdwan Division, PHE Dte. [Length-59 Mtr][Gr.-F] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000557/2021-2022 | 1028/BSD | 05/08/2021 | 19/09/2021 | MUKHERJEE ENTERPRISE | 4.45 | 0 | 0 | 1
10 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Amra Piped Water Supply Scheme | SM/06969 | Retrofitting | Providing FHTC for Dogachia Mouza [(Habitation (Village)] for AMRA piped W/S Scheme, Jamalpur Dev. Block under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000068/2023-2024 | 2019/BWD | 28/04/2023 | 28/05/2023 | DEY NIRMAN | 20.61 | 0 | 0 | 100
11 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Amra Piped Water Supply Scheme | SM/06969 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Jougram village (Jougram habitation) of Jougram Piped Water Supply Scheme within Burdwan Sub-Divn. under Burdwan Division, PHE. Dte. (Part-C) [SL. No. : 11] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000031/2021-2022 | 3408/BWD | 25/06/2021 | 10/07/2021 | N.S. ENTERPRISE | 4.86 | 4.27 | 87.86 | 1
12 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Amra Piped Water Supply Scheme | SM/06969 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Dattapur village (Adampur habitation) of Jougram Piped Water Supply Scheme within Burdwan Sub-Divn. under Burdwan Division, PHE. Dte. [SL. No. : 11] |  |  | ORD/000428/2020-2021 | 590/BWD | 25/01/2021 | 09/02/2021 | N.S. ENTERPRISE | 4.86 | 3.29 | 67.86 | 0
13 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Amra Piped Water Supply Scheme | SM/06969 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Jougram village (Jougram habitation) of Jougram Piped Water Supply Scheme within Burdwan Sub-Divn. under Burdwan Division, PHE. Dte. (Part-B) [SL. No. : 13] |  |  | ORD/000427/2020-2021 | 592/BWD | 25/01/2021 | 09/02/2021 | DEY NIRMAN | 4.84 | 4.84 | 100 | 0
14 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Amra Piped Water Supply Scheme | SM/06969 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Jougram village (Jougram habitation) of Jougram Piped Water Supply Scheme within Burdwan Sub-Divn. under Burdwan Division, PHE. Dte. (Part-A) [SL. No. : 12] (Agreement No. 671/BWD of 2020-21) |  |  | ORD/000429/2020-2021 | 591/BWD | 25/01/2021 | 09/02/2021 | MUKHERJEE ENTERPRISE | 4.86 | 4.86 | 100 | 0
15 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Amra Piped Water Supply Scheme | SM/06969 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Jougram village (Jougram habitation) of Jougram Piped Water Supply Scheme within Burdwan Sub-Divn. under Burdwan Division, PHE. Dte. (Part-A) [SL. No. : 12] (Agreement no. 839/BWD of 2020-21) |  |  | ORD/000430/2020-2021 | 1397/BWD | 15/02/2021 | 02/03/2021 | MUKHERJEE ENTERPRISE | 4.86 | 4.86 | 100 | 0
16 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Amra Piped Water Supply Scheme | SM/06969 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Jajanpur village and Jajanpur-Tangaberia habitation of JAUGRAM piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte.[Phase-I][Gr.-6B] |  |  | ORD/000740/2020-2021 | 3331/BWD | 18/09/2020 | 18/10/2020 | DEY NIRMAN | 4.86 | 4.86 | 100 | 0
Total | [13 empty] | 150.54 | 67.43 | 44.79