## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Natungram Piped Water Supply Scheme | SM/06970 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Amar village of Natungram piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-579/BWD/2020-21) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000263/2020-2021 | 4465/BWD | 11/11/2020 | 11/12/2020 | BAMDEB CONSTRUCTION & CO | 4.92 | 4.92 | 100 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Natungram Piped Water Supply Scheme | SM/06970 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Natungram Piped Water Supply Scheme at Amar (6 Nos Habitation Part), Natungram (4 Nos Habitation Part) & Bohar Village (Mouza), Bardhaman-I Block under Burdwan Division, PHE Dte.(Agreement No. 73/2020-2021 OF SE/CC/PHE. DTE.) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000140/2020-2021 | 7052/BWD | 22/12/2020 | 22/03/2021 | HAMID SK | 48.2 | 41.4 | 85.88 | 1
3 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Natungram Piped Water Supply Scheme | SM/06970 | Retrofitting | Providing Functional House hold Tap connection (FHTC) from existing distribution system within the command area of NATUNGRAM piped water supply scheme at Natungram village under Bardhaman-I Block under Burdwan Division, PHE Dte.[Gr.-C] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000152/2021-2022 | 687/BSD | 09/06/2021 | 09/07/2021 | HAMID SK | 2.95 | 2.91 | 98.53 | 1
4 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Natungram Piped Water Supply Scheme | SM/06970 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Amra village of Natungram piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-332/BWD/2020-21) |  |  | ORD/000079/2020-2021 | 2732/BWD | 10/08/2020 | 09/09/2020 | BAMDEB CONSTRUCTION & CO | 4.92 | 4.92 | 100 | 1
5 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Natungram Piped Water Supply Scheme | SM/06970 | Retrofitting | Publication charges bill for the office of the Executive Engineer, Burdwan Division, PHE Dte.[Invoice No.-BCWB20RV-0001293, dt.-19/05/20, BCWB20RV-0001770, dt.-31/05/20, BCWB20RV-0001920, dt.-05/06/20, BCWB20RV-0001860, dt.-03/06/20, BCWB20RV-0001861, dt.-03/06/20, BCWB20RV-0001928, dt.-05/06/20, BCWB20RV-0001820, dt.-03/06/20, BCWB19RV-0059455, dt.-20/03/20, BCWB19RV-0059454. dt.-20/03/20, BCWB19RV-0057682, dt.-12/03/20, BCWB20RV-0003210, dt.-26/06/20, BCWB20RV-0000918, dt.-07/05/20, BCWB20RV-0001352, dt.-22/05/20, BCWB19RV-0050592, dt.-30/01/20] |  |  | VCH/000411/2022-2023 | 240/DW/22-23 | 04/07/2022 | 04/07/2022 | BENNETT COLEMAN & COMPANY LIMITED | 1.89 | 0 | 0 | 0
6 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Natungram Piped Water Supply Scheme | SM/06970 | Retrofitting | Providing leftout water tap connection in different villages for 100% coverage to make it Sajal Gram from existing distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Burdwan ¿ I Block under Burdwan Division, PHE. Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000342/2021-2022 | 32/BWD | 04/01/2022 | 03/02/2022 | ROY BISWAS CONSTRUCTION | 9.89 | 0 | 0 | 1
7 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Natungram Piped Water Supply Scheme | SM/06970 | Retrofitting | Providing 45 Nos.FHTC at SIJEPARA village for declearation of SWAJALGRAM under NATUNGRAM Piped Water Supply Scheme , Block- Burdwan-I within Burdwan Sub Division under Burdwan Division PHE Dte |  | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000298/2024-2025 | 1280/BSD | 12/07/2024 | 26/08/2024 | SHANKHA GHOSH | 1.76 | 0 | 0 | 0
8 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Natungram Piped Water Supply Scheme | SM/06970 | Retrofitting | Providing 50 Nos.FHTC at BIRPUR village for declearation of SWAJALGRAM under NATUNGRAM Piped Water Supply Scheme , Block- Burdwan-I within Burdwan Sub Division under Burdwan Division PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE,Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000299/2024-2025 | 1281/BSD | 12/07/2024 | 26/08/2024 | I.S. ENTERPRISE | 2.28 | 0 | 0 | 100
Total | [13 empty] | 76.82 | 54.15 | 70.49