## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Natu Piped Water Supply Scheme | SM/06972 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Natu village of Natu piped water supply scheme within Headquarters under Burdwan Division, PHE Dte. [Phase-I](Tr No.-162/BWD/2020-21) |  |  | ORD/000080/2020-2021 | 2687/BWD | 07/08/2020 | 06/09/2020 | SINGHA ROY AND CO. | 4.92 | 9.84 | 200 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Natu Piped Water Supply Scheme | SM/06972 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Haripur village of Natu piped water supply scheme within Headquarters under Burdwan Division, PHE Dte. [Phase-I](Tr No.-161/BWD/2020-21) |  |  | ORD/000081/2020-2021 | 2688/BWD | 07/08/2020 | 06/09/2020 | MITRA CONSTRUCTION | 4.92 | 9.84 | 200 | 1
3 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Natu Piped Water Supply Scheme | SM/06972 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Haripur village of Natu piped water supply scheme within Headquarters under Burdwan Division, PHE Dte. [Phase-I](Tr No.-278/BWD/2020-21) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000295/2020-2021 | 3365/BWD | 21/09/2020 | 21/10/2020 | MITRA CONSTRUCTION | 4.92 | 9.84 | 200 | 1
4 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Natu Piped Water Supply Scheme | SM/06972 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Natu Piped Water Supply Scheme at Notu (2 Nos Habitation Part), Horipur (4 Nos Habitation Part), Uttar Mohanpur Village (Mouza), Raina-I Block under Burdwan Division, PHE Dte.(Agreement No. 49/2020-2021 OF SE/CC/PHE. DTE.) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000126/2020-2021 | 4767/BWD | 01/12/2020 | 01/03/2021 | SINGHA ROY AND CO. | 57.87 | 82.52 | 142.61 | 1
5 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Natu Piped Water Supply Scheme | SM/06972 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Natu village of Natu piped water supply scheme within Headquarters under Burdwan Division, PHE Dte. [Phase-I](Tr No.-276/BWD/2020-21) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000297/2020-2021 | 3363/BWD | 21/09/2020 | 21/10/2020 | SINGHA ROY AND CO. | 4.46 | 8.92 | 200 | 1
6 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Natu Piped Water Supply Scheme | SM/06972 | Retrofitting | Supply of SS316 grade flow control valve for FHTC at different water supply schemes within Kalna Sub-Division under Burdwan Division, PHE Dte. and delivered at Barsul Divisional store.[Part-2] | Assistant Engineer |  | ORD/001307/2020-2021 | 1792 /BWD | 26/02/2021 | 08/03/2021 | INDIA PIPE FITTING CO | 9.7 | 3.13 | 32.23 | 1
7 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Natu Piped Water Supply Scheme | SM/06972 | Retrofitting | Providing leftout water tap connection in different villages for 100% coverage to make it Sajal Gram from existing distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Raina ¿ I Block under Burdwan Division, PHE. Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000344/2021-2022 | 39/BWD | 05/01/2022 | 04/02/2022 | HAFIJUR RAHAMAN MIDYA | 15.62 | 0.62 | 3.97 | 1
8 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Natu Piped Water Supply Scheme | SM/06972 | Retrofitting | Extension of 75 mm dia pipeline at Miya Para, Modhya Bohar & Bhagar Para Purba Bohar regarding FHTC under Satgachia (Zone-I) water supply scheme under Burdwan Division, PHE Dte.[Gr.-A] | Assistant Engineer ,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000350/2021-2022 | 703/BSD | 11/06/2021 | 16/06/2021 | M/S SAYAN CHAKRABORTY | 0.88 | 0.81 | 91.67 | 1
9 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Natu Piped Water Supply Scheme | SM/06972 | Retrofitting | Laying Parallel Pipeline to improve drinking water supply, Construction of Boundary wall, Path Way, Drain at Head Work Site and providing leftout FHTC, Road Restoration with allied work for NATU Piped Water Supply Scheme, Block-Raina-I within Burdwan Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000373/2024-2025 | 2994/BWD | 01/08/2024 | 01/12/2025 | ANWESHA CONSTRUCTION | 55.19 | 0 | 0 | 75
Total | [13 empty] | 158.48 | 125.52 | 79.21