## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional House Hold Tap Connection (FHTC) by retrofitting within the command area of Sahapurr Piped Water Supply Scheme | SM/07201 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Sahapur (Pt-A) village of Sahapur Piped Water Supply Scheme within Katwa Sub-Divn. under Burdwan Division, PHE. Dte. [Phase - I] [SL.No : 11A] (Agreement no. 500/BWD of 2020-21) | Assistant Engineer |  | ORD/000143/2020-2021 | 2608/BWD | 04/08/2020 | 03/09/2020 | RAINBOW CONSTRUCTION | 4.92 | 4.92 | 100 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional House Hold Tap Connection (FHTC) by retrofitting within the command area of Sahapurr Piped Water Supply Scheme | SM/07201 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Sahapur (Pt-A) village of Sahapur Piped Water Supply Scheme within Katwa Sub-Divn. under Burdwan Division, PHE. Dte. [Phase - I] [SL.No : 11A] (Agreement no.505/BWD of 2020-21) | Assistant Engineer |  | ORD/000144/2020-2021 | 2607/BWD | 04/08/2020 | 03/09/2020 | DUBE ENTERPRISE | 4.92 | 4.92 | 100 | 1
3 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional House Hold Tap Connection (FHTC) by retrofitting within the command area of Sahapurr Piped Water Supply Scheme | SM/07201 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Sahapur (Pt-B) village of Sahapur Piped Water Supply Scheme within Katwa Sub-Divn. under Burdwan Division, PHE. Dte. [Phase - I] [SL.No : ¿11B¿](Agreement no.-497/BWD of 2020-21) | Assistant Engineer |  | ORD/000146/2020-2021 | 4913/BWD | 08/12/2020 | 07/01/2021 | DUBE ENTERPRISE | 2.84 | 0 | 0 | 1
4 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional House Hold Tap Connection (FHTC) by retrofitting within the command area of Sahapurr Piped Water Supply Scheme | SM/07201 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Sahapur (Part-A) village of Sahapur piped water supply scheme within Katwa Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-503/BWD/20-21) | Assistant Engineer |  | ORD/000176/2020-2021 | 238/KTS | 30/09/2020 | 04/10/2020 | RAINBOW CONSTRUCTION | 1.45 | 1.45 | 99.85 | 1
5 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional House Hold Tap Connection (FHTC) by retrofitting within the command area of Sahapurr Piped Water Supply Scheme | SM/07201 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in SAHAPUR (Part-B) village of Sahapur piped water supply scheme within Katwa Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-494/BWD/2020-21) | Assistant Engineer |  | ORD/000174/2020-2021 | 239/KTS | 30/09/2020 | 04/10/2020 | DUBE ENTERPRISE | 1.42 | 1.41 | 99.25 | 1
6 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional House Hold Tap Connection (FHTC) by retrofitting within the command area of Sahapurr Piped Water Supply Scheme | SM/07201 | Retrofitting | Publication charges bill for the office of the Executive Engineer, Burdwan Division, PHE Dte.[Invoice No.-BCWB20RV-0001293, dt.-19/05/20, BCWB20RV-0001770, dt.-31/05/20, BCWB20RV-0001920, dt.-05/06/20, BCWB20RV-0001860, dt.-03/06/20, BCWB20RV-0001861, dt.-03/06/20, BCWB20RV-0001928, dt.-05/06/20, BCWB20RV-0001820, dt.-03/06/20, BCWB19RV-0059455, dt.-20/03/20, BCWB19RV-0059454. dt.-20/03/20, BCWB19RV-0057682, dt.-12/03/20, BCWB20RV-0003210, dt.-26/06/20, BCWB20RV-0000918, dt.-07/05/20, BCWB20RV-0001352, dt.-22/05/20, BCWB19RV-0050592, dt.-30/01/20] |  |  | VCH/000411/2022-2023 | 240/DW/22-23 | 04/07/2022 | 04/07/2022 | BENNETT COLEMAN & COMPANY LIMITED | 1.89 | 0 | 0 | 0
7 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional House Hold Tap Connection (FHTC) by retrofitting within the command area of Sahapurr Piped Water Supply Scheme | SM/07201 | Retrofitting | Hire & fuel charges of vehicle (Car No.-WB-04G-7127) for the month of May & June'23. |  |  | BILL/00791/2023-2024 | 632/JJM | 13/09/2023 | 13/09/2023 | PARTHA PRATIM ACHARYA | 0.77 | 0 | 0 | 0
8 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional House Hold Tap Connection (FHTC) by retrofitting within the command area of Sahapurr Piped Water Supply Scheme | SM/07201 | Retrofitting | Detail route survey, design of distribution network and preparation of estimate, drawing & DPR for providing FHTC in the scheme AGRADWIP, KHETPUR PALASHI, SAHAPUR PWSS (Sl No-1) | Assistant Engineer | JUNIOR ENGINEER KATWA SUB-DIVISION PHE DTE | ORD/000069/2023-2024 | 393/KTS | 13/04/2023 | 13/05/2023 | SIRCON ENGINEERING SERVICES | 3.71 | 0 | 0 | 100
9 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional House Hold Tap Connection (FHTC) by retrofitting within the command area of Sahapurr Piped Water Supply Scheme | SM/07201 | Retrofitting | Augmentation of SAHAPUR Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC & renovation of switch-rooms & boundary walls at different TW site under Katwa-II Block, District:- Purba-Bardhaman. | Assistant Engineer | JUNIOR ENGINEER KATWA SUB-DIVISION PHE DTE | ORD/000132/2023-2024 | 2343/BWD | 22/05/2023 | 19/09/2023 | KHEPIMA ENGINEERS CO. OPERATIVE SOCIETY LTD. | 137.76 | 0 | 0 | 95
10 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional House Hold Tap Connection (FHTC) by retrofitting within the command area of Sahapurr Piped Water Supply Scheme | SM/07201 | Retrofitting | Continuation work order for Supply of 1 (one) No. Diesel driven Ambassador Car (Luxury Taxi) / Motor Cab on hire basis for the Office of the Assistant Engineer, under Katwa Sub-Division within Burdwan Division, P.H.E. Dte. [Period from 01.07.2024 to 31.12.2024]. | Assistant Engineer | JUNIOR ENGINEER KATWA SUB-DIVISION PHE DTE | ORD/000562/2024-2025 | 788/KTS | 28/06/2024 | 28/12/2024 | KRISHNA MONDAL | 2.4 | 0 | 0 | 80
Total | [13 empty] | 162.1 | 12.7 | 7.83