## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional House Hold Tap Connection (FHTC) by retrofitting within the command area of Kshetpur Palashi Piped Water Supply Scheme | SM/07202 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Khetpur (Pt-B) village of Khetpur Palasi piped water supply scheme within Katwa Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-165/BWD/2020-21) | Assistant Engineer |  | ORD/000105/2020-2021 | 2605/BWD | 04/08/2020 | 03/09/2020 | SANTANU BHATTACHARYAY | 4.92 | 4.92 | 100 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional House Hold Tap Connection (FHTC) by retrofitting within the command area of Kshetpur Palashi Piped Water Supply Scheme | SM/07202 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Khetpur (Pt.-A) village of Khetpur Palasi piped water supply scheme within Katwa Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-183/BWD/2020-21) | Assistant Engineer |  | ORD/000104/2020-2021 | 2601/BWD | 04/08/2020 | 03/09/2020 | CHANCHAL PAL | 4.92 | 4.92 | 100 | 1
3 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional House Hold Tap Connection (FHTC) by retrofitting within the command area of Kshetpur Palashi Piped Water Supply Scheme | SM/07202 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Khetpur Palashi (Pt-B) village of Khetpur Palashi piped water supply scheme within Katwa Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-463/BWD/2020-21) | Assistant Engineer |  | ORD/000284/2020-2021 | 242/KTS | 01/10/2020 | 05/10/2020 | SANTANU BHATTACHARYAY | 1.21 | 1.2 | 99.21 | 1
4 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional House Hold Tap Connection (FHTC) by retrofitting within the command area of Kshetpur Palashi Piped Water Supply Scheme | SM/07202 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Khetpur (Pt-A) village of Khetpur-Palashi piped water supply scheme within Katwa Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-257/BWD/2020-21) | Assistant Engineer |  | ORD/000473/2020-2021 | 3528-A/BWD | 25/09/2020 | 25/10/2020 | CHANCHAL PAL | 2.81 | 2.81 | 100 | 1
5 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional House Hold Tap Connection (FHTC) by retrofitting within the command area of Kshetpur Palashi Piped Water Supply Scheme | SM/07202 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Khetpur village of Khetpur Palashi piped water supply scheme within Katwa Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/000626/2020-2021 | 366/KTS | 15/12/2020 | 22/12/2020 | TAPAS KUMAR ROY | 2.82 | 2.8 | 99.31 | 1
6 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional House Hold Tap Connection (FHTC) by retrofitting within the command area of Kshetpur Palashi Piped Water Supply Scheme | SM/07202 | Retrofitting | Construction of sluice valve chamber (80 mm dia S/V) of Khetpur Palashi piped water supply scheme under Katwa Sub-Division under Burdwan Division, PHE Dte.[Sl No.-01] | Assistant Engineer |  | ORD/000731/2020-2021 | 14/KTS | 08/01/2021 | 11/01/2021 | CHANCHAL PAL | 0.41 | 0.41 | 100 | 1
7 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional House Hold Tap Connection (FHTC) by retrofitting within the command area of Kshetpur Palashi Piped Water Supply Scheme | SM/07202 | Retrofitting | Providing Functional Household Tap Connection from existing distribution system within the command area of Kshetpur Palashi PWSS under Katwa Sub-Division under Burdwan Division PHE Dte. [Sl No-1] | Assistant Engineer |  | ORD/000589/2021-2022 | 126/KTS | 21/02/2022 | 23/03/2022 | SANTANU BHATTACHARYAY | 3.19 | 0 | 0 | 1
8 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional House Hold Tap Connection (FHTC) by retrofitting within the command area of Kshetpur Palashi Piped Water Supply Scheme | SM/07202 | Retrofitting | Hire & fuel charges of vehicle (Car No.-WB-41H/3668) for the office of the Assistant Engineer, RWS Burdwan Sub-Division, PHE Dte. for the month of July & August'2022. |  |  | VCH/000645/2022-2023 | 612/VEH/22-23 | 23/09/2022 | 23/09/2022 | MD HASIN | 0.56 | 0 | 0 | 0
9 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional House Hold Tap Connection (FHTC) by retrofitting within the command area of Kshetpur Palashi Piped Water Supply Scheme | SM/07202 | Retrofitting | Continuation work order for supply of 10 mm NB Gun-Metal /Brass Ferrul conforming to IS:2692-1989 for water tap connection in each household from existing distribution system within scheme jurisdiction in different piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. and delivered at Barsul Divisional Store.[Part-6] | Assistant Engineer |  | ORD/000867/2020-2021 | 4318/BWD | 04/11/2020 | 14/11/2020 | MD HASIN | 4.93 | 0 | 0 | 1
10 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional House Hold Tap Connection (FHTC) by retrofitting within the command area of Kshetpur Palashi Piped Water Supply Scheme | SM/07202 | Retrofitting | Hire & fuel charges of vehicle (Car No.-WB-04G-6018) for the office of the Assistant Engineer, Katwa Sub-Division, PHE Dte. for the month of January'23. |  |  | BILL/00468/2022-2023 | 1118/JJM | 27/02/2023 | 27/02/2023 | M/S MUNMUN DEY | 0.26 | 0 | 0 | 0
11 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional House Hold Tap Connection (FHTC) by retrofitting within the command area of Kshetpur Palashi Piped Water Supply Scheme | SM/07202 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Khetpur Palashi (Part-A) village of Khetpur Palashi piped water supply scheme within Katwa Sub-Division under Burdwan Division, PHE Dte. (Tr No.-471/BWD/2020-21) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000350/2020-2021 | 241/KTS | 01/10/2020 | 05/10/2020 | CHANCHAL PAL | 1.19 | 1.17 | 97.83 | 1
12 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional House Hold Tap Connection (FHTC) by retrofitting within the command area of Kshetpur Palashi Piped Water Supply Scheme | SM/07202 | Retrofitting | Detail route survey, design of distribution network and preparation of estimate, drawing & DPR for providing FHTC in the scheme AGRADWIP, KHETPUR PALASHI, SAHAPUR PWSS (Sl No-1) | Assistant Engineer | JUNIOR ENGINEER KATWA SUB-DIVISION PHE DTE | ORD/000069/2023-2024 | 393/KTS | 13/04/2023 | 13/05/2023 | SIRCON ENGINEERING SERVICES | 3.71 | 0 | 0 | 100
Total | [13 empty] | 30.93 | 18.23 | 58.93