## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional House Hold Tap Connection (FHTC) by retrofitting within the command area of Ekaihat Piped Water Supply Scheme | SM/07203 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Akaihat village of Ekaihat piped water supply scheme within Katwa Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-196/BWD/2020-21) | Assistant Engineer |  | ORD/000107/2020-2021 | 2597/BWD | 04/08/2020 | 03/09/2020 | JAI MAA DURGA & CO. | 4.92 | 9.84 | 200 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional House Hold Tap Connection (FHTC) by retrofitting within the command area of Ekaihat Piped Water Supply Scheme | SM/07203 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Bikaihat & Akaihat village of Ekaihat piped water supply scheme within Katwa Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-169/BWD/2020-21) | Assistant Engineer |  | ORD/000106/2020-2021 | 2598/BWD | 04/08/2020 | 03/09/2020 | JAGADANANDAPUR CO. OP. LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 4.92 | 9.84 | 200 | 1
3 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional House Hold Tap Connection (FHTC) by retrofitting within the command area of Ekaihat Piped Water Supply Scheme | SM/07203 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Ekaihat & Bikaihat (Pt-A) village of Ekaihat piped water supply scheme within Katwa Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-486/BWD/2020-21) | Assistant Engineer |  | ORD/000265/2020-2021 | 236/KTS | 30/09/2020 | 04/10/2020 | JAI MAA DURGA & CO. | 1.29 | 2.55 | 197.37 | 1
4 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional House Hold Tap Connection (FHTC) by retrofitting within the command area of Ekaihat Piped Water Supply Scheme | SM/07203 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Ekaihat village of Ekaihat piped water supply scheme within Katwa Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-329/BWD/2020-21) | Assistant Engineer |  | ORD/000261/2020-2021 | 3739/BWD | 07/10/2020 | 06/11/2020 | JAI MAA DURGA & CO. | 1.74 | 3.47 | 200 | 1
5 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional House Hold Tap Connection (FHTC) by retrofitting within the command area of Ekaihat Piped Water Supply Scheme | SM/07203 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Ekaihat & Bikaihat (Part-B) village of Ekaihat & Bikaihat piped water supply scheme within Katwa Sub-Division under Burdwan Division, PHE Dte. (Tr No.-539/BWD/2020-21) | Assistant Engineer |  | ORD/000357/2020-2021 | 237/KTS | 30/09/2020 | 04/10/2020 | JAGADANANDAPUR CO. OP. LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 1.32 | 2.65 | 200.06 | 1
6 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional House Hold Tap Connection (FHTC) by retrofitting within the command area of Ekaihat Piped Water Supply Scheme | SM/07203 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Bikaihat & Ekaihat village of Ekaihat piped water supply scheme within Katwa Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-538/BWD/2020-21) | Assistant Engineer |  | ORD/000474/2020-2021 | 3697/BWD | 05/10/2020 | 04/11/2020 | JAGADANANDAPUR CO. OP. LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 1.79 | 3.59 | 200 | 1
7 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional House Hold Tap Connection (FHTC) by retrofitting within the command area of Ekaihat Piped Water Supply Scheme | SM/07203 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Ekaihat & Bikaihat village of Ekaihat piped water supply scheme within Katwa Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/000625/2020-2021 | 364/KTS | 15/12/2020 | 22/12/2020 | BISHWAJIT DAS | 1.18 | 2.35 | 200 | 1
8 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional House Hold Tap Connection (FHTC) by retrofitting within the command area of Ekaihat Piped Water Supply Scheme | SM/07203 | Retrofitting | Providing Functional Household Tap Connection from existing distribution system within the command area of Akaihat and Bikihat PWSS under Katwa Sub-Division under Burdwan Division PHE Dte. (Sl No-1) | Assistant Engineer |  | ORD/000238/2021-2022 | 750/KTS | 24/11/2021 | 09/12/2021 | JAI MAA DURGA & CO. | 2.54 | 2.52 | 99.04 | 1
9 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional House Hold Tap Connection (FHTC) by retrofitting within the command area of Ekaihat Piped Water Supply Scheme | SM/07203 | Retrofitting | Continuation work order for supply of 10 mm NB Gun-Metal /Brass Ferrul conforming to IS:2692-1989 for water tap connection in each household from existing distribution system within scheme jurisdiction in different piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. and delivered at Barsul Divisional Store.[Part-6] | Assistant Engineer |  | ORD/000867/2020-2021 | 4318/BWD | 04/11/2020 | 14/11/2020 | MD HASIN | 4.93 | 0.61 | 12.29 | 1
10 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional House Hold Tap Connection (FHTC) by retrofitting within the command area of Ekaihat Piped Water Supply Scheme | SM/07203 | Retrofitting | Detail route survey, design of distribution network and preparation of estimate, drawing & DPR for providing FHTC in the scheme EKAIHAT, PANUHAT PWSS (Sl No-2) | Assistant Engineer | JUNIOR ENGINEER KATWA SUB-DIVISION PHE DTE | ORD/000070/2023-2024 | 394/KTS | 13/04/2023 | 13/05/2023 | SIRCON ENGINEERING SERVICES | 2.48 | 1.24 | 50 | 100
11 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional House Hold Tap Connection (FHTC) by retrofitting within the command area of Ekaihat Piped Water Supply Scheme | SM/07203 | Retrofitting | Vehicle bill [Car No.-WB-04G-6018] for the month of September & October'2023. |  |  | BILL/02056/2023-2024 | 1269/JJM | 16/01/2024 | 16/01/2024 | M/S MUNMUN DEY | 0.49 | 0 | 0 | 0
12 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional House Hold Tap Connection (FHTC) by retrofitting within the command area of Ekaihat Piped Water Supply Scheme | SM/07203 | Retrofitting | Vehicle bill [Car No.-WB-04G-6018] for the month of November & December'2023. |  |  | BILL/02053/2023-2024 | 1894/JJM | 28/03/2024 | 28/03/2024 | M/S MUNMUN DEY | 0.45 | 0 | 0 | 0
13 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional House Hold Tap Connection (FHTC) by retrofitting within the command area of Ekaihat Piped Water Supply Scheme | SM/07203 | Retrofitting | Necessary FHTC work of Ekaihat PWSS under Katwa Sub-Division Block Katwa-I Burdwan Division PHE Dte. (Sl No -5) | Assistant Engineer | Junior Engineer, R.W.S., Katwa-I Dev. Block | ORD/001052/2024-2025 | 1609/KTS | 14/11/2024 | 29/12/2024 | HAMID SK | 0.95 | 0 | 0 | 90
Total | [13 empty] | 28.99 | 38.66 | 133.33