## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional House Hold Tap Connection (FHTC) by retrofitting within the command area of Shaktigarh Piped Water Supply Scheme | SM/07204 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Saktigarh (Pt-A) village of Saktigarh piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-172/BWD/2020-21) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000098/2020-2021 | 2747/BWD | 10/08/2020 | 09/09/2020 | SARKAR AGENCY | 4.92 | 4.92 | 100 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional House Hold Tap Connection (FHTC) by retrofitting within the command area of Shaktigarh Piped Water Supply Scheme | SM/07204 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Saktigarh (Pt-B) village of Shaktigarh Piped Water Supply Scheme within Burdwan Sub-Divn. under Burdwan Division, PHE. Dte. [Phase - I] [GROUP : ¿8B¿] (T.R. No.-380/BWD/2020-21) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000151/2020-2021 | 2742/BWD | 10/08/2020 | 09/09/2020 | T.K. BANERJEE & CO. | 4.91 | 4.91 | 100 | 1
3 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional House Hold Tap Connection (FHTC) by retrofitting within the command area of Shaktigarh Piped Water Supply Scheme | SM/07204 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Saktigarh (Pt-A) village of Shaktigarh Piped Water Supply Scheme within Burdwan Sub-Divn. under Burdwan Division, PHE. Dte. [Phase - I] [GROUP : ¿8A¿] (T.R. No. 428/BWD/2020-21) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000150/2020-2021 | 3801/BWD | 08/10/2020 | 07/11/2020 | SARKAR AGENCY | 4.92 | 4.92 | 100 | 1
4 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional House Hold Tap Connection (FHTC) by retrofitting within the command area of Shaktigarh Piped Water Supply Scheme | SM/07204 | Retrofitting | Providing Functional Household Tap connection (FHTC) from existing distribution system within the command area of Saktigarh Piped water supply scheme at Shaktigarh village, Burdwan-II Block under Burdwan Division, PHE Dte. [Tr No.-101/SE/CC/2020-21] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000403/2020-2021 | 715/BWD | 28/01/2021 | 29/03/2021 | SARKAR AGENCY | 62.17 | 17.35 | 27.91 | 1
5 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional House Hold Tap Connection (FHTC) by retrofitting within the command area of Shaktigarh Piped Water Supply Scheme | SM/07204 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Shaktigarh (Part-B) village of Shaktigarh piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-649/BWD/2020-21) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000253/2020-2021 | 4271/BWD | 03/11/2020 | 03/12/2020 | T.K. BANERJEE & CO. | 4.91 | 4.91 | 100 | 1
6 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional House Hold Tap Connection (FHTC) by retrofitting within the command area of Shaktigarh Piped Water Supply Scheme | SM/07204 | Retrofitting | Construction of Pump House cum chlorine room without sanitary and water supply arrangement at 2nd tube well site for Shaktigarh & its adjoining mouzas water supply scheme , Block-Bardhaman-II under Burdwan Division, PHE Dte.[Gr.-G] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000754/2021-2022 | 1391/BSD | 07/10/2021 | 06/12/2021 | DEBJYOTI GOSWAMI | 2.77 | 0 | 0 | 1
Total | [13 empty] | 84.61 | 37.02 | 43.75