## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional House Hold Tap Connection (FHTC) by retrofitting within the command area of Nandra Piped Water Supply Scheme | SM/07205 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Nandra village of Nandra piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-176/BWD/2020-21) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000102/2020-2021 | 2735/BWD | 10/08/2020 | 09/09/2020 | BHARAT CONSTRUCTION | 4.92 | 9.84 | 200 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional House Hold Tap Connection (FHTC) by retrofitting within the command area of Nandra Piped Water Supply Scheme | SM/07205 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Kalyanpur & Dangachha village of Nandra piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-177/BWD/2020-21) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000103/2020-2021 | 2736/BWD | 10/08/2020 | 09/09/2020 | BHARAT CONSTRUCTION | 4.92 | 9.84 | 200 | 1
3 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional House Hold Tap Connection (FHTC) by retrofitting within the command area of Nandra Piped Water Supply Scheme | SM/07205 | Retrofitting | Additional Extension of UPVC distribution pipeline in connection with FHTC for NANDRA & adjoining mouzas water supply scheme at Bardhaman-I Block under Burdwan division, PHE Dte.[Gr.-C] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000743/2020-2021 | 73/BSD | 19/01/2021 | 18/02/2021 | BHARAT CONSTRUCTION | 4.22 | 8.37 | 198.26 | 1
4 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional House Hold Tap Connection (FHTC) by retrofitting within the command area of Nandra Piped Water Supply Scheme | SM/07205 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Nandra village of Nandra piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte. [Phase-I] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000714/2020-2021 | 4087/BWD | 16/10/2020 | 15/11/2020 | BHARAT CONSTRUCTION | 2 | 4 | 200 | 1
5 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional House Hold Tap Connection (FHTC) by retrofitting within the command area of Nandra Piped Water Supply Scheme | SM/07205 | Retrofitting | Providing FHTC (130 nos.) and Extension of UPVC dist. Pipeline at Noapara, Pirtala ,Nandra village of NANDRA water supply scheme at Burdwan-II Block under Burdwan Division PHE Dte..Gr. I | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000213/2021-2022 | 1479/BSD | 09/11/2021 | 09/12/2021 | BHARAT CONSTRUCTION | 4.81 | 4.81 | 100 | 1
6 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional House Hold Tap Connection (FHTC) by retrofitting within the command area of Nandra Piped Water Supply Scheme | SM/07205 | Retrofitting | Providing FHTC in Nandra & Naopara village for 100% coverage in Sajal Gram from existing distribution system within NANDRA PWSS, Bardhhaman-II Development Block under Burdwan Division, PHE Dte. Gr.F. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000339/2022-2023 | 1360/BSD | 03/08/2022 | 08/08/2022 | BHARAT CONSTRUCTION | 0.97 | 0 | 0 | 1
7 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional House Hold Tap Connection (FHTC) by retrofitting within the command area of Nandra Piped Water Supply Scheme | SM/07205 | Retrofitting | Providing leftout water tap connection in different villages for 100% coverage in Sajal Gram from existing distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Burdwan ¿ II Block under Burdwan Division, PHE. Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000416/2021-2022 | 385/BWD | 20/01/2022 | 19/02/2022 | BISWAS ENTERPRISE | 11.97 | 0 | 0 | 100
8 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional House Hold Tap Connection (FHTC) by retrofitting within the command area of Nandra Piped Water Supply Scheme | SM/07205 | Retrofitting | Providing FHTC in Nandra & Naopara village for 100% coverage in Sajal Gram from existing distribution system within Nandra PWSS, Bardhhaman-II Development Block under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000654/2022-2023 | 1360-A/BSD | 03/08/2022 | 08/08/2022 | BHARAT CONSTRUCTION | 0.97 | 0.96 | 99.6 | 1
9 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional House Hold Tap Connection (FHTC) by retrofitting within the command area of Nandra Piped Water Supply Scheme | SM/07205 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Kalyanpur & Dangachha village of Nandra Piped Water Supply Scheme within Burdwan Sub-Divn. under Burdwan Division, PHE. Dte. [Phase - I] [GROUP : ¿10B¿] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, Burdwan Sadar Sub-Division | ORD/000463/2020-2021 | 4085/BWD | 16/10/2020 | 15/11/2020 | BHARAT CONSTRUCTION | 1.65 | 3.3 | 200 | 0
Total | [13 empty] | 36.43 | 41.13 | 112.9