## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Kenna Piped Water Supply Scheme | SM/07544 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Kailaspur Habitation of Kenna Piped Water Supply Scheme within Burdwan Sub-Divn. under Burdwan Division, PHE. Dte. [GROUP : ¿L¿] (T.R. No. 201/BWD of 2020-2021) |  |  | ORD/000161/2020-2021 | 2399/BWD | 20/07/2020 | 19/08/2020 | BRINDABAN KONAR | 4.92 | 0 | 0 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Kenna Piped Water Supply Scheme | SM/07544 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Kailaspur Habitation of Kenna Piped Water Supply Scheme within Burdwan Sub-Divn. under Burdwan Division, PHE. Dte. [GROUP : ¿L¿] (T.R. No. 248/BWD of 2020-2021) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000162/2020-2021 | 3517/BWD | 25/09/2020 | 25/10/2020 | BRINDABAN KONAR | 4.92 | 0 | 0 | 1
3 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Kenna Piped Water Supply Scheme | SM/07544 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Kenna village of Kenna piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000604/2020-2021 | 1225/BWD | 11/02/2021 | 13/03/2021 | BRINDABAN KONAR | 4.92 | 9.84 | 200 | 1
4 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Kenna Piped Water Supply Scheme | SM/07544 | Retrofitting | Extension of pipeline for Kenna Water Supply Scheme (Kenna, Dahura, Kailashpur, Dadur, Baral Village) within Memari - I Block including leftout household water tap connection (FHTC) under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000207/2021-2022 | 6307/BWD | 09/11/2021 | 08/01/2022 | T.K. BANERJEE & CO. | 41.46 | 41.02 | 98.92 | 1
5 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Kenna Piped Water Supply Scheme | SM/07544 | Retrofitting | Extension of pipeline for KENNA Piped Water Supply Scheme at Kaliashpur 25 Nos FHTC Work for Sajal Gram (As per Field Verification Report for Har Ghar Jal Certification within Memari-I Block including leftout household water tap connection (FHTC) under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, RWS, Memari-I Dev. Bolck | ORD/000848/2022-2023 | 1391-A/BSD | 08/08/2022 | 13/08/2022 | BRINDABAN KONAR | 0.97 | 0 | 0 | 0
6 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Kenna Piped Water Supply Scheme | SM/07544 | Retrofitting | Providing leftout water tap connection in different villages for 100% coverage to make it Sajal Gram from existing distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Memari-I Block (Daluibazar-II, Gopegantar-I & II G.P.) under Burdwan Division, PHE. Dte. Dte._Part-A. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000371/2021-2022 | 209/BWD | 11/01/2022 | 10/02/2022 | M/S ANAND CONSTRUCTION | 21.11 | 5 | 23.68 | 1
7 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Kenna Piped Water Supply Scheme | SM/07544 | Retrofitting | Hire & fuel charges of vehicle (Car No.-WB-41G-2149) for the office of the Assistant Engineer, Burdwan Sub-Division, PHE Dte. for the month of February'23. |  |  | BILL/00565/2022-2023 | 1226/JJM | 20/03/2023 | 20/03/2023 | SK.ASFIA | 0.4 | 0 | 0 | 0
8 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Kenna Piped Water Supply Scheme | SM/07544 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of KENNA Piped Water Supply Scheme at Dandur, Kailashpur (2 Nos. Habitation) village (Mouza), Memari - I Block under Burdwan Division, PHE Dte.[Agreement No. 570/BWD OF 2020-2021.] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000329/2020-2021 | 438/BWD | 19/01/2021 | 18/02/2021 | BRINDABAN KONAR | 22.09 | 43.57 | 197.26 | 0
Total | [13 empty] | 100.78 | 99.43 | 98.65