## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Dharma Danga Piped Water Supply Scheme | SM/07545 | Retrofitting | Continuation order for water tap connection in each house hold from existing distribution system within scheme jurisdiction in Rameswarpur village and Rameswarpur habitation of Dharmadanga piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte.[Phase-I][Group-1B] | Assistant Engineer |  | ORD/000732/2020-2021 | 4743/BWD | 01/12/2020 | 31/12/2020 | TAPAS KUMAR ROY | 3.2 | 0 | 0 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Dharma Danga Piped Water Supply Scheme | SM/07545 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Madhuban village of Dharmadanga Piped Water Supply Scheme within Kalna Sub-Divn. under Burdwan Division, PHE. Dte. [Phase - I] [Sl.No : 6B] | Assistant Engineer |  | ORD/000972/2020-2021 | 4745/BWD | 01/12/2020 | 31/12/2020 | KHEPIMA ENGINEERS CO. OPERATIVE SOCIETY LTD. | 2.66 | 2.66 | 100 | 1
3 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Dharma Danga Piped Water Supply Scheme | SM/07545 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Dharmadanga Piped Water Supply Scheme at Dharmadanga (P) Village (Mouza), Kalna-I Block under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/000255/2021-2022 | 6641/BWD | 29/11/2021 | 29/12/2021 | INVENT ENGINEERS CO. OPERATIVE SOCIETY LTD. | 14.94 | 15.39 | 103 | 1
4 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Dharma Danga Piped Water Supply Scheme | SM/07545 | Retrofitting | Extension of different dia UPVC pipeline at Rameswarpur village of Dharmadanga water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. [Sl No.-A] | Assistant Engineer |  | ORD/000829/2020-2021 | 167/KSD | 19/02/2021 | 21/03/2021 | BISHWAJIT DAS | 3.97 | 0 | 0 | 1
5 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Dharma Danga Piped Water Supply Scheme | SM/07545 | Retrofitting | Water tap connection in each household from existing distribution system within scheme jurisdiction in Koldanga-Mirpur village (35 Nos) & Rameswarpur village (50 Nos) (Total-85 Nos) of Dharmadanga water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte.[SL NO.-C] | Assistant Engineer |  | ORD/000321/2021-2022 | 1026/KSD | 01/10/2021 | 16/10/2021 | SETH ENTERPRISE | 2.95 | 2.95 | 100 | 1
6 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Dharma Danga Piped Water Supply Scheme | SM/07545 | Retrofitting | Work order for "Providing Functional house hold tap connections for Sajal Gram Village within Kalna-I Block under Kalna Sub-Division under Burdwan Division, PHE Dte. (Dharmadanga Water Supply Scheme) Sl No- 5 | Assistant Engineer | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000689/2022-2023 | 101/KSD | 08/02/2023 | 08/03/2023 | BUILD-TECH | 0.88 | 0.88 | 99.44 | 100
7 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Dharma Danga Piped Water Supply Scheme | SM/07545 | Retrofitting | Work Order for "Providing Functional house hold tap connections within command ares of Dharmadanga water supply scheme within Kalna-I Block under Kalna Sub-Division under Burdwan Division, PHE Dte." | Assistant Engineer | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000550/2023-2024 | 1305/KSD | 23/08/2023 | 07/09/2023 | BISWAS ENTERPRISE | 2.81 | 1.81 | 64.65 | 100
8 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Dharma Danga Piped Water Supply Scheme | SM/07545 | Retrofitting | Designing, Making and Erection of Sign Board for SAJAL GRAM in Madhuban (P) Village, Kalna - I Block within Dharma Danga PWSS under Burdwan Division, PHE Dte. (5 Nos Board) | AE(HQs) | J.E. 1 BURDWAN | ORD/000794/2023-2024 | 873/AE/HQ | 07/11/2023 | 07/12/2023 | PAPRI HAZRA | 0.76 | 0.72 | 95.4 | 100
9 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Dharma Danga Piped Water Supply Scheme | SM/07545 | Retrofitting | Designing, Making and Erection of Sign Board for SAJAL GRAM in Rameswarpur (P) Village, Kalna - I Block within Dharma Danga PWSS under Burdwan Division, PHE Dte. (5 Nos Board) | AE(HQs) | J.E. 1 BURDWAN | ORD/000741/2023-2024 | 836/AE/HQ | 31/10/2023 | 30/11/2023 | MUNSHI JAVEDUR JAMAN | 0.76 | 0.72 | 95.4 | 100
10 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Dharma Danga Piped Water Supply Scheme | SM/07545 | Retrofitting | Hire & fuel charges of vehicle (Car No.-WB-04G-6018) for the office of the Assistant Engineer, Katwa Sub-Division, PHE Dte. for the month of March'23. |  |  | BILL/00290/2023-2024 | 204/JJM | 01/06/2023 | 01/06/2023 | M/S MUNMUN DEY | 0.28 | 0 | 0 | 0
11 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Dharma Danga Piped Water Supply Scheme | SM/07545 | Retrofitting | Work Order for "Laying distribution system including providing FHTC in the leftout portion of Dharmadanga (SM/07545) water supply scheme under Kalna Sub-Division under Burdwan Division, PHE Dte.". | Assistant Engineer | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000953/2024-2025 | 1921/KSD | 02/12/2024 | 01/01/2025 | H SAMANTA | 2.02 | 0 | 0 | 0
12 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Dharma Danga Piped Water Supply Scheme | SM/07545 | Retrofitting | Rest portion of OHR work (Plastering, Priming & Painting and interconnection of Rising Main with Specials) & Construction of Boundary wall with Smriti Saudha at Aug. of DHARMADANGA Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. (Length - 81.01 Mtr, No of Columns=28 Nos. Centre to Centre- 3.0 Mtr.). | Assistant Engineer | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000995/2023-2024 | 267/BWD | 15/01/2024 | 15/03/2024 | S.K. CONSTRUCTION | 27.45 | 26.2 | 95.44 | 100
13 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Dharma Danga Piped Water Supply Scheme | SM/07545 | Retrofitting | Work Order for 'Laying distribution system including providing FHTC in the left out portion of Dharmadanga piped water supply scheme under Kalna Sub-Division under Burdwan Division, PHE Dte.'. | Assistant Engineer | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000806/2024-2025 | 1770/KSD | 20/11/2024 | 20/12/2024 | BISWAS ENTERPRISE | 1.67 | 1.37 | 82.29 | 100
14 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Dharma Danga Piped Water Supply Scheme | SM/07545 | Retrofitting | Balance work for construction of OHR having capacity 300 CuM along with other allied works in connection with augmentation of Dharmadanga PWSS under Kalna Sub Division under Burdwan Division, PHE. Dte. | Assistant Engineer | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000331/2025-2026 | 1354/BWD | 06/05/2025 | 20/06/2025 | S.K. CONSTRUCTION | 15.87 | 0 | 0 | 100
Total | [13 empty] | 80.21 | 52.71 | 65.71