## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Itla Piped Water Supply Scheme | SM/07549 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of ITLA Piped Water Supply Scheme at Itla (Itla Adibasipara Habitation) & Sudipur (Sudipur Habitation) Village (Mouza), Jamalpur Block under Burdwan Division, PHE Dte. (Agreement No. 583/BWD OF 2020-2021.) | AE(HQs) |  | ORD/000275/2020-2021 | 545/BWD | 22/01/2021 | 23/03/2021 | ANWESHA CONSTRUCTION | 17.35 | 0 | 0 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Itla Piped Water Supply Scheme | SM/07549 | Retrofitting | Interconnection between inlet & delivery pipe with main distribution pipeline within command area of ITLA Piped W/S. Scheme, Jamalpur Block under Burdwan Division, PHE. Dte. | AE(HQs) | J.E. 2 BURDWAN | ORD/000825/2022-2023 | 213/AE/HQ | 31/03/2023 | 30/04/2023 | BHARAT CONSTRUCTION | 0.87 | 0 | 0 | 0
3 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Itla Piped Water Supply Scheme | SM/07549 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of ITLA Piped Water Supply Scheme at Bahadurpur (Bahadurpur Habitation) Village (Mouza), Jamalpur Block under Burdwan Division, PHE Dte. | AE(HQs) |  | ORD/000276/2020-2021 | 617/BWD | 25/01/2021 | 26/03/2021 | A R TRADERS | 19.81 | 0 | 0 | 1
4 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Itla Piped Water Supply Scheme | SM/07549 | Retrofitting | Laying of uPVC pipe for providing FHTC at Itla Village within Itla Piped Water Supply Scheme, Jamalpur Block under Burdwan Division P.H.E Dte. [Group : E] | AE(HQs) |  | ORD/000489/2021-2022 | 66/AE/HQ | 11/02/2022 | 13/03/2022 | MAUVE ENGINEERING AND SERVICES PVT LTD | 4.73 | 0 | 0 | 100
5 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Itla Piped Water Supply Scheme | SM/07549 | Retrofitting | Repairing and restoration of damaged and chokaged various dia UPVC pipeline and Construction of Valve chambers to control flow of water for providing FHTC in ITLA Piped W/S. Scheme at Jamalpur Dev Block under Burdwan Division ,P.H.E Dte._Gr-I | AE(HQs) |  | ORD/000667/2021-2022 | 147/AE/HQ | 16/03/2022 | 05/04/2022 | BHARAT CONSTRUCTION | 4.55 | 0 | 0 | 1
6 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Itla Piped Water Supply Scheme | SM/07549 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of ITLA Piped Water Supply Scheme at Itla (Itla Habitation) Village (Mouza), Jamalpur Block under Burdwan Division, PHE Dte. [Agreement No. 593/BWD OF 2020-2021] | AE(HQs) |  | ORD/000308/2020-2021 | 618/BWD | 25/01/2021 | 26/03/2021 | JAYANTA CHAKRABORTY | 18.36 | 0 | 0 | 1
7 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Itla Piped Water Supply Scheme | SM/07549 | Retrofitting | Re-Laying of UPVC Pipeline (damaged by Local Irrigation Work) for providing FHTC at Bag Kalapahar Mouza (Habitation) under ITLA Piped Water Supply Scheme, Jamalpur Development Block under Burdwan Division, PHE Dte. | AE(HQs) | Junior Engineer, Burdwan Division | ORD/000903/2023-2024 | 5513/BWD | 14/12/2023 | 13/01/2024 | UTPAL NANDI | 8.61 | 0 | 0 | 100
8 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Itla Piped Water Supply Scheme | SM/07549 | Retrofitting | Interconnection between OHR & Delivery line at Head Works site under ITLA PWSS, Jamalpur Dev. Block under Burdwan Division, PHE Dte. | AE(HQs) | Junior Engineer, Burdwan Division | ORD/000629/2024-2025 | 747/AE/HQ | 13/09/2024 | 13/10/2024 | DEBJYOTI GOSWAMI | 0.8 | 0 | 0 | 100
9 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Itla Piped Water Supply Scheme | SM/07549 | Retrofitting | Construction of Boundary wall, Land Development for various PWSS, Block- Jamalpur, District:- Purba-Bardhaman within Burdwan Sub Division under Burdwan Division PHE Dte. | AE(HQs),AE(HQs), Burdwan Division, PHE Dte. | Junior Engineer, Burdwan Division | ORD/001100/2024-2025 | 433/BWD | 20/01/2025 | 20/05/2025 | RABINDRA NATH GORANG | 132.64 | 0 | 0 | 40
Total | [13 empty] | 207.73 | 0 | 0