## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Mahindar Piped Water Supply Scheme | SM/07550 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000055/2022-2023 | 5523/BWD | 23/12/2022 | 23/12/2022 | Resource Division | 0.62 | 0 | 0 | 0
2 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Mahindar Piped Water Supply Scheme | SM/07550 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Mahindar Piped Water Supply Scheme at Mahindar Village (2 Nos habitations), Faimpur Village, Shitalpur Village, Sahapur Village (2 Nos. habitations & Parbatpur Village (2 Nos. habitations), Jamalpur Block under Burdwan Division, PHE Dte. [Agreement No. 684/BWD OF 2020-2021.] | AE(HQs) |  | ORD/000301/2020-2021 | 1456/BWD | 18/02/2021 | 19/04/2021 | S.S. CONSTRUCTION | 73.07 | 0 | 0 | 1
3 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Mahindar Piped Water Supply Scheme | SM/07550 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Madhabpur village and Madhabpur habitation of MADHABPUR Piped Water Supply Scheme within Burdwan Sub-Divn. under Burdwan Division, PHE. Dte. [Phase - I] [GROUP : ¿7C¿] | AE(HQs),Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000846/2020-2021 | 7050/BWD | 22/12/2020 | 21/01/2021 | KAJAL MUKHERJEE | 4.86 | 0 | 0 | 1
4 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Mahindar Piped Water Supply Scheme | SM/07550 | Retrofitting | Laying of uPVC pipe for providing FHTC at Faimpur, Parbatpur, Sahapur, Silatpur and Mahindar Village within Mahindar Piped Water Supply Scheme, Jamalpur Block under Burdwan Division P.H.E Dte._Gr. F | AE(HQs) |  | ORD/000631/2021-2022 | 128/AE/HQ | 04/03/2022 | 19/03/2022 | M/S S. CHOUDHURY | 4.82 | 0 | 0 | 1
5 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Mahindar Piped Water Supply Scheme | SM/07550 | Retrofitting | Providing Functional Household Tap Connection (FHTC) at Sahapur and Faimpur village within the command area of MAHINDAR Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, PHE Dte. [Group : D] | AE(HQs) |  | ORD/000048/2022-2023 | 202/AE/HQ | 06/04/2022 | 06/05/2022 | DEBJYOTI GOSWAMI | 4.84 | 0 | 0 | 1
6 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Mahindar Piped Water Supply Scheme | SM/07550 | Retrofitting | Laying of rising main for interconnection of Pump House No 1 & 2 and distribution main alongwith bypass arrangement for Over Head Reservoir for Mahindar Piped water supply scheme within Jamalpur Block under Burdwan Division, PHE Dte. [Gr.-D] | AE(HQs) |  | ORD/000957/2020-2021 | 1229/AE/HQ | 10/02/2021 | 12/03/2021 | APORUPA CONSTRUCTION | 4.97 | 0 | 0 | 1
7 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Mahindar Piped Water Supply Scheme | SM/07550 | Retrofitting | Providing Functional Household Tap Connection (FHTC) at Parbatpur village within the command area of MAHINDAR Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, PHE Dte. [Group : A] | AE(HQs) |  | ORD/000040/2022-2023 | 227/AE/HQ | 19/04/2022 | 19/05/2022 | M/S S. CHOUDHURY | 4.78 | 0 | 0 | 1
8 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Mahindar Piped Water Supply Scheme | SM/07550 | Retrofitting | Providing Functional Household Tap Connection (FHTC) at Mahindar village within the command area of MAHINDAR Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, PHE Dte. [Group : E] | AE(HQs) |  | ORD/000049/2022-2023 | 203/AE/HQ | 06/04/2022 | 06/05/2022 | M/S ASHA CONSTRUCTION | 4.85 | 0 | 0 | 1
9 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Mahindar Piped Water Supply Scheme | SM/07550 | Retrofitting | Repairing of concrete road damaged due to laying of pipeline within command area of MAHINDER PWSS under Burdwan Division PHE Dte. | AE(HQs) | J.E. 2 BURDWAN | ORD/000560/2023-2024 | 760/AE/HQ | 23/08/2023 | 22/09/2023 | GHOSH CONSTRUCTION | 2.68 | 0 | 0 | 100
10 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Mahindar Piped Water Supply Scheme | SM/07550 | Retrofitting | Construction of approach road to get to the Head works site of MAHINDAR Piped Water Supply Scheme, Jamalpur Block under Burdwan Division P.H.E Dte._2ND CALL [Group : G] | AE(HQs) |  | ORD/000051/2022-2023 | 205/AE/HQ | 06/04/2022 | 06/05/2022 | APORUPA CONSTRUCTION | 4.84 | 0 | 0 | 100
Total | [13 empty] | 110.33 | 0 | 0