## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Siptai Piped Water Supply Scheme | SM/07551 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Siptai Piped Water Supply Scheme at Shrimanpur Village, Siptai Village, Ilampur Village, Prijpur Village & Gohaldaha Village, Jamalpur Block under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000024/2021-2022 | 3342/BWD | 21/06/2021 | 05/08/2021 | ASHOK KUMAR GHOSH | 41.9 | 80.84 | 192.95 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Siptai Piped Water Supply Scheme | SM/07551 | Retrofitting | Extension of pipeline including FHTC for Siptai Piped Water Supply Scheme at Ilampur (30 Nos) habitation for Sajal Gram (As per FIELD VERIFICATION REPORT DULY SIGNED BY PRADHAN FOR HAR GHAR JAL CERTIFICATION) within Jamalpur Block under Burdwan Division, PHE Dte. Gr.S. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000355/2022-2023 | 1394/BSD | 08/08/2022 | 13/08/2022 | ROY CONSTRUCTION | 0.96 | 0 | 0 | 1
3 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Siptai Piped Water Supply Scheme | SM/07551 | Retrofitting | Extension of pipeline including providing FHTC for SIPTAI Piped Water Supply Scheme at Pirijpur 40 No¿s Habitation for Sajal Gram (As per FIELD VERIFICATION REPORT FOR HAR GHAR JAL CERTIFICATION within Jamalpur under Burdwan Division, PHE Dte. Gr.Q. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000353/2022-2023 | 1392/BSD | 08/08/2022 | 13/08/2022 | ROY CONSTRUCTION | 0.95 | 0.95 | 100 | 1
4 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Siptai Piped Water Supply Scheme | SM/07551 | Retrofitting | Extension of pipeline including providing FHTC for SIPTAI Piped Water Supply Scheme at Siptai (42 Nos) Habitation for Sajal Gram (As per FIELD VERIFICATION REPORT DULY SIGNED BY PRADHAN FOR HAR GHAR JAL CERTIFICATION) within Jamalpur Block under Burdwan Division, PHE Dte. Gr.R | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000354/2022-2023 | 1393/BSD | 08/08/2022 | 13/08/2022 | ROY CONSTRUCTION | 0.97 | 0 | 0 | 100
5 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Siptai Piped Water Supply Scheme | SM/07551 | Retrofitting | Extension of pipeline including FHTC for SIPTAI Piped Water Supply Scheme at Pirijpur (40 Nos) Habitation for Sajal Gram (As per field verification report duly signed by Pradhan for Har Ghar Jal Certification) within Jamalpur Block under Burdwan Division, PHE Dte. |  |  | ORD/000849/2022-2023 | 1392-A/BSD | 08/08/2022 | 13/08/2022 | ROY CONSTRUCTION | 0.95 | 0 | 0 | 0
6 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Siptai Piped Water Supply Scheme | SM/07551 | Retrofitting | Extension of pipeline including FHTC for SIPTAI Piped Water Supply Scheme at Siptai (42 Nos) Habitation for Sajal Gram (As per field verification report duly signed by Pradhan for Har Ghar Jal Certification) within Jamalpur Block under Burdwan Division, PHE Dte. |  |  | ORD/000850/2022-2023 | 1393-A/BSD | 08/08/2022 | 13/08/2022 | ROY CONSTRUCTION | 0.97 | 0.97 | 100 | 100
7 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Siptai Piped Water Supply Scheme | SM/07551 | Retrofitting | Extension of pipeline including providing FHTC for Siptai Piped Water Supply Scheme at Ilampur[30 No's],Habitation for Sajal Gram (As per Sajal Gram(As per Field Verification Report duly signed by Pradhan for Har Ghar Jal Certification)within Jamalpur Block under Burdwan Division, PHE Dte. |  |  | ORD/000851/2022-2023 | 1394-A/BSD | 08/08/2022 | 13/08/2022 | ROY CONSTRUCTION | 0.96 | 0.96 | 100 | 100
8 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Siptai Piped Water Supply Scheme | SM/07551 | Retrofitting | Providing FHTC for 100% coverage at Srimanpur (Village) (Habitation) for SIPTAI Piped W/S Scheme, Jamalpur Dev. Block under Burdwan Division, PHE Dte. | AE(HQs) | Junior Engineer, Burdwan Division | ORD/000921/2023-2024 | 5487/BWD | 13/12/2023 | 12/01/2024 | GOUTAM KUMAR MITRA | 4.34 | 4.3 | 99.02 | 100
9 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Siptai Piped Water Supply Scheme | SM/07551 | Retrofitting | Additional work for laying of UPVC pipeline for providing FHTC at Srimanpur (Village) (Habitation) under SIPTAI Piped W/S. Scheme, Jamalpur Dev. Block under Burdwan Division, PHE Dte. | AE(HQs) | Junior Engineer, Burdwan Division | ORD/001030/2023-2024 | 99/AE/HQ | 15/02/2024 | 16/03/2024 | GOUTAM KUMAR MITRA | 0.72 | 0.72 | 100 | 100
Total | [13 empty] | 52.71 | 88.73 | 168.34