## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Taraposh Piped Water Supply Scheme | SM/07553 | Retrofitting | Hire & fuel charges of vehicle (Car No.-WB-41H-9788) for the office of the Assistant Engineer, Headquarters, Burdwan Division, PHE Dte. for the month of September & October'2022. |  |  | VCH/000839/2022-2023 | 766/VEH/22-23 | 22/11/2022 | 22/11/2022 | SK. ASRAFUDDIN | 0.7 | 0 | 0 | 0
2 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Taraposh Piped Water Supply Scheme | SM/07553 | Retrofitting | Hire & fuel charges of vehicle (Car No.-WB-41H-9788) for the office of the Assistant Head Quarters, Burdwan Division, PHE Dte. for the month of June & July'22. |  |  | VCH/000493/2022-2023 | 460/VEH/22-23 | 29/08/2022 | 29/08/2022 | SK. ASRAFUDDIN | 0.76 | 0 | 0 | 0
3 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Taraposh Piped Water Supply Scheme | SM/07553 | Retrofitting | Providing functional household tap connection (FHTC) from existing distribution system within the command area of Taraposh piped water supply scheme at Alladipur, Chintamonipur, Jarul, Kamdebpur, Punia, Sunia & Taraposh, Khandaghosh Block under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000584/2020-2021 | 4766/BWD | 01/12/2020 | 01/03/2021 | SINGHA ROY AND CO. | 70.55 | 27.59 | 39.11 | 1
4 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Taraposh Piped Water Supply Scheme | SM/07553 | Retrofitting | Providing leftout water tap connection in different villages for 100% coverage to make it Sajal Gram from existing distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Khandaghosh Block under Burdwan Division, PHE. Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000405/2021-2022 | 283/BWD | 17/01/2022 | 16/02/2022 | J. K. CORPORATION | 11.88 | 11.87 | 99.94 | 1
5 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Taraposh Piped Water Supply Scheme | SM/07553 | Retrofitting | Repairing of Pipeline of DVC 11 No. Canal towards Amila Bazar and DVC 11B No. Conal Towards Sehara Bazar at TARAPOSH Pipes Water Supply Scheme at Khandaghosh Block under Burdwan Division,PHE Dte. Group : F | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000093/2022-2023 | 833/BSD | 23/05/2022 | 22/06/2022 | HAFIJUR RAHAMAN MIDYA | 1.56 | 1.57 | 100.31 | 1
6 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Taraposh Piped Water Supply Scheme | SM/07553 | Retrofitting | Construction of 250 cum capacity 20 Mtr staging height RCC Over Head Reservoir including pipe connection and cost of pipes specials including soil investigation for TARAPOSH & its adjoining mouzas water supply scheme under Burdwan Sub-Division, under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000973/2020-2021 | 4594/BWD | 24/11/2020 | 23/05/2021 | MITRA CONSTRUCTION | 57 | 56 | 98.25 | 100
7 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Taraposh Piped Water Supply Scheme | SM/07553 | Retrofitting | Extension Pipeline with Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of TARAPOSE Piped Water Supply Scheme within KHANDAGHOSH Block of Burdwan Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000759/2022-2023 | 1289/BWD | 20/03/2023 | 19/04/2023 | GENUINE ENGINEERING CO-OP. SOCIETY LTD. | 21.86 | 0 | 0 | 100
Total | [13 empty] | 164.32 | 97.03 | 59.05