## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Bamangaria Piped Water Supply Scheme | SM/07556 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Banki village and Banki Habitation of Bamangaria piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. [Phase-I] | Assistant Engineer |  | ORD/000606/2020-2021 | 4123/BWD | 16/10/2020 | 15/11/2020 | GOUTAM KUMAR MITRA | 4.86 | 4.52 | 92.86 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Bamangaria Piped Water Supply Scheme | SM/07556 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Banki village and Banki habitation of Bamungoria Piped Water Supply Scheme within Kalna Sub-Divn. under Burdwan Division, PHE. Dte. [Phase - I] [GROUP : ¿10B¿] | Assistant Engineer |  | ORD/000137/2021-2022 | 4543/BWD | 06/09/2021 | 06/10/2021 | GOUTAM KUMAR MITRA | 0.97 | 0 | 0 | 1
3 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Bamangaria Piped Water Supply Scheme | SM/07556 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Bamangaria village and Bamangaria habitation of Bamangaria piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-536/BWD/2020-21) | Assistant Engineer |  | ORD/000169/2020-2021 | 4122/BWD | 16/10/2020 | 15/11/2020 | PAL CONSTRUCTION | 4.86 | 4.86 | 100 | 1
4 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Bamangaria Piped Water Supply Scheme | SM/07556 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Bamangaria village and Bamungoria habitation of Bamungoria Piped Water Supply Scheme within Kalna Sub-Divn. under Burdwan Division, PHE. Dte. [Phase - I] [GROUP : ¿10A¿] | Assistant Engineer |  | ORD/000920/2020-2021 | 151/BWD | 08/01/2021 | 07/02/2021 | PAL CONSTRUCTION | 1.73 | 0 | 0 | 1
5 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Bamangaria Piped Water Supply Scheme | SM/07556 | Retrofitting | Extension of different dia UPVC pipeline to provide house connections to the different leftout areas in the command area of Bamungaria W/S Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. (Sl No-B) | Assistant Engineer |  | ORD/000392/2021-2022 | 07/KSD Dt-04.01.2022 | 04/01/2022 | 04/02/2022 | PAL CONSTRUCTION | 2.52 | 0 | 0 | 1
6 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Bamangaria Piped Water Supply Scheme | SM/07556 | Retrofitting | Hire & fuel charges of vehicle (Car No.-WB-04G-7127) for the office of the Assistant Engineer, Kalna Sub-Division, PHE Dte. for the month of March to September'2022. |  |  | BILL/00145/2022-2023 | 866/VEH | 09/12/2022 | 09/12/2022 | PARTHA PRATIM ACHARYA | 2.79 | 0 | 0 | 0
7 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Bamangaria Piped Water Supply Scheme | SM/07556 | Retrofitting | Hire & fuel charges of vehicle (Car No.-04G-7127) for the office of the Assistant Engineer, Kalna Sub-Division, PHE Dte. for the month of October & November'2022. |  |  | BILL/00288/2022-2023 | 956/JJM/22-23 | 13/01/2023 | 13/01/2023 | PARTHA PRATIM ACHARYA | 0.77 | 0 | 0 | 0
8 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Bamangaria Piped Water Supply Scheme | SM/07556 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Bhaturia village (Bhaturia habitation) of Bamungoria Piped Water Supply Scheme within Kalna Sub-Divn. under Burdwan Division, PHE. Dte. (Part-A). [SL. No. : 22] | AE(HQs) | J.E. 2 BURDWAN | ORD/000467/2020-2021 | 1461/BWD | 18/02/2021 | 05/03/2021 | ABDUL HAI | 4.86 | 4.86 | 100 | 0
9 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Bamangaria Piped Water Supply Scheme | SM/07556 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Bhaturia village (Bhaturia habitation) of Bamungoria Piped Water Supply Scheme within Kalna Sub-Divn. under Burdwan Division, PHE. Dte. (Part-B). [SL. No. : 23] | AE(HQs) | J.E. 2 BURDWAN | ORD/000530/2020-2021 | 1460/BWD | 18/02/2021 | 05/03/2021 | SANTANU BHATTACHARYAY | 4.86 | 4.86 | 100 | 0
10 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Bamangaria Piped Water Supply Scheme | SM/07556 | Retrofitting | Digital structurization of pipeline alignment and asset evaluation including holistic design, preparation of design drawings of overall LDS & preparation of estimate for 14 Nos. Piped W/S. Schemes under Purbasthali I Block under Kalna Sub-Division under Burdwan Division, PHE. Dte. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000337/2024-2025 | 3017/BWD | 05/08/2024 | 19/10/2024 | HORIZEN | 38 | 0 | 0 | 100
11 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Bamangaria Piped Water Supply Scheme | SM/07556 | Retrofitting | Different Types of work involved in connection with Augmentation of SONARUDRA (SM/16349) & KACHUA (SM/13497) Piped Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000192/2024-2025 | 2430/BWD | 27/06/2024 | 20/10/2025 | R.G. INFRASTRUCTURE | 240.7 | 0 | 0 | 2
Total | [13 empty] | 306.93 | 19.1 | 6.22