## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Shushuni Piped Water Supply Scheme | SM/07557 | Retrofitting | Continuation work order for water tap connection in each household from existing distribution system within scheme jurisdiction in Kuli habitation of Shushunia piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. [Gr.-H] | Assistant Engineer |  | ORD/000910/2020-2021 | 4787./BWD | 02/12/2020 | 01/01/2021 | SUSUNIA GP CO. OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 2.92 | 0 | 0 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Shushuni Piped Water Supply Scheme | SM/07557 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Shushuni Piped Water Supply Scheme at Shushuni (Part) (Ghoshpara & Sethpur habitation) Village (Mouza), Monteswar Block under Burdwan Division, PHE Dte. [Agreement No.661/BWD OF 2020-2021] | AE(HQs) | J.E. 2 BURDWAN | ORD/000300/2020-2021 | 1152/BWD | 09/02/2021 | 11/03/2021 | SUSUNIA GP CO. OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 19.79 | 0 | 0 | 1
3 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Shushuni Piped Water Supply Scheme | SM/07557 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Shushuni Piped Water Supply Scheme at Shushuni (Part) (Tentulia Bogpara habitation), Budhpur & Kalswar Village (Mouza), Monteswar Block under Burdwan Division, PHE Dte.[Agreement No. 660/BWD OF 2020-2021] | Assistant Engineer |  | ORD/000333/2020-2021 | 1151/BWD | 09/02/2021 | 11/03/2021 | SUSUNIA GP CO. OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 22.8 | 0 | 0 | 1
4 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Shushuni Piped Water Supply Scheme | SM/07557 | Retrofitting | Work order for Restoration of road and base concreting in FHTC for retrofitting of Shushunia water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/000131/2023-2024 | 427/KSD | 11/05/2023 | 10/06/2023 | SUSUNIA GP CO. OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 0.6 | 0 | 0 | 100
5 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Shushuni Piped Water Supply Scheme | SM/07557 | Retrofitting | Laying of UPVC pipeline for smooth running of FHTC work of SHUSHUNIA Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/000115/2023-2024 | 2342/BWD | 22/05/2023 | 21/06/2023 | SUSUNIA GP CO. OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 22.26 | 0 | 0 | 100
6 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Shushuni Piped Water Supply Scheme | SM/07557 | Retrofitting | Designing, Making and Erection of Sign Board for SAJAL GRAM in Kuli Village, Monteswar Block within Susunia PWSS under Burdwan Division, PHE Dte. (5 Nos Board) | AE(HQs) | J.E. 1 BURDWAN | ORD/000734/2023-2024 | 827/AE/HQ | 30/10/2023 | 29/11/2023 | ISHAN CONSTRUCTION | 0.76 | 0 | 0 | 100
7 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Shushuni Piped Water Supply Scheme | SM/07557 | Retrofitting | Designing, Making and Erection of Sign Board for SAJAL GRAM in Budhpur Village, Monteswar Block within Susunia PWSS under Burdwan Division, PHE Dte. (5 Nos Board) | AE(HQs) | J.E. 1 BURDWAN | ORD/000735/2023-2024 | 828/AE/HQ | 30/10/2023 | 29/11/2023 | ISHAN CONSTRUCTION | 0.76 | 0 | 0 | 100
Total | [13 empty] | 69.88 | 0 | 0