## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting withinthe command area of Gopikantapur Piped Water Supply Scheme at Jamalpur Block | SM/07775 | Retrofitting | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. |  |  | VCH/001237/2021-2022 | 1132/DW | 26/02/2022 |  | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 221 | 0 | 0 | 0
2 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting withinthe command area of Gopikantapur Piped Water Supply Scheme at Jamalpur Block | SM/07775 | Retrofitting | Formal Work Order for Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Gopikantapur Piped Water Supply Scheme at Bishnubati, Chakdighi & Dhapdhara Village (Mouza), Jamalpur Block under Burdwan Division, PHE Dte. [Agreement No. 96/SE/CC/PHE/Dte of 2020-2021.] | AE(HQs),Assistant Engineer |  | ORD/000439/2020-2021 | 716/BWD | 28/01/2021 | 14/03/2021 | BHARAT CONSTRUCTION | 47 | 16.87 | 35.89 | 1
3 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting withinthe command area of Gopikantapur Piped Water Supply Scheme at Jamalpur Block | SM/07775 | Retrofitting | Hire & fuel charges of vehicle (Car No.-WB-41H-3668) for the office of the Assistant Engineer, RWS Burdwan Sub-Division, PHE Dte. for the month of May & June'22. |  |  | VCH/000494/2022-2023 | 462/VEH/22-23 | 29/08/2022 |  | MD HASIN | 0.51 | 0 | 0 | 0
4 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting withinthe command area of Gopikantapur Piped Water Supply Scheme at Jamalpur Block | SM/07775 | Retrofitting | Formal Work Order for Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Gopikantapur Piped Water Supply Scheme at Kubajpur, Pranballabhpur (2 Nos Habitation) & Ramchandrapur Village (Mouza), Jamalpur Block under Burdwan Division, PHE Dte. [Agreement No. 98/SE/CC/PHE/Dte of 2020-2021.] | AE(HQs),Assistant Engineer |  | ORD/000417/2020-2021 | 914/BWD | 02/02/2021 | 03/04/2021 | S.S. CONSTRUCTION | 62.95 | 29.05 | 46.15 | 1
5 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting withinthe command area of Gopikantapur Piped Water Supply Scheme at Jamalpur Block | SM/07775 | Retrofitting | Construction of 400 cum capacity 20 Mtr. staging height RCC Over Head Reservoir including pipe connection and cost of pipes, specials for Gopikantapur & it's adjoining mouzas W/S. scheme under Burdwan Division, P.H.E. Dte.Ref. Drawing No.PC-I/OHR/11/2012 (Sheet No.1&2)(R-I) Dated 20.06.2012. [Revision - 1 dt. 20.12.2012] | AE(HQs),Assistant Engineer |  | ORD/000438/2021-2022 | 696/BWD | 02/02/2022 | 01/08/2022 | M/S JAN MAHAMMAD | 76.26 | 0 | 0 | 0
6 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting withinthe command area of Gopikantapur Piped Water Supply Scheme at Jamalpur Block | SM/07775 | Retrofitting | Laying of uPVC pipeline due to obstruction arise for PWD roads within Gopikantapur W/S Scheme under Burdwan Division, PHE Dte. [Group: ¿F¿] | AE(HQs),Assistant Engineer |  | ORD/000222/2021-2022 | 1817/AE/HQ | 21/09/2021 | 21/10/2021 | M/S S. CHOUDHURY | 3.55 | 0 | 0 | 1
7 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting withinthe command area of Gopikantapur Piped Water Supply Scheme at Jamalpur Block | SM/07775 | Retrofitting | Extension of pipeline (Branch & Sub Branch) for Functional House Hold Tap Connection from existing distribution system within the command area of GOPIKANTAPUR Piped Water Supply Scheme, at Bhairabpur village, Jamalpur Block under Burdwan Division P.H.E Dte._Gr-H | AE(HQs),Assistant Engineer |  | ORD/000633/2021-2022 | 130/AE/HQ | 04/03/2022 | 19/03/2022 | D.M. ENTERPRISE | 2.37 | 0 | 0 | 1
8 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting withinthe command area of Gopikantapur Piped Water Supply Scheme at Jamalpur Block | SM/07775 | Retrofitting | Laying of HDPE and UPVC pipe for providing FHTC at Pranballabhpur Village within GOPIKANTAPUR Piped Water Supply Scheme, Jamalpur Block under Burdwan Division P.H.E Dte._Gr-G | AE(HQs),Assistant Engineer |  | ORD/000662/2021-2022 | 148/AE/HQ | 16/03/2022 | 05/04/2022 | OM ENTERPRISE | 4.8 | 0 | 0 | 1
9 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting withinthe command area of Gopikantapur Piped Water Supply Scheme at Jamalpur Block | SM/07775 | Retrofitting | Continuation work order for water tap connection in each house hold from existing distribution system within scheme jurisdiction in Bhairabpur Habitation of Gopikantapur piped water supply scheme within Headquarters under Burdwan Division, PHE Dte. | AE(HQs),Assistant Engineer |  | ORD/000562/2021-2022 | 4818/BWD | 22/09/2021 | 22/10/2021 | D.M. ENTERPRISE | 3.76 | 3.76 | 100 | 1
10 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting withinthe command area of Gopikantapur Piped Water Supply Scheme at Jamalpur Block | SM/07775 | Retrofitting | Laying of UPVC pipe for providing FHTC in different habitaion of Ramchandrapur, Pranballabpur Mouza within Gopikantapur piped water supply scheme within Jamalpur Block under Burdwan Division, PHE Dte. [Gr.-B] | AE(HQs),Assistant Engineer |  | ORD/000768/2021-2022 | 1856/AE/HQ | 05/10/2021 | 04/11/2021 | M/S S. CHOUDHURY | 4.82 | 4.82 | 100 | 1
11 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting withinthe command area of Gopikantapur Piped Water Supply Scheme at Jamalpur Block | SM/07775 | Retrofitting | Laying of uPVC pipe for providing FHTC at Gopikantapur, Ramchandrapur and Bishnubati Village within Gopikantapur Piped Water Supply Scheme, Jamalpur Block under Burdwan Division P.H.E Dte._Gr-G | AE(HQs),Assistant Engineer |  | ORD/000632/2021-2022 | 129/AE/HQ | 04/03/2022 | 19/03/2022 | S.S. CONSTRUCTION | 3.71 | 0 | 0 | 1
12 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting withinthe command area of Gopikantapur Piped Water Supply Scheme at Jamalpur Block | SM/07775 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000117/2021-2022 | 1102/BWD | 26/02/2022 |  | Resource Division | 8.61 | 0 | 0 | 0
13 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting withinthe command area of Gopikantapur Piped Water Supply Scheme at Jamalpur Block | SM/07775 | Retrofitting | Sinking of 300 mm X 200 mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CM) and UPVC Medium Well Screen (RMS) with construction of Pump House & Boundary wall of GOPIKANTAPUR Piped Water Supply Scheme, Block- Jamalpur, District:- Purba-Bardhaman under Burdwan Division PHE Dte. [FOR 3rd. TUBE WELL SITE]. | AE(HQs) |  | ORD/001043/2023-2024 | 786/BWD | 27/02/2024 | 27/04/2024 | BIBHUTI SHAW | 23.9 | 0 | 0 | 0
Total | [13 empty] | 463.23 | 54.5 | 11.76