## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Gramdihi Piped Water Supply Scheme at Bhatar Block | SM/07777 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Gramdihi Piped Water Supply Scheme at Mandarbati, Gholada & Bigra Village (Mouza), Bhatar Block under Burdwan Division, PHE Dte. (Agreement no. 792/BWD of 2020-2021) | Assistant Engineer |  | ORD/000434/2020-2021 | 1794/BWD | 26/02/2021 | 12/04/2021 | M/S GUPTA ENTERPRISE | 41.94 | 33.9 | 80.83 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Gramdihi Piped Water Supply Scheme at Bhatar Block | SM/07777 | Retrofitting | Extension of UPVC pipe line of LDS at Gholada village for providing FHTC of Gramdihi and its adjoining mouzas W/S Scheme within Bhatar Block under Burdwan Division, P.H.E. Dte. [Gr.-C] | Assistant Engineer |  | ORD/000264/2021-2022 | 691/DSD | 08/12/2021 | 07/01/2022 | M/S GUPTA ENTERPRISE | 4.84 | 0 | 0 | 1
3 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Gramdihi Piped Water Supply Scheme at Bhatar Block | SM/07777 | Retrofitting | Extension of pipeline in Connection to FHTC work at Gramdihi village of Gramdihi and its adjoining Mouza's Piped W/S Scheme at Bhatar Block within Durgapur (Bardhaman North)Sub-Division under Burdwan Division, P.H.E. Dte. (Gr.-A) | Assistant Engineer |  | ORD/000105/2021-2022 | 416/DSD | 02/07/2021 | 01/08/2021 | DEY NIRMAN | 4.71 | 0.23 | 4.8 | 1
4 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Gramdihi Piped Water Supply Scheme at Bhatar Block | SM/07777 | Retrofitting | Extension of UPVC pipe line of LDS at Bighra village for providing FHTC of Gramdihi and its adjoining mouzas W/S Scheme within Bhatar Block under Burdwan Division, P.H.E. Dte. [Gr.-D] | Assistant Engineer |  | ORD/000265/2021-2022 | 692/DSD | 08/12/2021 | 07/01/2022 | SHUBHRA KANTI GHOSH | 4.3 | 4.1 | 95.38 | 1
5 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Gramdihi Piped Water Supply Scheme at Bhatar Block | SM/07777 | Retrofitting | Extension of UPVC pipe line of LDS at Manderbati village and Majhipara for providing FHTC of Gramdihi and its adjoining mouzas W/S Scheme within Bhatar Block under Burdwan Division, P.H.E. Dte. [Gr.-B] | Assistant Engineer |  | ORD/000263/2021-2022 | 690/DSD | 08/12/2021 | 07/01/2022 | BIPLAB SAMANTA | 2.26 | 2.22 | 98.05 | 1
6 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Gramdihi Piped Water Supply Scheme at Bhatar Block | SM/07777 | Retrofitting | Providing leftout water tap connection in different villages for 100% coverage to make it Sajal Gram from existing distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Bhatar Block under Burdwan Division, PHE. Dte. | Assistant Engineer ,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000389/2021-2022 | 268/BWD | 14/01/2022 | 13/02/2022 | BHARAT CONSTRUCTION | 14.17 | 7.45 | 52.55 | 1
7 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Gramdihi Piped Water Supply Scheme at Bhatar Block | SM/07777 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Gramdihi Piped Water Supply Scheme at Gramdihi & Sanchalida Village (Mouza), Bhatar Block under Burdwan Division, PHE Dte. [Agreement No. 631/BWD OF 2020-2021.] | AE(HQs) | J.E. 2 BURDWAN | ORD/000436/2020-2021 | 956/BWD | 03/02/2021 | 20/03/2021 | DEY NIRMAN | 35.08 | 41.01 | 116.89 | 0
8 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Gramdihi Piped Water Supply Scheme at Bhatar Block | SM/07777 | Retrofitting | Restoration of work due to laying of Water Supply Pipelines along Bonpass Village(Kamarpara) to Banpass Railway Station Road by Public Health Engineering Directorate under " Jal Jeevan Mission from 0.00 km to 1.54 km in the district of Purba Bardhaman under Burdwan Division,P.W.D." |  |  | BILL/00709/2024-2025 | 866/JJM | 23/09/2024 | 23/09/2024 | EXECUTIVE ENGINEER PWD BURDWAN DIVISION | 2.94 | 0 | 0 | 0
9 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Gramdihi Piped Water Supply Scheme at Bhatar Block | SM/07777 | Retrofitting | Payment of vehicle bill (Car No.-WB-41H-9788) for the month of September'23. |  |  | BILL/01343/2023-2024 | 899/JJM | 22/11/2023 | 22/11/2023 | SK. ASRAFUDDIN | 0.4 | 0 | 0 | 0
10 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Gramdihi Piped Water Supply Scheme at Bhatar Block | SM/07777 | Retrofitting | Restoration of damaged flanks due to laying of HDPE pipe line along the flank of Burdwan Katwa Road from 14.70 kmp to 16.20 kmp in the district of Purba Bardhaman under Bardhaman Division,P.W.D. |  |  | BILL/00711/2024-2025 | 867/JJM | 23/09/2024 | 23/09/2024 | EXECUTIVE ENGINEER PWD BURDWAN DIVISION | 7.9 | 0 | 0 | 0
11 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Gramdihi Piped Water Supply Scheme at Bhatar Block | SM/07777 | Retrofitting | Laying Piper Line and FHTC for Gramdihi Jr. Basic School under Gramdihi Piped water supply Scheme , P.H.E Dte. Block:-Bhatar Dist: Purba Bardhaman |  |  | ORD/000524/2025-2026 | 1020/DSD | 10/07/2025 | 25/07/2025 | INDIAN ENGINEERS CO.-OPERATIVE SOCIETY LTD. | 0.15 | 0 | 0 | 0
Total | [13 empty] | 118.69 | 88.9 | 74.9