## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Ruppur Piped Water Supply Scheme at Jamalpur Block | SM/07778 | Retrofitting | Extensionof pipe linefor providing functional house hold tap connection at Ruppur village(Habitation)of RUPPUR Piped Water Supply Scheme Piped Water Supply Scheme within Burdwan Sub-Division under Burdwan Division,PHE Dte".Gr.B. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000474/2021-2022 | 275/BSD | 15/02/2022 | 17/03/2022 | SAMANTA CONSTRUCTION | 4.82 | 0 | 0 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Ruppur Piped Water Supply Scheme at Jamalpur Block | SM/07778 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Ruppur Piped Water Supply Scheme at Ruppur Village (6 Nos. habitations), Biswambharpur Village & Dhuluk Village (6 Nos. habitations) Jamalpur Block under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000041/2021-2022 | 3446/BWD | 29/06/2021 | 28/08/2021 | NATIONAL CONSTRUCTION | 87.06 | 0 | 0 | 1
Total | [13 empty] | 91.88 | 0 | 0