## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Lohai Piped Water Supply Scheme at Raina-II Block | SM/07779 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Natungram village and Natungram, Daspara, Palpara habitation of Lohana piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-475/BWD/2020-21) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000370/2020-2021 | 4781/BWD | 02/12/2020 | 01/01/2021 | PARTHA PRATIM ACHARYA | 2.95 | 0 | 0 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Lohai Piped Water Supply Scheme at Raina-II Block | SM/07779 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of LOHAI Piped Water Supply Scheme at Madhabdihi, Bhanjanpur, Akhina & Dakhin Gopalpur Village (Mouza), Raina-II Block under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000157/2021-2022 | 4635/BWD | 09/09/2021 | 08/11/2021 | CREATION CONSTRUCTION | 61.85 | 0 | 0 | 1
3 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Lohai Piped Water Supply Scheme at Raina-II Block | SM/07779 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Lohai Piped Water Supply Scheme at Arui, Dighra, Jotragob, Konerpur & Lohai Village (Mouza), Raina-II Block under Burdwan Division, PHE Dte. [Agreement No. 54/2020-2021 OF SE/CC/PHE. DTE.] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000419/2020-2021 | 4888/BWD | 07/12/2020 | 07/03/2021 | M/S S. CHOUDHURY | 75.66 | 0 | 0 | 1
4 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Lohai Piped Water Supply Scheme at Raina-II Block | SM/07779 | Retrofitting | Plinth protection and uplift of inner side of base floor of OHR and construction of sluice valve chamber at LOHAI PWSS at Raina-II Block under Burdwan Division PHE Dte. [Group : B] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000359/2022-2023 | 446/AE/HQ | 16/08/2022 | 15/09/2022 | INDIAN ENGINEERS CO.-OPERATIVE SOCIETY LTD. | 1.91 | 0 | 0 | 1
5 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Lohai Piped Water Supply Scheme at Raina-II Block | SM/07779 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Barakalmi & Sirajpur village of Lohana Piped Water Supply Scheme within Kalna Sub-Divn. under Burdwan Division, PHE. Dte. [SL. No. : 22] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000195/2021-2022 | 6188/BWD | 28/10/2021 | 12/11/2021 | PARTHA PRATIM ACHARYA | 4.86 | 0 | 0 | 1
6 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Lohai Piped Water Supply Scheme at Raina-II Block | SM/07779 | Retrofitting | Laying of uPVC pipe for providing FHTC in different habitation of Lohai, Akhina and Dakshin Gopalpur Mouza within Lohai Piped Water Supply Scheme, Raina-II Block under Burdwan Division P.H.E DTE. [Group: ¿E¿] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000221/2021-2022 | 1816/AE/HQ | 21/09/2021 | 21/10/2021 | M/S S. CHOUDHURY | 4.76 | 0 | 0 | 1
7 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Lohai Piped Water Supply Scheme at Raina-II Block | SM/07779 | Retrofitting | Laying of uPVC pipe for providing FHTC at Madhabdihi, Lohai and Akhina Village within LOHAI Piped Water Supply Scheme, Raina-II Block under Burdwan Division P.H.E Dte._Gr-E | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000668/2021-2022 | 137/AE/HQ | 15/03/2022 | 04/04/2022 | M/S S. CHOUDHURY | 4.8 | 0 | 0 | 1
8 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Lohai Piped Water Supply Scheme at Raina-II Block | SM/07779 | Retrofitting | Laying of uPVC pipe for providing FHTC at Bhanjapur, Alampur and Akhina Village within Lohai Piped Water Supply Scheme, Raina-II Block under Burdwan Division P.H.E Dte.Gr. E | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000630/2021-2022 | 127/AE/HQ | 04/03/2022 | 19/03/2022 | M/S S. CHOUDHURY | 4.79 | 0 | 0 | 1
9 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Lohai Piped Water Supply Scheme at Raina-II Block | SM/07779 | Retrofitting | Laying of dedicated HDPE pipeline for supply of sufficient water at Bhanjapur village of Lohai piped water supply scheme, Raina-II Block under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000575/2021-2022 | 6741/BWD | 03/12/2021 | 02/01/2022 | THREE MAA ENTERPRISE | 20.11 | 0 | 0 | 1
10 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Lohai Piped Water Supply Scheme at Raina-II Block | SM/07779 | Retrofitting | Extension of pipeline for providing functional house hold tap connection at Bhanjapur Mouza within Lohai water supply scheme under Burdwan Division, PHE Dte.[Gr.-D] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000969/2020-2021 | 1259/AE/HQ | 15/02/2021 | 17/03/2021 | M/S S. CHOUDHURY | 4.14 | 0 | 0 | 1
11 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Lohai Piped Water Supply Scheme at Raina-II Block | SM/07779 | Retrofitting | MAINTENANCE OF ROAD (WHISH IS DAMAGED FOR LAYING PIPELINE BY PHE DEPTT) NAMELY NARUGRAM H.C TO BADSHI ROAD VIDE- PACKAGE NO- WB 22 12 UNDER PMGSY-III UNDER NARUGRAM GP. & RAINA-I BLOCK, IN PURBA BARDHAMAN DISTRICT |  |  | BILL/00740/2024-2025 | 894/JJM | 25/09/2024 | 25/09/2024 | EXECUTIVE ENGINEER (WBSRDA) PURBA BARDHAMAN DIVISION | 3.86 | 0 | 0 | 0
12 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Lohai Piped Water Supply Scheme at Raina-II Block | SM/07779 | Retrofitting | Balance Work for extension of pipe lines to provide FHTC with Sinking of Tubwell, Construction of pump house with Boundary wall & other related work for LOHAI PWSS under Burdwan Sub-Div., Block -Raina-II, under Burdwan Division PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/001014/2024-2025 | 61/BWD | 06/01/2025 | 06/05/2025 | B.S. ENTERPRISE | 62.48 | 0 | 0 | 0
Total | [13 empty] | 252.19 | 0 | 0