## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Eruar Piped Water Supply Scheme at Bhatar Block | SM/07780 | Retrofitting | Providing Functional Household Tap connection (FHTC) from existing distribution system within the command area of ERUAR piped water supply scheme at Muratipur (Part) (Muratipur Part Habitation) village (Mouza) within Bhatar Block under Burdwan Division, PHE Dte._2nd Call. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000765/2020-2021 | 1266/BWD | 11/02/2021 | 13/03/2021 | S.N. ENTERPRISE | 18.71 | 8.73 | 46.67 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Eruar Piped Water Supply Scheme at Bhatar Block | SM/07780 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of ERUAR Piped Water Supply Scheme at Eruar (Part-A) (Eruar (Part-A) Habitation) village (Mouza), Bhatar Block under Burdwan Division, PHE Dte. (Agreement no. 569/BWD of 2020-2021) | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000290/2020-2021 | 356/BWD | 15/01/2021 | 14/02/2021 | HAFIJUR RAHAMAN MIDYA | 19.95 | 12.15 | 60.88 | 1
3 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Eruar Piped Water Supply Scheme at Bhatar Block | SM/07780 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of ERUAR Piped Water Supply Scheme at Eruar (Part-D) (Eruar (Part-D) Habitation) village (Mouza), Bhatar Block under Burdwan Division, PHE Dte. ._2ND CALL (Agreement No.703/BWD of 2020-2021) | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000296/2020-2021 | 1569/15/BWD | 22/02/2021 | 24/03/2021 | DUBE ENTERPRISE | 18.61 | 23 | 123.6 | 1
4 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Eruar Piped Water Supply Scheme at Bhatar Block | SM/07780 | Retrofitting | Providing Functional Household Tap Connection (FHTC) & Restoration of pipeline at Sixteen Nos. samsad of Eruar Gram Panchayat from ERUAR Piped Water Supply Scheme at Bhatar Block under Burdwan Division, PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000296/2021-2022 | 7033/BWD | 17/12/2021 | 15/02/2022 | IJABUL SEKH | 92.08 | 76.47 | 83.04 | 1
5 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Eruar Piped Water Supply Scheme at Bhatar Block | SM/07780 | Retrofitting | Providing Left-Out FHTC to Eruar Habitation within ERUAR PWSS, within Durgapur (Burdwan North) Sub-Division, PHE Dte, under Burdwan Division, PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000382/2023-2024 | 557/DSD | 20/07/2023 | 19/08/2023 | SANDIPAN SENGUPTA | 4.44 | 0 | 0 | 0
6 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Eruar Piped Water Supply Scheme at Bhatar Block | SM/07780 | Retrofitting | Providing Functional Household tap connection (FHTC) from existing distribution system within the command area of ERUAR piped water supply scheme at Eruar (Part-B) (Eruar (Part-B) Habitation) village (Mouza), Bhatar Block under Burdwan Division, PHE Dte. [Tr No.-678/BWD/20-21] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000386/2020-2021 | 1264/BWD | 11/02/2021 | 13/03/2021 | S.T. ENTERPRISE | 22.24 | 0.82 | 3.69 | 100
7 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Eruar Piped Water Supply Scheme at Bhatar Block | SM/07780 | Retrofitting | Providing Functional House hold Tap connection (FHTC) from existing distribution system within the command area of ERUAR piped water supply scheme at Erusr (Part-C) (Eruar Part-C Habitation) village (Mouza) within Bhatar Block under Burdwan Division, PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000763/2020-2021 | 1265 /BWD | 11/02/2021 | 13/03/2021 | S.T. ENTERPRISE | 18.05 | 30.08 | 166.58 | 1
8 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Eruar Piped Water Supply Scheme at Bhatar Block | SM/07780 | Retrofitting | Extension of pipeline at "Sansad No. 10, 11 and 24" of Eruar and its adjoining mouza's Piped W/S Scheme at Bhatar Block within Durgapur (Bardhaman North) Sub Division under Burdwan Division, P.H.E. Dte. [Gr.-N] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000173/2021-2022 | 607/DSD | 07/10/2021 | 06/11/2021 | DUBE ENTERPRISE | 3.15 | 2.3 | 72.92 | 1
9 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Eruar Piped Water Supply Scheme at Bhatar Block | SM/07780 | Retrofitting | Hire & fuel charges of vehicle (Car No.-WB-41D-4561) for the office of the Assistant Engineer, Durgapur Sub-Division, PHE Dte. for the month of September & October'2022. |  |  | BILL/00142/2022-2023 | 823/VEH | 02/12/2022 | 02/12/2022 | SUJAUDDIN SEKH | 0.73 | 0 | 0 | 0
10 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Eruar Piped Water Supply Scheme at Bhatar Block | SM/07780 | Retrofitting | Hire & fuel charges of vehicle (Car No.-WB-37C-8293) for the office of the Assistant Engineer, Durgapur Sub-Division, PHE Dte. for the month of November'2022. |  |  | BILL/00286/2022-2023 | 954/JJM/22-23 | 13/01/2023 | 13/01/2023 | SUJAUDDIN SEKH | 0.38 | 0 | 0 | 0
11 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Eruar Piped Water Supply Scheme at Bhatar Block | SM/07780 | Retrofitting | Laying of pipeline for ERUAR Piped Water Supply Scheme in Bhatar Block under Burdwan Division, PHE. Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000443/2024-2025 | 3079/BWD | 09/08/2024 | 07/11/2024 | SOUMYAVASH DAS | 5.01 | 0 | 0 | 0
12 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Eruar Piped Water Supply Scheme at Bhatar Block | SM/07780 | Retrofitting | Construction of 1.5 mtrs. Height Boundary Wall along with 750 mm Height 3 layer barbed wire around Other than head work site(ERRUAR4 TH Pump House),Kaluttak under ERUAR PWSS, Bhatar Dev. Block, within Durgapur (Burdwan North) Sub-Division under Burdwan Division, P.H.E. DTE. |  | JUNIOR ENGINEER DURGAPUR SUB-DIVISION PHE DTE | ORD/000936/2024-2025 | 1082/DSD | 11/12/2024 | 09/02/2025 | SWAPAN KUMAR ROY | 3.72 | 0 | 0 | 0
13 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Eruar Piped Water Supply Scheme at Bhatar Block | SM/07780 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Muratipur village and Muratipur habitation of ERUAR Piped Water Supply Scheme within Durgapur (Burdwan North) Sub-Divn. under Burdwan Division, PHE. Dte. [Phase - I] [GROUP : ¿11B¿] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer | ORD/000457/2020-2021 | 4748/BWD | 01/12/2020 | 31/12/2020 | S. MONDAL | 4.86 | 9.73 | 200 | 0
14 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Eruar Piped Water Supply Scheme at Bhatar Block | SM/07780 | Retrofitting | Replacing of existing damaged pipe line at KALUTAK and repairing of 4th Pump house and changing of 2 nos. valve at ERUAR village of ERAUR PWSS of Bhatar Block within Durgapur (Burdwan North) Sub- Division under Burdwan Division PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer ,JUNIOR ENGINEER DURGAPUR SUB-DIVISION PHE DTE | ORD/000937/2023-2024 | 909/DSD | 15/12/2023 | 29/01/2024 | SWAPAN KUMAR ROY | 0.93 | 0.61 | 65.45 | 100
Total | [13 empty] | 212.88 | 163.88 | 76.98