## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Agradwip Piped Water Supply Scheme at Katwa-II Block | SM/07782 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of AGRADWIP Piped Water Supply Scheme at Agradwip, Babla danga, Gonsaidhowra, Saheb Nagar & Sarawaridhowra (Mouza), Katwa - II Block under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/000445/2021-2022 | 6253/BWD | 01/11/2021 | 31/12/2021 | SHUBHRA KANTI GHOSH | 53.67 | 19.01 | 35.41 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Agradwip Piped Water Supply Scheme at Katwa-II Block | SM/07782 | Retrofitting | Replacement and extension of pipe line from the existing Distribution System within scheme jurisdiction at Agradwip Ghosh para village under AGRADWIP PWSS under Katwa Sub-Division under Burdwan Division PHE Dte.(Sl No-6) | Assistant Engineer | JUNIOR ENGINEER KATWA SUB-DIVISION PHE DTE | ORD/000145/2021-2022 | 594/KTS | 06/09/2021 | 06/10/2021 | SHUBHRA KANTI GHOSH | 3.56 | 3.56 | 99.95 | 1
3 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Agradwip Piped Water Supply Scheme at Katwa-II Block | SM/07782 | Retrofitting | Replacement and extension of pipe line from the existing Distribution System within scheme jurisdiction at Agradwip Gopinath para and Majherpara village under AGRADWIP PWSS under Katwa Sub-Division under Burdwan Division PHE Dte.(Sl No-5) | Assistant Engineer | JUNIOR ENGINEER KATWA SUB-DIVISION PHE DTE | ORD/000144/2021-2022 | 593/KTS | 06/09/2021 | 06/10/2021 | CHANCHAL PAL | 3.47 | 3.47 | 99.81 | 1
4 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Agradwip Piped Water Supply Scheme at Katwa-II Block | SM/07782 | Retrofitting | Replacement and extension of pipe line from the existing Distribution System within scheme jurisdiction at Sahebnagar village under AGRADWIP PWSS under Katwa Sub-Division under Burdwan Division PHE Dte.(Sl No-4) | Assistant Engineer | JUNIOR ENGINEER KATWA SUB-DIVISION PHE DTE | ORD/000143/2021-2022 | 592/KTS | 06/09/2021 | 06/10/2021 | TAPAS KUMAR ROY | 4.84 | 4.82 | 99.79 | 1
5 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Agradwip Piped Water Supply Scheme at Katwa-II Block | SM/07782 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Agradwip Piped Water Supply Scheme at Agradwip (P) village & Kharpur (P) village, Katwa - II Block under Burdwan Division, PHE Dte._Part-B.[Agreement No. 685/BWD OF 2020-2021.] | Assistant Engineer | JUNIOR ENGINEER KATWA SUB-DIVISION PHE DTE | ORD/000305/2020-2021 | 1511/BWD | 19/02/2021 | 05/04/2021 | SHUBHRA KANTI GHOSH | 44.47 | 87.03 | 195.69 | 0
6 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Agradwip Piped Water Supply Scheme at Katwa-II Block | SM/07782 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Agradwip Piped Water Supply Scheme at Agradwip (P) village & Kharpur (P) village, Katwa - II Block under Burdwan Division, PHE Dte._Part-A. [Agreement No. 704/BWD OF 2020-2021] | Assistant Engineer | JUNIOR ENGINEER KATWA SUB-DIVISION PHE DTE | ORD/000323/2020-2021 | 1567/BWD | 22/02/2021 | 08/04/2021 | KHEPIMA ENGINEERS CO. OPERATIVE SOCIETY LTD. | 44.39 | 86.97 | 195.93 | 0
Total | [13 empty] | 154.4 | 204.85 | 132.68