## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Nabagram Piped Water Supply Scheme at Memari-I Block | SM/07798 | Retrofitting | Extension of pipeline for NABAGRAM Piped Water Supply Scheme at Konarpara [24 No's]Total 24 No's FHTC Work for Sajal Gram (As per Resulation taken in Special Gram Sava on 01-08-2022 within Memari-I Block including leftout husehold water tap connection (FHTC) under Burdwan Division, PHE Dte".Gr. B | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000334/2022-2023 | 1351/BSD | 02/08/2022 | 07/08/2022 | BHARAT CONSTRUCTION | 0.97 | 0 | 0 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Nabagram Piped Water Supply Scheme at Memari-I Block | SM/07798 | Retrofitting | Extension of pipeline for NABAGRAM Piped water Supply Scheme at Kalupukur[2 Nos]Kalanabagram[5 Nos]Dadpur[8 Nos],Paschim Memari[6 Nos]Pingur[3 Nos]Chuadanga:3 Nos Total 27 Nos FHTC Work for Sajal Gram(As per Resulation taken in Special Gram Sava on 01-08-2022 within Memari-I Block including leftout household water tap connection(FHTC)under Burdwan Division,PHE Dte.Gr.C. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000335/2022-2023 | 1352/BSD | 02/08/2022 | 07/08/2022 | BHARAT CONSTRUCTION | 0.97 | 0 | 0 | 1
3 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Nabagram Piped Water Supply Scheme at Memari-I Block | SM/07798 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Nabagram Piped Water Supply Scheme at Konar Village (2 Nos. habitations), Dadpur Village (4 Nos. habitations), Paschim Memari Village (2 Nos. habitations), Pingur Village & Nabagram Village (4 Nos. habitations), Memari - I Block under Burdwan Division, PHE Dte.[Agreement No. 681/BWD OF 2020-2021] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000311/2020-2021 | 1400/BWD | 15/02/2021 | 16/04/2021 | UNIQUE AGENCY | 68.1 | 63.58 | 93.37 | 1
4 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Nabagram Piped Water Supply Scheme at Memari-I Block | SM/07798 | Retrofitting | Providing leftout water tap connection in different villages for 100% coverage to make it Sajal Gram from existing distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Memari-I Block (Daluibazar-II, Gopegantar-I & II G.P.) under Burdwan Division, PHE. Dte. Dte._Part-A. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000371/2021-2022 | 209/BWD | 11/01/2022 | 10/02/2022 | M/S ANAND CONSTRUCTION | 21.11 | 0 | 0 | 1
5 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Nabagram Piped Water Supply Scheme at Memari-I Block | SM/07798 | Retrofitting | Sinking of 150mm. dia. 100 Mtr. Deep tube well & Laying Distribution pipeline including FHTC under Jal Swapna Scheme for SWASTI PALLY Mini Piped W/S. Scheme within NABAGRAM Piped W/S. Scheme under Burdwan Division, PHE. Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000714/2022-2023 | 890/BWD | 01/03/2023 | 15/04/2023 | BAMDEB CONSTRUCTION & CO | 30.68 | 0 | 0 | 100
6 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Nabagram Piped Water Supply Scheme at Memari-I Block | SM/07798 | Retrofitting | Extension of pipeline for NABAGRAM Piped Water Supply Scheme at Konarpara [24 No's]Total 24 No's FHTC Work for Sajal Gram (As per Resulation taken in Special Gram Sava on 01-08-2022 within Memari-I Block including leftout husehold water tap connection(FHTC) under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000645/2022-2023 | 1351-A/BSD | 02/08/2022 | 07/08/2022 | BHARAT CONSTRUCTION | 0.97 | 0 | 0 | 1
7 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Nabagram Piped Water Supply Scheme at Memari-I Block | SM/07798 | Retrofitting | Extension of pipeline for NABAGRAM Piped Water Supply Scheme at Kalupukur [2 No's], Kalanabagram[5 No's] Dadpur [8 No's], Paschim Memari [6 No's], Pingur [3 No's] Chuadanga [3 No's] Total 27 No's FHTC Work for Sajal Gram (As per Resulation taken in Special Gram Sava on 01-08-2022 within Memari-I Block including leftout household water tap connection (FHTC) under Burdwan Division, PHE Dte | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000646/2022-2023 | 1352-A/BSD | 02/08/2022 | 07/08/2022 | BHARAT CONSTRUCTION | 0.97 | 0 | 0 | 1
Total | [13 empty] | 123.76 | 63.58 | 51.37