## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Mahishgaria Piped Water Supply Scheme at Jamalpur Block | SM/07799 | Retrofitting | Extension of pipeline including leftout Functional Household Tap Connection (FHTC) for Mahishgoria Piped Water Supply Scheme at Mahishgoria, Bidyabatipur, Narayanpur village in Jamalpur Block under Burdwan Division, PHE Dte. GROUP : D | AE(HQs) |  | ORD/000230/2022-2023 | 427/AE/HQ | 03/08/2022 | 02/09/2022 | A R TRADERS | 4.91 | 0 | 0 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Mahishgaria Piped Water Supply Scheme at Jamalpur Block | SM/07799 | Retrofitting | Providing FHTC for 100% coverage at Baidyabatipur, Tilkuria, Mahishgaria, Narayanpur & Mathurapur village (Mouza) for MAHISHGARIA Piped W/S Scheme, Jamalpur Dev. Block under Burdwan Division, PHE Dte. |  |  | ORD/000101/2023-2024 | 2259/BWD | 18/05/2023 | 17/06/2023 | MUKHERJEE ENTERPRISE | 11.92 | 0 | 0 | 100
3 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Mahishgaria Piped Water Supply Scheme at Jamalpur Block | SM/07799 | Retrofitting | Land development and Construction of valve chamber by raising of height for control of water flow within command area of MAHISHGORIA H/W Pump house, MAHISHGORIA piped W/S Scheme at Jamalpur Development Block under Burdwan Division, PHE Dte. |  | JE/RWS/JAMALPUR | ORD/001034/2024-2025 | 86/AE/HQ | 08/01/2025 | 07/02/2025 | A.R. TRADERS | 0.93 | 0 | 0 | 0
4 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Mahishgaria Piped Water Supply Scheme at Jamalpur Block | SM/07799 | Retrofitting | Land development and Construction of valve chamber by raising of height at 2nd Pumphouse, MAHISHGORIA piped W/S Scheme at Jamalpur Development Block under Burdwan Division, PHE Dte. |  | JE/RWS/JAMALPUR | ORD/001033/2024-2025 | 85/AE/HQ | 08/01/2025 | 07/02/2025 | A.R. TRADERS | 0.72 | 0 | 0 | 0
Total | [13 empty] | 18.48 | 0 | 0