## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Gopalpur Piped Water Supply Scheme | SM/07800 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Paschim Gopalpur (Part) village (Jadabbati, Mirapur & Paschim Gopalpur (Part) habitation) & Radhanagar village (Radhanagar habitation) of Paschim Gopalpur Piped Water Supply Scheme within Katwa Sub-Divn. under Burdwan Division, PHE. Dte. [Sl. No. : ¿14¿] | Assistant Engineer |  | ORD/000711/2020-2021 | 64/BWD | 05/01/2021 | 20/01/2021 | ASMA ENTERPRISE | 4.86 | 4.86 | 100 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Gopalpur Piped Water Supply Scheme | SM/07800 | Retrofitting | Extension of pipe line from the existing Distribution System within scheme jurisdiction at Paschim Gopalpur & Mirapur village under Paschim Gopalpur PWSS under Katwa Sub-Division under Burdwan Division PHE Dte. (Sl No-1) | Assistant Engineer |  | ORD/000236/2021-2022 | 698/KTS | 27/10/2021 | 11/11/2021 | ASMA ENTERPRISE | 1.06 | 1.06 | 99.67 | 1
3 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Gopalpur Piped Water Supply Scheme | SM/07800 | Retrofitting | Providing Functional Household Tap Connection from existing distribution system at Sukhpukuria village under Gotistha Gram Panchayet under Mongalkote Block under Paschim Gopalpur PWSS under Katwa Sub-Division under Burdwan Division PHE Dte. (Sl No-2) | Assistant Engineer |  | ORD/000274/2021-2022 | 799/KTS | 10/12/2021 | 25/12/2021 | JAMALUDDIN SK | 3.69 | 3.67 | 99.45 | 1
4 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Gopalpur Piped Water Supply Scheme | SM/07800 | Retrofitting | Providing leftout water tap connection in different villages for 100% coverage to make it Sajal Gram from existing distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Mongalkote Block under Burdwan Division, PHE. Dte. | Assistant Engineer |  | ORD/000407/2021-2022 | 284/BWD | 17/01/2022 | 16/02/2022 | BABUL SK | 6.81 | 0.41 | 5.96 | 1
5 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Gopalpur Piped Water Supply Scheme | SM/07800 | Retrofitting | Providing Functional Household Tap Connection at Jadabbati,Sukhpukuria and Pilsona habitation of Paschim Gopalpur, Sukhpukuria and Pilsona village of Gotistha G.P. from existing distribution system within the command area of Paschim Gopalpur PWSS under Mongalkote Block under Katwa Sub-Division under Burdwan Division PHE Dte. | Assistant Engineer |  | ORD/000591/2021-2022 | 1439/BWD | 11/03/2022 | 10/04/2022 | PARTHA PRATIM ACHARYA | 10.47 | 10.41 | 99.46 | 1
6 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Gopalpur Piped Water Supply Scheme | SM/07800 | Retrofitting | Restoration of pipe line at Mera Para to Babunara, Gopalpur to Nayapaya and Pilsoya to Darshini due to construction of drain by PRI bodies along with crossing culvert under the command area Paschim Gopalpur PWSS (SM/07800) under Mongalkote Block under Katwa Sub-Division under Burdwan Division PHE Dte. (Sl No-02) | Assistant Engineer | JUNIOR ENGINEER KATWA SUB-DIVISION PHE DTE | ORD/001262/2024-2025 | 343/KTS | 05/03/2025 | 04/04/2025 | M/S S. CHOUDHURY | 3.63 | 0 | 0 | 100
7 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Gopalpur Piped Water Supply Scheme | SM/07800 | Retrofitting | Construction of approach Road and Land Development at Head Work Site of Paschim Gopalpur PWSS (SM/07800) under Katwa Sub-Division under Mongolkote Block within Burdwan Division PHE Dte. (Sl No -01) | Assistant Engineer | JUNIOR ENGINEER KATWA SUB-DIVISION PHE DTE | ORD/001260/2024-2025 | 342/KTS | 05/03/2025 | 04/04/2025 | OM CONSTRUCTION | 4.83 | 0 | 0 | 100
Total | [13 empty] | 35.35 | 20.41 | 57.74