## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Nadangahat Piped Water Supply Scheme | SM/07801 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Dhamai village and Dhamai habitation of Nadanghat piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-558/BWD/2020-21) | Assistant Engineer |  | ORD/000255/2020-2021 | 4120/BWD | 16/10/2020 | 15/11/2020 | NANDY UDYOG | 4.85 | 4.85 | 100 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Nadangahat Piped Water Supply Scheme | SM/07801 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Dhamai village and Nimar habitation of Nadanghat piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-389/BWD/2020-21) | Assistant Engineer |  | ORD/000258/2020-2021 | 4121/BWD | 16/10/2020 | 15/11/2020 | RUPALI ENTERPRISE | 4.86 | 4.86 | 100 | 1
3 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Nadangahat Piped Water Supply Scheme | SM/07801 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Nadanghat Piped Water Supply Scheme at Kundapara village & Nadanghat village, Purbasthali - I Block under Burdwan Division, PHE Dte. (Agreement No. 700/BWD of 2020-2021) | Assistant Engineer |  | ORD/000334/2020-2021 | 1543/BWD | 22/02/2021 | 23/04/2021 | MAA LAXMI ENTERPRISE | 51.66 | 0 | 0 | 1
4 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Nadangahat Piped Water Supply Scheme | SM/07801 | Retrofitting | Providing functional household tap connection (FHTC) from existing distribution system within the command area of Nadanghat piped water supply scheme at Kundapara village (37 nos FHTC) & Nadanghat village (75 nos FHTC), Purbasthali-I Block within Kalna Sub-Division under Burdwan Division, PHE Dte. (Sl No-B) | Assistant Engineer |  | ORD/000470/2021-2022 | 153/KSD | 15/02/2022 | 02/03/2022 | MAA LAXMI ENTERPRISE | 4.51 | 0 | 0 | 1
5 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Nadangahat Piped Water Supply Scheme | SM/07801 | Retrofitting | Hire & fuel charges of vehicle (Car No.-WB-04G-7127) for the office of the Assistant Engineer, Kalna Sub-Division, PHE Dte. for the month of December22 to February'23. |  |  | BILL/00118/2023-2024 | 30/JJM | 19/04/2023 | 19/04/2023 | PARTHA PRATIM ACHARYA | 1.19 | 0 | 0 | 0
Total | [13 empty] | 67.08 | 9.71 | 14.48