## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Dirghapara Piped Water Supply Scheme at Purbasthali-I Block | SM/07804 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Dirghapara village and Dirghapara (Part-B) habitation of Dirghapara piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-484/BWD/2020-21) | Assistant Engineer |  | ORD/000175/2020-2021 | 4119/BWD | 16/10/2020 | 15/11/2020 | SK NUR ALAM | 4.86 | 4.86 | 100 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Dirghapara Piped Water Supply Scheme at Purbasthali-I Block | SM/07804 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Kharashgram (Part) village (Kharashgram (Part) habitation) of Dirghapara Piped Water Supply Scheme within Kalna Sub-Divn. under Burdwan Division, PHE. Dte. (Part - B) [Sl. No. : ¿11¿] | Assistant Engineer |  | ORD/000649/2020-2021 | 61/BWD | 05/01/2021 | 20/01/2021 | SK NUR ALAM | 4.86 | 4.86 | 100 | 1
3 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Dirghapara Piped Water Supply Scheme at Purbasthali-I Block | SM/07804 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Kharashgram (Part) village , Kharashgram (Part) habitation of Dirghapara piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. [Part-C][SL NO.-12] | Assistant Engineer |  | ORD/000705/2020-2021 | 62/BWD | 05/01/2021 | 20/01/2021 | INVENT ENGINEERS CO. OPERATIVE SOCIETY LTD. | 4.84 | 4.84 | 100 | 1
4 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Dirghapara Piped Water Supply Scheme at Purbasthali-I Block | SM/07804 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Kharashgram (Part) village (Kharashgram (Part) habitation) of Dirghapara Piped Water Supply Scheme within Kalna Sub-Divn. under Burdwan Division, PHE. Dte. (Part - A) [Sl. No. : ¿10¿] | Assistant Engineer |  | ORD/000197/2021-2022 | 6231/BWD | 01/11/2021 | 16/11/2021 | HAFIJUR RAHAMAN MIDYA | 4.86 | 0 | 0 | 1
5 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Dirghapara Piped Water Supply Scheme at Purbasthali-I Block | SM/07804 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Kharashgram (Part) village (Kharashgram (Part) habitation) of Dirghapara Piped Water Supply Scheme within Kalna Sub-Divn. under Burdwan Division, PHE. Dte. (Part - B) [Sl. No. : ¿11¿] | Assistant Engineer |  | ORD/000198/2021-2022 | 6232/BWD | 01/11/2021 | 16/11/2021 | SK NUR ALAM | 4.86 | 0 | 0 | 1
6 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Dirghapara Piped Water Supply Scheme at Purbasthali-I Block | SM/07804 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Dirghapara village and Dirghapara (Part-A) habitation of Dirghapara Piped Water Supply Scheme within Kalna Sub-Divn. under Burdwan Division, PHE. Dte. [Phase - I] [GROUP : ¿8A¿] | Assistant Engineer |  | ORD/000121/2021-2022 | 4391/BWD | 31/08/2021 | 30/09/2021 | HAFIJUR RAHAMAN MIDYA | 4.55 | 4.1 | 90.08 | 1
7 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Dirghapara Piped Water Supply Scheme at Purbasthali-I Block | SM/07804 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Kharashgram (Part) village (Kharashgram (Part) habitation) of Dirghapara Piped Water Supply Scheme within Kalna Sub-Divn. under Burdwan Division, PHE. Dte. (Part - A) [Sl. No. : ¿10¿] | Assistant Engineer |  | ORD/000648/2020-2021 | 60/BWD | 05/01/2021 | 20/01/2021 | HAFIJUR RAHAMAN MIDYA | 4.86 | 4.86 | 100 | 1
8 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Dirghapara Piped Water Supply Scheme at Purbasthali-I Block | SM/07804 | Retrofitting | Extension of 63 mm dia UPVC pipeline to provide house connection at different leftout portion of Dirghapara w/s scheme within Kalna Sub-Division under Burdwan Division, PHE Dte.[Sl-E] | Assistant Engineer |  | ORD/000937/2020-2021 | 171/KSD | 19/02/2021 | 21/03/2021 | SK RAJU | 1.78 | 0 | 0 | 1
9 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Dirghapara Piped Water Supply Scheme at Purbasthali-I Block | SM/07804 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Kharashgram (Part) village (Kharashgram (Part) habitation) of Dirghapara Piped Water Supply Scheme within Kalna Sub-Divn. under Burdwan Division, PHE. Dte. (Part - C) [Sl. No. : ¿12¿] | Assistant Engineer |  | ORD/000205/2021-2022 | 6401/BWD | 16/11/2021 | 01/12/2021 | INVENT ENGINEERS CO. OPERATIVE SOCIETY LTD. | 4.84 | 0 | 0 | 1
10 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Dirghapara Piped Water Supply Scheme at Purbasthali-I Block | SM/07804 | Retrofitting | Restoration of UPVC pipeline which damaged during construction of PCC road & providing FHTC work at DIRGHAPARA Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. |  |  | ORD/000949/2023-2024 | 5594/BWD | 20/12/2023 | 19/01/2024 | UTPAL NANDI | 8.31 | 0 | 0 | 0
11 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Dirghapara Piped Water Supply Scheme at Purbasthali-I Block | SM/07804 | Retrofitting | Extension of different dia UPVC pipeline at the leftout portion of Kharoshgram village of Dirghapara PWSS within Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/000243/2021-2022 | 6106/BWD | 08/10/2021 | 07/11/2021 | M/S UNIQUE | 6.67 | 0 | 0 | 1
12 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Dirghapara Piped Water Supply Scheme at Purbasthali-I Block | SM/07804 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Jagarpur & Mugura village of Mugura Piped Water Supply Scheme within Headquarters under Burdwan Division, PHE. Dte. [Phase - I] [GROUP : ¿3B¿] (Agreement no.238/BWD of 2020-21) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000136/2020-2021 | 4118/BWD | 16/10/2020 | 15/11/2020 | HAFIJUR RAHAMAN MIDYA | 4.92 | 4.86 | 98.92 | 1
13 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Dirghapara Piped Water Supply Scheme at Purbasthali-I Block | SM/07804 | Retrofitting | Different types of works involve in connection with Augmentation of DIRGHAPARA (SM/07804) Water Supply Scheme, MOUDANGA (SM/ 14020) Water supply Scheme & BHANDARTIKURI (SM/14925) Water Supply Scheme under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000357/2024-2025 | 2912/BWD | 25/07/2024 | 29/09/2025 | BANSBERIA CONSTRUCTION CO. | 293.38 | 0 | 0 | 22
Total | [13 empty] | 353.57 | 28.38 | 8.03