## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of kalyanpur Piped Water Supply Scheme at Kalna-II Block | SM/07806 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Kalyanpur (Part) village, Kalyan (Part) habitation of Kalyanpur piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. (Part-A)[SL NO.-07] | Assistant Engineer |  | ORD/000691/2020-2021 | 57/BWD | 05/01/2021 | 20/01/2021 | SETH ENTERPRISE | 4.86 | 9.73 | 200 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of kalyanpur Piped Water Supply Scheme at Kalna-II Block | SM/07806 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Kalyanpur (Part) village (Kalyanpur Part habitation) of Kalyanpur piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte.(Part-B)[SL NO.-08] | Assistant Engineer |  | ORD/000744/2020-2021 | 58/BWD | 05/01/2021 | 20/01/2021 | BISHWAJIT DAS | 4.86 | 9.72 | 200 | 1
3 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of kalyanpur Piped Water Supply Scheme at Kalna-II Block | SM/07806 | Retrofitting | Sinking of 250 X 150mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CM) and UPVC Deep Well Screen (RMS) for 2nd TW Site of KALYANPUR & its adjoining mouzas Piped Water Supply Scheme, Block ? Kalna ? II, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/000546/2022-2023 | 5128/BWD | 21/11/2022 | 21/12/2022 | MUNSHI ENTERPRISE | 8.72 | 8.16 | 93.53 | 100
4 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of kalyanpur Piped Water Supply Scheme at Kalna-II Block | SM/07806 | Retrofitting | Digital structurization of pipeline alignment and asset evaluation including holistic design, preparation of design drawings of overall LDS & preparation of estimate for 03 Nos. Piped W/S. Schemes under Kalna II Block under Kalna Sub-Division under Burdwan Division, PHE. Dte. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000336/2024-2025 | 3016/BWD | 05/08/2024 | 25/08/2024 | HORIZEN | 7.55 | 2.52 | 33.4 | 100
Total | [13 empty] | 26 | 30.13 | 115.89