## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Tehata Piped Water Supply Scheme at Kalna-II Block | SM/07812 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Tehata (Part) village Tehata (Part) habitation of Tehata piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. [SL NO.-05] | Assistant Engineer |  | ORD/000689/2020-2021 | 1223/BWD | 11/02/2021 | 26/02/2021 | ROY & ROY CONSTRUCTION | 3.16 | 3.16 | 100 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Tehata Piped Water Supply Scheme at Kalna-II Block | SM/07812 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Bajitpur village, Bajit habitation & Jhikra village (Jhikra habitation) of Tehata piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. [SL NO.-02] | Assistant Engineer |  | ORD/000692/2020-2021 | 52/BWD | 05/01/2021 | 20/01/2021 | YOUNG ENGINEERS CO.-OPERATIVE SOCIETY LTD. | 4.86 | 4.86 | 100 | 1
3 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Tehata Piped Water Supply Scheme at Kalna-II Block | SM/07812 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Baitipara village (Baitipara Habitation) of Tehata piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. [Sl No.-01] | Assistant Engineer |  | ORD/000709/2020-2021 | 51/BWD | 05/01/2021 | 20/01/2021 | SUKANTA DEY | 4.87 | 0 | 0 | 1
4 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Tehata Piped Water Supply Scheme at Kalna-II Block | SM/07812 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Baitipara village (Baitipara habitation) of Tehata Piped Water Supply Scheme within Kalna Sub-Divn. under Burdwan Division, PHE. Dte. [Sl. No. : ¿01¿] | Assistant Engineer |  | ORD/000123/2021-2022 | 4020/BWD | 05/08/2021 | 20/08/2021 | SUKANTA DEY | 3.23 | 0 | 0 | 1
5 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Tehata Piped Water Supply Scheme at Kalna-II Block | SM/07812 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Tehata (Part) village, Tehata (Part) habitation of Tehata piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. [SL NO.-05] | Assistant Engineer |  | ORD/000690/2020-2021 | 55/BWD | 05/01/2021 | 20/01/2021 | ROY & ROY CONSTRUCTION | 4.86 | 4.86 | 100 | 1
6 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Tehata Piped Water Supply Scheme at Kalna-II Block | SM/07812 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Kutubpur (Part) village (Kutub Habitation) & Suipara village (Suipara Habitation) of Tehata piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. [Sl No.-04] | Assistant Engineer |  | ORD/000723/2020-2021 | 54/BWD | 05/01/2021 | 20/01/2021 | INVENT ENGINEERS CO. OPERATIVE SOCIETY LTD. | 4.84 | 4.84 | 100 | 1
7 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Tehata Piped Water Supply Scheme at Kalna-II Block | SM/07812 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Tehata (Part) village (Bajitpur & Sarpukur habitation) of Tehata piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. [SL NO.-06] | Assistant Engineer |  | ORD/000693/2020-2021 | 56/BWD | 05/01/2021 | 20/01/2021 | M/S UNIQUE | 4.86 | 4.86 | 100 | 1
8 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Tehata Piped Water Supply Scheme at Kalna-II Block | SM/07812 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Tehata Piped Water Supply Scheme at Bajitpur (P), Jhiekra (P), Habibpur (P), Narenga Kutubpur (P) & Saipara (P) Village (Mouza), Kalna-II Block under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/000254/2021-2022 | 6640/BWD | 29/11/2021 | 29/12/2021 | INVENT ENGINEERS CO. OPERATIVE SOCIETY LTD. | 26.96 | 0 | 0 | 1
9 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Tehata Piped Water Supply Scheme at Kalna-II Block | SM/07812 | Retrofitting | Providing FHTC work at Agradaha village (25 Nos), Jhikra village (20 Nos), Kutubpur village (122 Nos) Habibpur village (232 Nos) & Bajitpur village (16 Nos) under Tehata Zone-II Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. |  |  | ORD/000884/2023-2024 | 5515/BWD | 14/12/2023 | 13/01/2024 | YOUNG ENGINEERS CO.-OPERATIVE SOCIETY LTD. | 23.96 | 0 | 0 | 0
10 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Tehata Piped Water Supply Scheme at Kalna-II Block | SM/07812 | Retrofitting | Providing FHTC work at Suipara village (13 Nos), Tehata village (52 Nos), Bajitpur village (18 Nos) Narenga village (282 nos) & Baitipara village (52 Nos) under TEHATA Zone-I Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. |  |  | ORD/000883/2023-2024 | 5516/BWD | 14/12/2023 | 13/01/2024 | YOUNG ENGINEERS CO.-OPERATIVE SOCIETY LTD. | 19.32 | 0 | 0 | 0
11 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Tehata Piped Water Supply Scheme at Kalna-II Block | SM/07812 | Retrofitting | Work order for " Providing Functional house hold tap connections for Sajal Gram Village within Kalna-II Block under Kalna Sub-Division under Burdwan Division, PHE Dte. (Tehata Water Supply Scheme)" | Assistant Engineer | JUNIOR ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | ORD/000037/2023-2024 | 345/KSD | 17/04/2023 | 17/05/2023 | ARINDAM BHATTACHARYA | 0.88 | 0 | 0 | 100
12 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Tehata Piped Water Supply Scheme at Kalna-II Block | SM/07812 | Retrofitting | Hire & fuel charges of vehicle Car No.-WB-04G-7127 for the month of July & August'2023. |  |  | BILL/01047/2023-2024 | 767/JJM | 12/10/2023 | 12/10/2023 | PARTHA PRATIM ACHARYA | 0.78 | 0 | 0 | 0
13 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Tehata Piped Water Supply Scheme at Kalna-II Block | SM/07812 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Kutubpur (Part) village (Habibpur Habitation) of Tehata piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. [SL NO.-03] | AE(HQs) | J.E. 2 BURDWAN | ORD/000713/2020-2021 | 53/BWD | 05/01/2021 | 20/01/2021 | TAPAS KUMAR ROY | 4.86 | 4.86 | 100 | 0
14 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Tehata Piped Water Supply Scheme at Kalna-II Block | SM/07812 | Retrofitting | Vehicle bill [car No.-WB-04G-7127] for the month of October & November'2023. |  |  | BILL/02061/2023-2024 | 1321/JJM | 01/02/2024 | 01/02/2024 | PARTHA PRATIM ACHARYA | 0.73 | 0 | 0 | 0
15 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Tehata Piped Water Supply Scheme at Kalna-II Block | SM/07812 | Retrofitting | Vehicle bill for the month of August & September'2023. |  |  | BILL/01675/2023-2024 | 1139/JJM | 29/12/2023 | 29/12/2023 | MD HASIN | 0.77 | 0 | 0 | 0
16 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Tehata Piped Water Supply Scheme at Kalna-II Block | SM/07812 | Retrofitting | Different types of works involve in connection with Augmentation of TEHATA Zone-I & II (SM/16301) Water Supply Scheme, CHAKSIMLA (SM/15586) Water Supply Scheme & DWARIATON (SM/16285) Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER RWS KALNA2 | ORD/000162/2024-2025 | 2201/BWD | 13/06/2024 | 05/07/2026 | M/S ASHA CONSTRUCTION | 449.98 | 0 | 0 | 25
Total | [13 empty] | 558.92 | 27.45 | 4.91