## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Sahhosenpur Piped Water Supply Scheme at Jamalpur Block | SM/07813 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Sahahosenpur Piped Water Supply Scheme at Srikrishnapur Village, Rajarampur Village (2 Nos. habitations), Paikpara Village, Jotdakshin Village & Jotsriram Village, Jamalpur Block under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000646/2020-2021 | 1690/BWD | 24/02/2021 | 25/04/2021 | DIPAK ROY | 70.56 | 9.56 | 13.54 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Sahhosenpur Piped Water Supply Scheme at Jamalpur Block | SM/07813 | Retrofitting | Construction of boundary wall including land development at 3rd Tube Well site of Sahhosenpur water supply scheme under Jamalpur Block of Burdwan Division, PHE Dte. (Length -58.00 Mtr, Col-21 Nos). GROUP : D | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000083/2022-2023 | 817/BSD | 20/05/2022 | 04/07/2022 | SARKAR CONSTRUCTION | 3.47 | 0 | 0 | 1
3 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Sahhosenpur Piped Water Supply Scheme at Jamalpur Block | SM/07813 | Retrofitting | Extension of pipeline including providing FHTC for SAHHOSENPUR Piped Water Supply Scheme at Jotdakshin (6 Nos), Jotshiram (20 Nos) Habitation for Sajal Gram (As per field verification report duly signed by Pradhan for Har Ghar Jal Certification) within Jamalpur Block under Burdwan Division, PHE Dte. Gr.T. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000356/2022-2023 | 1341/BSD | 02/08/2022 | 07/08/2022 | ROY BISWAS CONSTRUCTION | 0.95 | 0 | 0 | 1
4 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Sahhosenpur Piped Water Supply Scheme at Jamalpur Block | SM/07813 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Sahahosenpur (Part) village (Sahahosenpur (Part) habitation) of Sahahosenpur Piped Water Supply Scheme within Burdwan Sub-Divn. under Burdwan Division, PHE. Dte. (Part - A) [Sl. No. : ¿17¿] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000539/2020-2021 | 816/BWD | 01/02/2021 | 16/02/2021 | ROY BISWAS CONSTRUCTION | 4.86 | 0 | 0 | 1
5 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Sahhosenpur Piped Water Supply Scheme at Jamalpur Block | SM/07813 | Retrofitting | Extension of pipeline for Sahhosenpur water supply scheme at Sahhosenpur village (Near Masjid) within Jamalpur Block under Burdwan Division, PHE Dte.[Gr.-B] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000281/2021-2022 | 1212/BSD | 09/09/2021 | 09/10/2021 | ROY BISWAS CONSTRUCTION | 4.96 | 0 | 0 | 1
6 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Sahhosenpur Piped Water Supply Scheme at Jamalpur Block | SM/07813 | Retrofitting | Extension of pipeline for Sahhosenpur water supply scheme at Jotsrirram village within Jamalpur Block under Burdwan Division, PHE Dte.[Gr.-C] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000320/2021-2022 | 1333/BSD | 30/09/2021 | 30/10/2021 | PREMANANDA ROY BISWAS | 4.52 | 0 | 0 | 1
7 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Sahhosenpur Piped Water Supply Scheme at Jamalpur Block | SM/07813 | Retrofitting | Pipeline laying at different culvert crossing for damage of PMGSY Road of Sahhosenpur water supply scheme at Jamalpur Block under Burdwan Division, PHE Dte. [Gr.-F] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000552/2021-2022 | 1481/BSD | 09/11/2021 | 09/12/2021 | ROY BISWAS CONSTRUCTION | 3.53 | 0 | 0 | 1
8 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Sahhosenpur Piped Water Supply Scheme at Jamalpur Block | SM/07813 | Retrofitting | Extension of pipeline for Sahhosenpur water supply scheme at Srikrishnapur and Rajarampur village within Jamalpur Block under Burdwan Division, PHE Dte.[Gr.-H] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000553/2021-2022 | 1483/BSD | 09/11/2021 | 09/12/2021 | DIPAK ROY | 4.7 | 0 | 0 | 1
9 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Sahhosenpur Piped Water Supply Scheme at Jamalpur Block | SM/07813 | Retrofitting | Extension of pipeline for Sahhosenpur water supply scheme at Jotdakshin village within Jamalpur Block under Burdwan Division, PHE Dte.[Gr.-D] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000555/2021-2022 | 1524/BSD | 18/11/2021 | 18/12/2021 | THREE MAA ENTERPRISE | 4.81 | 0 | 0 | 1
10 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Sahhosenpur Piped Water Supply Scheme at Jamalpur Block | SM/07813 | Retrofitting | Extension of pipeline for Providing FHTC at Srikrishnapur village under SAHAHOSENPUR Piped Water Supply Scheme at Srikrishnapur village within Jamalpur Block , under Burdwan Division, PHE Dte. Group : B | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000089/2022-2023 | 829/BSD | 23/05/2022 | 22/06/2022 | MMS CONSTRUCTIONS PVT LTD | 4.62 | 0 | 0 | 1
11 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Sahhosenpur Piped Water Supply Scheme at Jamalpur Block | SM/07813 | Retrofitting | Construction of different slab of damage valve chamber due to widening of PMGSY ROAD and sand filling of PMGSY ROAD of Sahahossenpur water supply scheme under Jamalpur Block of Burdwan Division, PHE Dte. Gr.E. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000092/2022-2023 | 832/BSD | 23/05/2022 | 22/06/2022 | ROY BISWAS CONSTRUCTION | 2.68 | 0 | 0 | 1
12 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Sahhosenpur Piped Water Supply Scheme at Jamalpur Block | SM/07813 | Retrofitting | Laying of interconnection of the Pump No.-1, 2 & 3 with OHR and distribution main of 350 mm dia for Sahhosenpur water supply scheme within Jamalpur Block under Burdwan Division, PHE Dte.[Gr.-C] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000720/2021-2022 | 1482/BSD | 09/11/2021 | 09/12/2021 | THREE MAA ENTERPRISE | 4.83 | 0 | 0 | 1
13 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Sahhosenpur Piped Water Supply Scheme at Jamalpur Block | SM/07813 | Retrofitting | Hire & fuel charges of vehicle Car No.-WB-41G-8280 for the month of January to July'2023. |  |  | BILL/01042/2023-2024 | 852/JJM | 30/10/2023 | 30/10/2023 | MD HASIN | 2.5 | 0 | 0 | 0
14 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Sahhosenpur Piped Water Supply Scheme at Jamalpur Block | SM/07813 | Retrofitting | Hire & fuel charges of vehicle Car No.-wb-41H-9788 for the month of August'2023 |  |  | BILL/01037/2023-2024 | 747/JJM | 11/10/2023 | 11/10/2023 | SK. ASRAFUDDIN | 0.4 | 0 | 0 | 0
15 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Sahhosenpur Piped Water Supply Scheme at Jamalpur Block | SM/07813 | Retrofitting | Replace Damaged & deface FHTC(By WBSRDA)with all with accessories within the command area of SAHHOSENPUR Piped W/S Scheme at SahhosenpurSaikh Para and Rajarampur village,Jamalpur Development Block under Burdwan Division,PHE Dte. |  | RWS_JAMALPUR | ORD/000156/2024-2025 | 1045/BSD | 10/06/2024 | 10/07/2024 | SARKAR CONSTRUCTION | 0.83 | 0 | 0 | 100
16 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Sahhosenpur Piped Water Supply Scheme at Jamalpur Block | SM/07813 | Retrofitting | Vehicle bill for the month of October'2023. |  |  | BILL/01678/2023-2024 | 1040/JJM | 11/12/2023 | 11/12/2023 | SK.ASFIA | 0.38 | 0 | 0 | 0
17 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Sahhosenpur Piped Water Supply Scheme at Jamalpur Block | SM/07813 | Retrofitting | Vehicle Bill (Car No.-WB-41H-9788) for the month of October'2023. |  |  | BILL/01677/2023-2024 | 1033/JJM | 11/12/2023 | 11/12/2023 | SK. ASRAFUDDIN | 0.37 | 0 | 0 | 0
18 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Sahhosenpur Piped Water Supply Scheme at Jamalpur Block | SM/07813 | Retrofitting | Vehicle Bill [Car No.-WB-41H-9788] for the month of December'23. |  |  | BILL/02062/2023-2024 | 1322/JJM | 01/02/2024 | 01/02/2024 | SK. ASRAFUDDIN | 0.4 | 0 | 0 | 0
19 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Sahhosenpur Piped Water Supply Scheme at Jamalpur Block | SM/07813 | Retrofitting | Construction of Boundary wall, Land Development for various PWSS, Block- Jamalpur, District:- Purba-Bardhaman within Burdwan Sub Division under Burdwan Division PHE Dte. | AE(HQs),AE(HQs), Burdwan Division, PHE Dte. | Junior Engineer, Burdwan Division | ORD/001100/2024-2025 | 433/BWD | 20/01/2025 | 20/05/2025 | RABINDRA NATH GORANG | 132.64 | 0 | 0 | 40
Total | [13 empty] | 252.02 | 9.56 | 3.79